## CoverSheet
Draft Transmission Outage Programme 2027 (TOP27)
This report sets out the draft TOP27 outage programme, covering outages associated with both capital projects and maintenance works. As the programme remains under development, changes should be expected before the final TOP27 programme is issued.
Inclusion of an outage in this draft programme does not guarantee its inclusion in the final TOP27 programme or that the outage will proceed as currently scheduled. Additional outages are also being considered for inclusion, which may require outages currently shown in the draft programme to be rescheduled, amended or withdrawn.

## GEN_ALL
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-27-DND-T121-02 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | Unknown | Unknown |  | Planned | January | March
TO-27-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 26 | 20 | 20 | Proposed | 04/01/2027 | 29/01/2027
TO-27-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 53 | 38 | 38 | Proposed | 04/01/2027 | 25/02/2027
TO-27-110 kV A1 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A1 | Unknown | Unknown | 9 | Planned | January | January
TO-27-110 kV B1 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B1 | Unknown | Unknown | 9 | Planned | January | January
TO-27-CKG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-2CB | Unknown | Unknown | 9 | Planned | January | January
TO-27-CKG-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 9 | Planned | January | January
TO-27-CKG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-2CB | Unknown | Unknown | 9 | Planned | January | January
TO-27-CKG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 9 | Planned | January | January
TO-27-KRA-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 5 | 5 | 5 | Proposed | 04/01/2027 | 08/01/2027
TO-27-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 5 | 5 | 5 | Proposed | 04/01/2027 | 08/01/2027
TO-27-220 kV A1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A1 | Unknown | Unknown | 40 | Planned | January | March
TO-27-220 kV B1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B1 | Unknown | Unknown | 40 | Planned | January | March
TO-27-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | Unknown | Unknown | 40 | Planned | January | March
TO-27-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 142 | Planned | January | July
TO-27-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown | 142 | Planned | January | July
TO-27-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | Unknown | Unknown | 145 | Planned | January | August
TO-27-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | Unknown | Unknown | 145 | Planned | January | August
TO-27-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 18 | 14 | 14 | Proposed | 05/01/2027 | 22/01/2027
TO-27-LOU-T2102-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | Unknown | Unknown |  | Planned | January | August
TO-27-TTU-131-01 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | 2 | 2 | 2 | Proposed | 05/01/2027 | 06/01/2027
TO-27-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 1 | 1 | 1 | Proposed | 06/01/2027 | 06/01/2027
TO-27-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 29 | 20 | 20 | Proposed | 06/01/2027 | 03/02/2027
TO-27-FIN-NW-1-04 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 0 | 0 | Proposed | 09/01/2027 | 10/01/2027
TO-27-110 kV A1 @ BAG-01 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110A1 | 5 | 5 | 5 | Proposed | 11/01/2027 | 15/01/2027
TO-27-110 kV B1 @ BAG-01 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110B1 | 5 | 5 | 5 | Proposed | 11/01/2027 | 15/01/2027
TO-27-BAG-110K1-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110K1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 19 | 15 | 15 | Reference (Proposed) | 11/01/2027 | 29/01/2027
TO-27-BLK,T-BLK-1-01 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-CKM-PB-1-01 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-CLA-KRA-1-01 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 12 | 10 | 10 | Proposed | 11/01/2027 | 22/01/2027
TO-27-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 5 | 5 | 5 | Proposed | 11/01/2027 | 15/01/2027
TO-27-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 2 | 2 | 2 | Proposed | 11/01/2027 | 12/01/2027
TO-27-AUN-T123-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T123 | 2 | 2 | 2 | Proposed | 12/01/2027 | 13/01/2027
TO-27-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 4 | 4 | 4 | Proposed | 12/01/2027 | 15/01/2027
TO-27-LYT-MID-1-01 | 110kV FEEDER - LYSAGHTSTOWN 110-MIDLETON 110-1 | 176 | 120 | 120 | Proposed | 12/01/2027 | 06/07/2027
TO-27-LYT-MID-1-02 | 110kV FEEDER - LYSAGHTSTOWN 110-MIDLETON 110-1 | Unknown | Unknown | 120 | Planned | January | July
TO-27-MID-110SA1-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | Unknown | Unknown | 120 | Planned | January | July
TO-27-MID-110SA2-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | Unknown | Unknown | 120 | Planned | January | July
TO-27-MID-T101-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T101 | Unknown | Unknown | 120 | Reference (Planned) | January | July
TO-27-MID-T141-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 38-T141 | Unknown | Unknown | 120 | Reference (Planned) | January | July
TO-27-CBT-CKG-2-01 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | Unknown | Unknown | 2 | Planned | January | January
TO-27-KPG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 1 | 1 | 1 | Proposed | 13/01/2027 | 13/01/2027
TO-27-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 1 | 1 | 1 | Proposed | 15/01/2027 | 15/01/2027
TO-27-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 10 | 8 | 8 | Proposed | 18/01/2027 | 27/01/2027
TO-27-CAH-TIP-1-03 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | Unknown | Unknown | 8 | Planned | January | January
TO-27-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 12 | 10 | 10 | Proposed | 18/01/2027 | 29/01/2027
TO-27-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 4 | 4 | 4 | Proposed | 18/01/2027 | 21/01/2027
TO-27-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 12 | 10 | 10 | Proposed | 18/01/2027 | 29/01/2027
TO-27-TIP-110SA1-02 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | Unknown | Unknown | 8 | Planned | January | January
TO-27-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | Unknown | Unknown | 8 | Planned | January | January
TO-27-400 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | Unknown | Unknown | 25 | Planned | January | February
TO-27-BAG-CLG-1-01 | 110kV FEEDER - BARNAGEERAGH 110-CLOGHRAN 110-1 | 3 | 3 | 3 | Proposed | 19/01/2027 | 21/01/2027
TO-27-OBE-110K1-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K1 | 1 | 1 | 1 | Proposed | 19/01/2027 | 19/01/2027
TO-27-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | 22 | 15 | 15 | Proposed | 19/01/2027 | 09/02/2027
TO-27-WOO-T4204-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 60 | Planned | January | April
TO-27-BNK-CBT-2-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 1 | 1 | 1 | Proposed | 20/01/2027 | 20/01/2027
TO-27-BNK-T121-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T121 | Unknown | Unknown | 2 | Planned | January | January
TO-27-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 43 | 30 | 30 | Proposed | 21/01/2027 | 04/03/2027
TO-27-CF-CLO-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 5 | 3 | 3 | Proposed | 22/01/2027 | 26/01/2027
TO-27-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 1 | 1 | 1 | Proposed | 22/01/2027 | 22/01/2027
TO-27-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 5 | 5 | 5 | Proposed | 25/01/2027 | 29/01/2027
TO-27-CLA-KRA-1-02 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-CLA-MAC-1-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | Unknown | Unknown | 14 | Planned | January | February
TO-27-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 12 | 9 | 9 | Proposed | 25/01/2027 | 05/02/2027
TO-27-KUD-T102-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T102 | 2 | 2 | 2 | Proposed | 25/01/2027 | 26/01/2027
TO-27-KNR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 25/01/2027 | 29/01/2027
TO-27-220 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-220 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | January | January
TO-27-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | January | January
TO-27-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | Unknown | Unknown | 5 | Planned | January | January
TO-27-BLU-T131-01 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 2 | 2 | 2 | Proposed | 26/01/2027 | 27/01/2027
TO-27-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Proposed | 26/01/2027 | 27/01/2027
TO-27-GAR-PLA-1-01 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 2 | 2 | 2 | Proposed | 26/01/2027 | 27/01/2027
TO-27-MCE-T102-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T102 | Unknown | Unknown | 120 | Reference (Planned) | January | July
TO-27-GI GIS-220K2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 1 | 1 | 1 | Proposed | 27/01/2027 | 27/01/2027
TO-27-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-AGL-SH-1-03 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-AA GIS-ENN-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-AA GIS-T102-03 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-CDA-SH-2-01 | 110kV FEEDER - CLONDELARA 110-SHANNONBRIDGE 110-2 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-CDA-T102/4-01 | GENERATOR TRANSFORMER - CLONDELARA 110-CLONDELARA G2/4-T102/4 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-110 kV A2 @ ENN-01 | BUSBAR SECTION - ENNIS 110-ENNIS 110-110A2 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-ENN-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-110 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-AD-220K1-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 2 | 2 | 2 | Proposed | 02/02/2027 | 03/02/2027
TO-27-ARV-SKL-1-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | Unknown | Unknown | 1 | Planned | February | February
TO-27-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | February | February
TO-27-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | Unknown | Unknown | 4 | Planned | February | February
TO-27-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | Unknown | Unknown | 9 | Planned | February | February
TO-27-GAR-GOR-1-01 | 110kV FEEDER - GARBALLAGH 110-GORMAN 110-1 | Unknown | Unknown | 9 | Planned | February | February
TO-27-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 99 | Planned | February | June
TO-27-KLN-SH-1-03 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 99 | Planned | February | June
TO-27-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | Unknown | Unknown | 4 | Planned | February | February
TO-27-220 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | Unknown | Unknown | 95 | Planned | February | June
TO-27-220 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | Unknown | Unknown | 95 | Planned | February | June
TO-27-MUL-RTN-01 | 110kV FEEDER - MULLINGAR 110-RATTIN 110-1 | Unknown | Unknown | 9 | Planned | February | February
TO-27-BGT-KKY-1-01 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-BGT-141-01 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | February | February
TO-27-BGT-141-02 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | Unknown | Unknown | 30 | Reference (Planned) | February | March
TO-27-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | February | February
TO-27-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-CBT-INC-1-01 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | Unknown | Unknown | 20 | Planned | February | March
TO-27-CBT-INC-1-02 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | Unknown | Unknown | 35 | Planned | February | March
TO-27-FLA-110K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | Unknown | Unknown | 1 | Planned | February | February
TO-27-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | Unknown | Unknown | 2 | Planned | February | February
TO-27-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | Unknown | Unknown | 6 | Planned | February | February
TO-27-ROP-WEX-1-01 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | Unknown | Unknown | 1 | Planned | February | February
TO-27-110 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | Unknown | Unknown | 0 | Planned | February | February
TO-27-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | Unknown | Unknown | 10 | Planned | February | February
TO-27-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | Unknown | Unknown | 15 | Planned | February | February
TO-27-BDA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | Unknown | Unknown | 25 | Planned | February | March
TO-27-BDA-MON-1-02 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-BDA-MON-1-03 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 25 | Planned | February | March
TO-27-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 25 | Planned | February | March
TO-27-BDA-T102-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 25 | Planned | February | March
TO-27-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | Unknown | Unknown | 5 | Planned | February | February
TO-27-DER-T132-01 | GENERATOR TRANSFORMER - DERRYIRON 110-DERRYIRON 33-T132 | 2 | 2 | 2 | Proposed | 08/02/2027 | 09/02/2027
TO-27-DJG-KPG-1-01 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | Unknown | Unknown | 10 | Planned | February | February
TO-27-DJG-KPG-1-03 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | Unknown | Unknown | 10 | Planned | February | February
TO-27-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | Unknown | Unknown | 10 | Planned | February | February
TO-27-FIN GIS-110K5-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | Unknown | Unknown | 10 | Planned | February | February
TO-27-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 10 | Planned | February | February
TO-27-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | Unknown | Unknown | 5 | Planned | February | February
TO-27-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown | 5 | Planned | February | February
TO-27-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | Unknown | Unknown | 70 | Planned | February | May
TO-27-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | Unknown | Unknown | 3 | Planned | February | February
TO-27-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | February | February
TO-27-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | Unknown | Unknown | 10 | Planned | February | February
TO-27-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | Unknown | 1 | Planned | February | February
TO-27-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | Unknown | 1 | Planned | February | February
TO-27-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 7 | Planned | February | February
TO-27-BAN-110SA2-06 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 7 | Planned | February | February
TO-27-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | Unknown | Unknown | 7 | Planned | February | February
TO-27-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | Unknown | 15 | Planned | February | March
TO-27-BAN-T141-02 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | February | February
TO-27-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | Unknown | Unknown | 5 | Planned | February | February
TO-27-CAH-TIP-1-04 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | Unknown | Unknown | 2 | Planned | February | February
TO-27-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 10 | Planned | February | February
TO-27-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | Unknown | 8 | Planned | February | February
TO-27-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 5 | 5 | 5 | Proposed | 15/02/2027 | 19/02/2027
TO-27-TIP-110SA1-03 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-TIP-110SA2-02 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | Unknown | Unknown | 5 | Planned | February | February
TO-27-CDU-GLN-1-01 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | Unknown | Unknown | 4 | Planned | February | February
TO-27-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 2 | Planned | February | February
TO-27-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | Unknown | 8 | Planned | February | February
TO-27-110 kV A1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-110 kV B1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-DND-110K1-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | February | March
TO-27-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | Unknown | Unknown | 10 | Planned | February | March
TO-27-DND-T121-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | Unknown | Unknown | 5 | Planned | February | February
TO-27-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | Unknown | Unknown | 1 | Planned | February | February
TO-27-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | Unknown | 0 | Planned | February | February
TO-27-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | Unknown | Unknown | 0 | Planned | February | February
TO-27-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | Unknown | Unknown | 0 | Planned | February | February
TO-27-AD-GGO-1-04 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 0 | Planned | February | February
TO-27-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 0 | Planned | February | February
TO-27-220 kV B1 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220B1 | Unknown | Unknown | 0 | Planned | February | February
TO-27-220 kV B2 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220B2 | Unknown | Unknown | 0 | Planned | February | February
TO-27-GGO-T2001-05 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 0 | Planned | February | February
TO-27-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | Unknown | Unknown | 5 | Planned | February | February
TO-27-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | Unknown | Unknown | 17 | Planned | February | March
TO-27-DJG-TRL-1-01 | 110kV FEEDER - DROMBEG 110-TRALEE 110-1 | Unknown | Unknown | 1 | Planned | February | February
TO-27-DJG-TRL-1-04 | 110kV FEEDER - DROMBEG 110-TRALEE 110-1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-FIN GIS-110SA3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | Unknown | Unknown | 10 | Planned | February | March
TO-27-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | Unknown | Unknown | 9 | Planned | February | March
TO-27-KYT-MAY-1-01 | 220kV FEEDER - KELLYSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-KIN-RTN-01 | 110kV FEEDER - KINNEGAD 110-RATTIN 110-1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-110SA1-07 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-110SA2-07 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-CAP2-04 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-LSA-1-06 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-LSA-1-03 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-LSA-1-01 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-LIS-T142-04 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | Unknown | Unknown | 24 | Reference (Planned) | February | March
TO-27-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | Unknown | Unknown | 24 | Reference (Planned) | February | March
TO-27-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-BOG-TTU-1-01 | 110kV FEEDER - BANOGE 110-TULLABEG 110-1 | Unknown | Unknown | 1 | Planned | February | February
TO-27-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | February | February
TO-27-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | Unknown | Unknown | 3 | Planned | February | February
TO-27-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | Unknown | Unknown | 8 | Planned | February | March
TO-27-ATY-T101-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T101 | Unknown | Unknown | 80 | Reference (Planned) | March | June
TO-27-BLC-DND-1-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | Unknown | Unknown | 5 | Planned | March | March
TO-27-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-110 kV A3 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | Unknown | Unknown | 9 | Planned | March | March
TO-27-110 kV B3 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | Unknown | Unknown | 9 | Planned | March | March
TO-27-CKG-110K3-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | Unknown | Unknown | 9 | Planned | March | March
TO-27-CKG-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 9 | Planned | March | March
TO-27-CKG-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 9 | Planned | March | March
TO-27-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-DER-KIN-1-03 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-DJG-T134-01 | GENERATOR TRANSFORMER - DROMBEG 110-DROMBEG 33-T134 | Unknown | Unknown | 5 | Planned | March | March
TO-27-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | Unknown | Unknown | 10 | Planned | March | March
TO-27-KIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | March | March
TO-27-KIN-RTN-02 | 110kV FEEDER - KINNEGAD 110-RATTIN 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | Unknown | 5 | Planned | March | March
TO-27-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 20 | Planned | March | March
TO-27-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 20 | Planned | March | March
TO-27-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | Unknown | Unknown | 14 | Planned | March | March
TO-27-220 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | Unknown | Unknown | 49 | Planned | March | May
TO-27-220 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | Unknown | Unknown | 49 | Planned | March | May
TO-27-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | Unknown | Unknown | 4 | Planned | March | March
TO-27-CF-CLO-2-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | Unknown | Unknown | 3 | Planned | March | March
TO-27-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | Unknown | Unknown | 4 | Planned | March | March
TO-27-220 kV A8 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A8 | Unknown | Unknown | 15 | Planned | March | March
TO-27-220 kV B8 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B8 | Unknown | Unknown | 15 | Planned | March | March
TO-27-INC-SA6-8CB-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA6-8CB | Unknown | Unknown | 15 | Planned | March | March
TO-27-INC-SA8-10CB-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA8-10CB | Unknown | Unknown | 15 | Planned | March | March
TO-27-INC-SB6-8CB-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB6-8CB | Unknown | Unknown | 15 | Planned | March | March
TO-27-INC-SB8-10CB-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB8-10CB | Unknown | Unknown | 15 | Planned | March | March
TO-27-LOU-220K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 7 | Planned | March | March
TO-27-110 kV A2 @ BVK-03 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-110 kV B2 @ BVK-03 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-110K2-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | Unknown | 10 | Planned | March | March
TO-27-220 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-220 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | Unknown | Unknown | 10 | Planned | March | March
TO-27-CBT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | March | March
TO-27-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-CUN-SLI-1-02 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-DFR,T-KIN-1-03 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 9 | Planned | March | March
TO-27-FLA-SLI-1-02 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | Unknown | Unknown | 9 | Planned | March | March
TO-27-KIN-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | March | March
TO-27-KIN-T102-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | Unknown | 5 | Planned | March | March
TO-27-KIN-T102-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | Unknown | 1 | Planned | March | March
TO-27-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | Unknown | Unknown | 5 | Planned | March | March
TO-27-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | Unknown | Unknown | 9 | Planned | March | March
TO-27-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | Unknown | Unknown | 5 | Planned | March | March
TO-27-SLI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | March | March
TO-27-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 9 | Planned | March | March
TO-27-SLI-SRA-2-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 40 | Planned | March | May
TO-27-SLI-SRA-2-04 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 60 | Planned | March | June
TO-27-SLI-T142-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | March | March
TO-27-WOO-400K1-2-03 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown | 5 | Planned | March | March
TO-27-WOO-T4202-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 5 | Planned | March | March
TO-27-WOO-T4204-04 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 5 | Planned | March | March
TO-27-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-AD-GGO-1-02 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-AD-GGO-1-03 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | Unknown | Unknown | 4 | Planned | March | March
TO-27-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 3 | Planned | March | March
TO-27-220 kV A1/A2 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220A1-A2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-220 kV B1/B2 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220B1-B2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-220K1-2-03 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-220K1-2-02 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | Unknown | 8 | Planned | March | March
TO-27-GGO-RAF-1-02 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | Unknown | Unknown | 19 | Planned | March | April
TO-27-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 5 | Planned | March | March
TO-27-GGO-T2001-03 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-T2001-04 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 20 | Planned | March | April
TO-27-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | Unknown | 8 | Planned | March | March
TO-27-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-CBT-CKG-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | Unknown | Unknown | 10 | Planned | March | March
TO-27-220 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 33 | Planned | March | April
TO-27-220 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 33 | Planned | March | April
TO-27-BAL-DEN-1-01 | 110kV FEEDER - BALTRASNA 110-DEENES 110-1 | Unknown | Unknown | 10 | Planned | March | March
TO-27-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | Unknown | Unknown | 1 | Planned | March | March
TO-27-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | Unknown | Unknown | 2 | Planned | March | March
TO-27-MLC-TSB-1-02 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | Unknown | Unknown | 1 | Planned | March | March
TO-27-TSB-110SA1-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | Unknown | Unknown | 5 | Planned | March | March
TO-27-TSB-T141-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | March | March
TO-27-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | Unknown | Unknown | 29 | Planned | March | April
TO-27-BGT-110K1-03 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-110kV B1 @ BGT-01 | BUSBAR SECTION - BALLYRAGGET 110-BALLYRAGGET 110-110B1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BGT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-CBT-KUD-1-01 | 110kV FEEDER - CASTLEBAGOT 110-KILMAHUD 110-1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-GOR-MAY-1-02 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 7 | Planned | March | March
TO-27-GOR-MAY-1-03 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 7 | Planned | March | March
TO-27-BOG-110SA2-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA2 | Unknown | Unknown | 1 | Planned | March | March
TO-27-BOG-T121-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T121 | Unknown | Unknown | 1 | Reference (Planned) | March | March
TO-27-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | Unknown | Unknown | 15 | Planned | March | April
TO-27-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | Unknown | Unknown | 123 | Planned | March | September
TO-27-BAL-110SA1-01 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA1 | Unknown | Unknown | 6 | Planned | March | March
TO-27-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | Unknown | Unknown | 2 | Planned | March | March
TO-27-SH-T2101-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | Unknown | Unknown | 5 | Planned | March | March
TO-27-CBT-KSG-1-01 | 110kV FEEDER - CASTLEBAGOT 110-KISHOGE 110-1 | Unknown | Unknown | 1 | Planned | March | March
TO-27-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | Unknown | Unknown | 1 | Planned | March | March
TO-27-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-CRA-110SA1-01 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-CRA-T141-01 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | March | March
TO-27-CRA-TTU-1-01 | 110kV FEEDER - CRANE 110-TULLABEG 110-1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 8 | Planned | March | April
TO-27-PHT-PLS-1-01 | 110kV FEEDER - PHILIPSTOWN 110-PORTLAOISE 110-1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-BYH-BVK-1-03 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-110 kV A2 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-110 kV B2 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-110K2-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-220 kV A2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-220 kV B2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-220K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-CUL-RTH-1-01 | 110kV FEEDER - CULLENAGH 110-RATHNASKILLOGE 110-1 | Unknown | Unknown | 1 | Planned | March | March
TO-27-TBG-T141-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T141 | Unknown | Unknown | 129 | Reference (Planned) | March | September
TO-27-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | Unknown | Unknown | 5 | Planned | March | April
TO-27-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown | 3 | Planned | March | April
TO-27-BAL-110SA2-01 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA2 | Unknown | Unknown | 6 | Planned | March | April
TO-27-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | Unknown | Unknown | 6 | Planned | March | April
TO-27-BAL-T122-01 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T122 | Unknown | Unknown | 6 | Reference (Planned) | March | April
TO-27-CBT-T2102-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2102 | Unknown | Unknown | 9 | Planned | March | April
TO-27-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | Unknown | Unknown | 8 | Planned | March | April
TO-27-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 6 | Planned | March | April
TO-27-CRA-WEX-1-03 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 9 | Planned | March | April
TO-27-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 7 | Planned | March | April
TO-27-220 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 4 | Planned | March | April
TO-27-FIN-220K1-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | Unknown | Unknown |  | Planned | March | October
TO-27-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 4 | Planned | March | April
TO-27-FIN-NW-1-01 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 88 | Planned | March | August
TO-27-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown |  | Planned | March | August
TO-27-GAL GIS-SAL-1-01 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | Unknown | Unknown | 12 | Planned | March | April
TO-27-GAL GIS-SAL-1-02 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | Unknown | Unknown | 40 | Planned | March | May
TO-27-LLA-TIV-1-01 | 110kV FEEDER - LENALEA 110-TIEVEBRACK 110-1 | Unknown | Unknown | 9 | Planned | March | April
TO-27-LIS-110SA1-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 59 | Planned | March | June
TO-27-LIS-110SA2-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 59 | Planned | March | June
TO-27-WEX-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | March | March
TO-27-WEX-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 9 | Planned | March | April
TO-27-WEX-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | March | April
TO-27-WEX-CAP2-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 9 | Planned | March | April
TO-27-WEX-CAP4-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 9 | Planned | March | April
TO-27-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown | 9 | Reference (Planned) | March | April
TO-27-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown | 9 | Reference (Planned) | March | April
TO-27-400 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | Unknown | Unknown | 5 | Planned | March | April
TO-27-400 kV B2 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | Unknown | Unknown | 5 | Planned | March | April
TO-27-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | Unknown | Unknown | 115 | Planned | March | September
TO-27-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | Unknown | Unknown | 115 | Planned | March | September
TO-27-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | Unknown | Unknown | 115 | Planned | March | September
TO-27-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | Unknown | Unknown | 115 | Planned | March | September
TO-27-DSN-T4201-04 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | Unknown | Unknown | 115 | Planned | March | September
TO-27-INC-PB-1-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | Unknown | Unknown | 15 | Planned | March | April
TO-27-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 15 | Planned | March | April
TO-27-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 87 | Planned | March | August
TO-27-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | Unknown | 2 | Planned | March | April
TO-27-LIS-110SA1-03 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-110SA2-03 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-CAP1-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | Unknown | Unknown | 3 | Planned | March | April
TO-27-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | March | April
TO-27-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | Unknown | Unknown | 2 | Planned | March | April
TO-27-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-CLW-KLS-1-03 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-CLW-KLS-1-02 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL-T141-03 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | April | April
TO-27-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | April | April
TO-27-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-DAL-1-03 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 24 | Planned | April | May
TO-27-DAL,T-STN-1-01 | 110kV FEEDER - DALLOW tee-STONESTOWN 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-STN-1-03 | 110kV FEEDER - DALLOW tee-STONESTOWN 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-220 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 84 | Planned | April | August
TO-27-FIN-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 84 | Planned | April | August
TO-27-GLN-T133-03 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | Unknown | Unknown | 5 | Planned | April | April
TO-27-GI GIS-LON-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LOUGHTOWN 220-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | Unknown | Unknown | 10 | Planned | April | April
TO-27-PA-110SA1-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-PA-110SA2-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 15 | Planned | April | April
TO-27-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | April | April
TO-27-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | Unknown | Unknown | 2 | Planned | April | April
TO-27-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | Unknown | 3 | Planned | April | April
TO-27-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | Unknown | Unknown | 8 | Planned | April | April
TO-27-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | Unknown | Unknown | 2 | Planned | April | April
TO-27-220 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 5 | Planned | April | April
TO-27-220 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B2 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CDU-GLN-1-02 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-DER-KIN-1-04 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DFR-T122-01 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | Unknown | Unknown | 2 | Reference (Planned) | April | April
TO-27-DFR-T122-02 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | Unknown | Unknown | 60 | Reference (Planned) | April | July
TO-27-DFR,T-DFR-1-02 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | Unknown | Unknown | 60 | Planned | April | July
TO-27-DFR,T-DFR-1-01 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DFR,T-KIN-1-01 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 20 | Planned | April | May
TO-27-DFR,T-KIN-1-04 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DFR,T-KIN-1-06 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 60 | Planned | April | July
TO-27-DFR,T-RNW-1-07 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 6 | Planned | April | April
TO-27-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DFR,T-RNW-1-04 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-DFR,T-RNW-1-05 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 60 | Planned | April | July
TO-27-GLN-110K1-01 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-GLN-PLA-1-01 | 110kV FEEDER - GALLANSTOWN 110-PLATIN 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-MAY-RNW-1-01 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | Unknown | 14 | Planned | April | April
TO-27-MAY-RNW-1-03 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-MAY-RNW-1-04 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-MAY-RYB GIS-1-01 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 1 | Planned | April | April
TO-27-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 50 | Planned | April | June
TO-27-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 50 | Planned | April | June
TO-27-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | Unknown | Unknown |  | Planned | April | May
TO-27-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | Unknown | Unknown |  | Planned | April | April
TO-27-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-CLG-CDU-1-01 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-DND-T123-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T123 | Unknown | Unknown | 5 | Planned | April | April
TO-27-FIN GIS-110SB3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | Unknown | Unknown | 10 | Planned | April | April
TO-27-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 15 | Planned | April | April
TO-27-GI-T2102-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 60 | Planned | April | July
TO-27-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | Unknown | 5 | Planned | April | April
TO-27-110 kV A1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-110 kV B1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-KRA-RAF-1-02 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | Unknown | Unknown |  | Planned | April | April
TO-27-110 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-MAY-T2101-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | Unknown | 5 | Planned | April | April
TO-27-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | Unknown | Unknown | 4 | Planned | April | April
TO-27-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown | 100 | Planned | April | September
TO-27-CUN-SLI-1-03 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 14 | Planned | April | April
TO-27-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 14 | Planned | April | April
TO-27-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 14 | Planned | April | April
TO-27-KLN-SH-1-05 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 52 | Planned | April | June
TO-27-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 14 | Planned | April | April
TO-27-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 14 | Planned | April | April
TO-27-SLI-T142-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 14 | Reference (Planned) | April | April
TO-27-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | Unknown | Unknown | 2 | Planned | April | April
TO-27-110 kV A1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | Unknown | Unknown | 111 | Planned | April | September
TO-27-110 kV A2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | Unknown | Unknown | 111 | Planned | April | September
TO-27-110 kV B1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | Unknown | Unknown | 111 | Planned | April | September
TO-27-110 kV B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | Unknown | Unknown | 111 | Planned | April | September
TO-27-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | Unknown | Unknown | 1 | Planned | April | April
TO-27-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CLE-T221-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T221 | Unknown | Unknown | 5 | Planned | April | April
TO-27-110 kV A1 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-110 kV B1 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-KUR-NAV-1-01 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-KUR-T3-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T3 | Unknown | Unknown | 3 | Reference (Planned) | April | April
TO-27-KUR-T4-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T4 | Unknown | Unknown | 3 | Reference (Planned) | April | April
TO-27-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | Unknown | Unknown | 8 | Planned | April | April
TO-27-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CLU-KUD-1-01 | 110kV FEEDER - CLUTTERLAND 110-KILMAHUD 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-110 kV A2 @ OBE-01 | BUSBAR SECTION - OLDBRIDGE 110-OLDBRIDGE 110-110A2 | Unknown | Unknown | 20 | Planned | April | May
TO-27-110 kV B2 @ OBE-01 | BUSBAR SECTION - OLDBRIDGE 110-OLDBRIDGE 110-110B2 | Unknown | Unknown | 20 | Planned | April | May
TO-27-OBE-110K2-02 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K2 | Unknown | Unknown | 20 | Planned | April | May
TO-27-OBE-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SA1-2CB | Unknown | Unknown | 20 | Planned | April | May
TO-27-OBE-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SB1-2CB | Unknown | Unknown | 20 | Planned | April | May
TO-27-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 13 | Planned | April | May
TO-27-RAF-TBG-2-04 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 8 | Planned | April | April
TO-27-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | Unknown | Unknown | 75 | Reference (Planned) | April | August
TO-27-PRN-T4301-02 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | Unknown | Unknown | 5 | Planned | April | April
TO-27-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | Unknown | Unknown | 5 | Planned | April | April
TO-27-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | Unknown | Unknown |  | Planned | April | April
TO-27-WOO-400K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown |  | Planned | April | April
TO-27-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown | 5 | Planned | April | April
TO-27-WOO-T4201-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown |  | Planned | April | April
TO-27-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | April | April
TO-27-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | April | April
TO-27-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-ATH-SH-1-02 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-ATH-T142-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | Unknown | Unknown | 51 | Reference (Planned) | April | July
TO-27-CLW-110SA1-01 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-CLW-110SA2-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | Unknown | Unknown | 80 | Planned | April | August
TO-27-CLW-KLS-2-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CLW-KLS-2-03 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown | 10 | Planned | April | May
TO-27-CLW-KLS-2-04 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown | 80 | Planned | April | August
TO-27-CLW-T142-01 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T142 | Unknown | Unknown | 80 | Reference (Planned) | April | August
TO-27-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | Unknown | Unknown | 5 | Planned | April | April
TO-27-DRY-OBE-1-02 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 12 | 9 | 9 | Proposed | 26/04/2027 | 07/05/2027
TO-27-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 80 | Planned | April | August
TO-27-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 80 | Planned | April | August
TO-27-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 80 | Reference (Planned) | April | August
TO-27-STR,T-CLW-1-03 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-STR,T-PA-1-03 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | Unknown | Unknown | 18 | Planned | April | May
TO-27-CTN-110SA1-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | Unknown | Unknown | 8 | Planned | April | May
TO-27-CTN-110SA2-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | Unknown | Unknown | 8 | Planned | April | May
TO-27-CTN-T142-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | April | May
TO-27-CTN-T144-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | Unknown | Unknown | 8 | Reference (Planned) | April | May
TO-27-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | Unknown | Unknown | 8 | Planned | April | May
TO-27-MAY-RNW-1-02 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | Unknown | 30 | Planned | April | June
TO-27-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 4 | Planned | April | April
TO-27-LIS-110SA1-04 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 14 | Planned | April | May
TO-27-LIS-110SA2-04 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 14 | Planned | April | May
TO-27-LIS-CAP2-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | Unknown | Unknown | 14 | Planned | April | May
TO-27-LIS-LSA-1-04 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 14 | Planned | April | May
TO-27-LIS-T142-02 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | Unknown | Unknown | 14 | Reference (Planned) | April | May
TO-27-110 kV A2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-110 kV B2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | Unknown | 7 | Planned | May | May
TO-27-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | Unknown | Unknown | 1 | Planned | May | May
TO-27-DAL-T141-02 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | May | May
TO-27-DAL,T-DAL-1-04 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-DAL,T-STN-1-04 | 110kV FEEDER - DALLOW tee-STONESTOWN 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown | 20 | Planned | May | June
TO-27-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | Unknown | Unknown | 6 | Planned | May | May
TO-27-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | Unknown | 30 | Planned | May | June
TO-27-SHL-D1/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | Unknown | 30 | Planned | May | June
TO-27-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | Unknown | 8 | Planned | May | May
TO-27-SHL-D2/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | Unknown | Unknown | 30 | Planned | May | June
TO-27-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | Unknown | Unknown | 2 | Planned | May | May
TO-27-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 5 | Planned | May | May
TO-27-FIN GIS-MCE-1-01 | 110kV FEEDER - FINGLAS GIS 110-MACETOWN 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-GAL GIS-T101-01 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 10-T101 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 7 | Planned | May | May
TO-27-MP GIS-T121-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MUL-CAP1-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-PB-R2002-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown | 5 | Planned | May | May
TO-27-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | Unknown | Unknown | 5 | Planned | May | May
TO-27-SH-TMY-1-03 | 110kV FEEDER - SHANNONBRIDGE 110-TIMONEY 110-1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-SH-TMY-1-02 | 110kV FEEDER - SHANNONBRIDGE 110-TIMONEY 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-27-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 8 | Planned | May | May
TO-27-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 10 | Planned | May | May
TO-27-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | May | May
TO-27-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | May | May
TO-27-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 2 | Planned | May | May
TO-27-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 2 | Planned | May | May
TO-27-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 2 | Reference (Planned) | May | May
TO-27-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | Unknown | Unknown | 3 | Planned | May | May
TO-27-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | Unknown | Unknown | 2 | Planned | May | May
TO-27-SK-T104-03 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | May | May
TO-27-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 4 | Planned | May | May
TO-27-BAN-BRI-2-04 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown |  | Planned | May | September
TO-27-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown |  | Planned | May | September
TO-27-BRI-T102-03 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown |  | Planned | May | September
TO-27-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | Unknown | Unknown | 40 | Planned | May | July
TO-27-SLB-T132-02 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 2 | Planned | May | May
TO-27-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-MRK3-02 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BAN-110SA1-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BAN-T142-02 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | May | May
TO-27-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 6 | Planned | May | May
TO-27-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | Unknown | Unknown | 10 | Planned | May | May
TO-27-DRY-OBE-1-03 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | Unknown | Unknown |  | Planned | May | May
TO-27-GLN-T133-01 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | Unknown | Unknown | 5 | Planned | May | May
TO-27-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | Unknown | Unknown | 10 | Planned | May | May
TO-27-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | Unknown | Unknown | 5 | Planned | May | May
TO-27-LSA-T131-01 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | Unknown | Unknown | 2 | Planned | May | May
TO-27-LOU-CAP1-01 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | Unknown | Unknown | 5 | Reference (Planned) | May | May
TO-27-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | Unknown | Unknown | 8 | Planned | May | May
TO-27-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | Unknown | Unknown | 8 | Planned | May | May
TO-27-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | Unknown | Unknown | 4 | Planned | May | May
TO-27-CRD-T131-01 | GENERATOR TRANSFORMER - CROAGHONAGH 110-CROAGHONAGH 33-T131 | Unknown | Unknown | 4 | Planned | May | May
TO-27-GAL GIS-T103-01 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 10-T103 | Unknown | Unknown | 2 | Planned | May | May
TO-27-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | Unknown | Unknown | 3 | Planned | May | May
TO-27-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-110 kV B2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | Unknown | Unknown | 3 | Planned | May | May
TO-27-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | Unknown | Unknown | 3 | Planned | May | May
TO-27-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | Unknown | Unknown | 3 | Planned | May | May
TO-27-KPG-T2102-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | Unknown | Unknown | 3 | Planned | May | May
TO-27-LIS-110SA1-05 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-110SA2-05 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-CAP1-03 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-LOU-1-03 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-T131-02 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-T141-02 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | May | June
TO-27-KLN-NEN-1-01 | 110kV FEEDER - KILLONAN 110-NENAGH 110-1 | Unknown | Unknown | 30 | Reference (Planned) | May | July
TO-27-KLN-NEN-1-02 | 110kV FEEDER - KILLONAN 110-NENAGH 110-1 | Unknown | Unknown | 20 | Reference (Planned) | May | June
TO-27-NEN-T141-01 | DISTRIBUTION TRANSFORMER - NENAGH 110-NENAGH 38-T141 | Unknown | Unknown | 30 | Reference (Planned) | May | July
TO-27-NEN-T141-02 | DISTRIBUTION TRANSFORMER - NENAGH 110-NENAGH 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | May | June
TO-27-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-MRK1-03 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-T141-02 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | May | May
TO-27-BDA-NEW-1-02 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | May | June
TO-27-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-DRU-CAP2-01 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-KYT-220K2-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | Unknown | Unknown | 10 | Planned | May | June
TO-27-PLA-T105-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | Unknown | Unknown | 5 | Planned | May | May
TO-27-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | Unknown | Unknown | 3 | Planned | May | May
TO-27-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | Unknown | Unknown | 5 | Planned | May | May
TO-27-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | Unknown | Unknown | 2 | Planned | May | May
TO-27-GAL GIS-T142-01 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 38-T142 | Unknown | Unknown | 3 | Planned | May | May
TO-27-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-CSH-SAL-1-03 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | Unknown | Unknown | 55 | Planned | May | August
TO-27-CSH-SAL-1-04 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | Unknown | Unknown | 40 | Planned | May | July
TO-27-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | Unknown | Unknown | 10 | Planned | May | June
TO-27-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | Unknown | Unknown | 1 | Planned | May | May
TO-27-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 2 | Planned | May | June
TO-27-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 2 | Planned | May | June
TO-27-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | Unknown | Unknown | 5 | Planned | May | June
TO-27-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | Unknown | Unknown | 9 | Planned | May | June
TO-27-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | Unknown | 9 | Planned | May | June
TO-27-KYT-220K3-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K3 | Unknown | Unknown | 5 | Planned | May | June
TO-27-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | Unknown | Unknown | 5 | Planned | May | June
TO-27-CHA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-27-CHA-GLE-1-02 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-KLN-1-03 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-T141-01 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | June | June
TO-27-CHA-T142-01 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | June | June
TO-27-GRI-T141-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | Unknown | 60 | Reference (Planned) | June | August
TO-27-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-27-GRI,T-GCA-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | Unknown | 60 | Planned | June | August
TO-27-GRI,T-GRI-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | Unknown | Unknown | 60 | Planned | June | August
TO-27-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | Unknown | 6 | Planned | June | June
TO-27-GRI,T-MAY-1-02 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | Unknown | 60 | Planned | June | August
TO-27-110 kV A2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110A2 | Unknown | Unknown | 22 | Planned | June | July
TO-27-110 kV B2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110B2 | Unknown | Unknown | 22 | Planned | June | July
TO-27-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | Unknown | 57 | Planned | June | August
TO-27-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | Unknown | Unknown | 57 | Planned | June | August
TO-27-CUN-SLI-1-04 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | Unknown | Unknown | 10 | Planned | June | June
TO-27-SLI-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | June | June
TO-27-SLI-T142-03 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-27-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | Unknown | Unknown | 3 | Planned | June | June
TO-27-KIR-T131-01 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | Unknown | Unknown | 1 | Planned | June | June
TO-27-KLN-LIM-1-03 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 90 | Planned | June | October
TO-27-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 3 | Planned | June | June
TO-27-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | Unknown | Unknown | 14 | Planned | June | June
TO-27-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-27-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | Unknown | Unknown | 4 | Reference (Planned) | June | June
TO-27-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown | 20 | Planned | June | July
TO-27-KUD-T101-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T101 | Unknown | Unknown | 2 | Planned | June | June
TO-27-220 kV A4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | Unknown | Unknown | 5 | Planned | June | June
TO-27-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | Unknown | Unknown | 5 | Planned | June | June
TO-27-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-ANR-T101-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-27-ANR-T103-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-27-BDN-DOO-1-03 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | Unknown | Unknown | 7 | Planned | June | June
TO-27-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | Unknown | Unknown | 26 | Planned | June | July
TO-27-COL-T121-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T121 | Unknown | Unknown | 55 | Reference (Planned) | June | August
TO-27-DEY-PLS-1-01 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | Unknown | Unknown | 15 | Planned | June | June
TO-27-DOO-110SA1-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | Unknown | Unknown | 7 | Planned | June | June
TO-27-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | June | June
TO-27-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | Unknown | Unknown | 1 | Planned | June | June
TO-27-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | Unknown | Unknown | 1 | Planned | June | June
TO-27-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-27-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown |  | Planned | June | July
TO-27-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown | 20 | Planned | June | July
TO-27-CDU-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | Unknown | Unknown | 10 | Planned | June | June
TO-27-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | Unknown | Unknown | 5 | Reference (Planned) | June | June
TO-27-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | Unknown | Unknown | 5 | Planned | June | June
TO-27-KYT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-220 kV A2 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 220-KILLONAN GIS 220-220A2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-220 kV B2 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 220-KILLONAN GIS 220-220B2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-KLN GIS-220K2-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220K2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-KLN GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-KLN GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 8 | Planned | June | June
TO-27-MRY-T131-02 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | Unknown | Unknown | 2 | Planned | June | June
TO-27-110 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | Unknown | Unknown | 25 | Planned | June | July
TO-27-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | Unknown | Unknown | 10 | Planned | June | June
TO-27-RAF-CAP2-02 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | Unknown | Unknown | 25 | Planned | June | July
TO-27-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | June | July
TO-27-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | Unknown | 20 | Planned | June | July
TO-27-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | Unknown | Unknown | 3 | Planned | June | June
TO-27-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 3 | Planned | June | June
TO-27-LIS-110SA1-06 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 4 | Planned | June | June
TO-27-LIS-110SA2-06 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 4 | Planned | June | June
TO-27-LIS-CAP2-03 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | Unknown | Unknown | 4 | Planned | June | June
TO-27-LIS-LSA-1-05 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-27-LIS-T142-03 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | Unknown | Unknown | 4 | Reference (Planned) | June | June
TO-27-STN-T131-01 | GENERATOR TRANSFORMER - STONESTOWN 110-STONESTOWN 33-T131 | Unknown | Unknown | 1 | Planned | June | June
TO-27-DSN-T4201-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | Unknown | Unknown | 60 | Planned | June | September
TO-27-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 6 | Planned | June | June
TO-27-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 80 | Planned | June | October
TO-27-110 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-110 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-CSH-CAP2-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | Unknown | 25 | Planned | June | July
TO-27-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-DRY-GOR-1-03 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 45 | Planned | June | August
TO-27-DRY-T142-01 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | Unknown | Unknown | 105 | Reference (Planned) | June | November
TO-27-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 10 | Planned | June | July
TO-27-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 10 | Planned | June | July
TO-27-KYT-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SA1-3CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown | 10 | Planned | June | July
TO-27-MCE-110SA1-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | Unknown | Unknown | 7 | Planned | June | June
TO-27-220 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 25 | Planned | June | July
TO-27-220 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 25 | Planned | June | July
TO-27-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-MUN-T102-02 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | Unknown | Unknown | 5 | Reference (Planned) | June | June
TO-27-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | Unknown | Unknown | 9 | Planned | June | July
TO-27-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 3 | Planned | June | June
TO-27-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-DRU-ENN-1-02 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | Unknown | Unknown | 80 | Planned | June | October
TO-27-110 kV A4 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A4 | Unknown | Unknown |  | Planned | June | July
TO-27-110 kV B4 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B4 | Unknown | Unknown | 7 | Planned | June | July
TO-27-KLN GIS-110K4-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110K4 | Unknown | Unknown | 7 | Planned | June | July
TO-27-KLN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA2-4CB | Unknown | Unknown | 7 | Planned | June | July
TO-27-KLN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB2-4CB | Unknown | Unknown | 7 | Planned | June | July
TO-27-220 kV A2 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 220-KILLONAN GIS 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-27-220 kV B2 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 220-KILLONAN GIS 220-220B2 | Unknown | Unknown | 2 | Planned | June | June
TO-27-KLN GIS-220K2-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220K2 | Unknown | Unknown | 2 | Planned | June | June
TO-27-KLN GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | June | June
TO-27-KLN GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | June | June
TO-27-KLN-KLN GIS-1-220-01 | 220kV FEEDER - KILLONAN 220-KILLONAN GIS 220-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | Unknown | Unknown | 59 | Planned | June | September
TO-27-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | June | July
TO-27-BAR,T-BAR-1-02 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | Unknown | 5 | Planned | June | July
TO-27-CBG-CBR-1-01 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | Unknown | Unknown | 8 | Reference (Planned) | June | July
TO-27-CBG-T142-01 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | June | July
TO-27-CBR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | Unknown | Unknown | 8 | Planned | June | July
TO-27-CBR-CAP2-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | Unknown | Unknown | 8 | Planned | June | July
TO-27-CBR-DLT-1-01 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-CBR-T142-01 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | June | July
TO-27-COL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | Unknown | Unknown | 10 | Planned | June | July
TO-27-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-COL-T103-04 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | Unknown | Unknown | 10 | Reference (Planned) | June | July
TO-27-COL-T121-03 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T121 | Unknown | Unknown | 10 | Reference (Planned) | June | July
TO-27-GOR-MAY-1-04 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-KYT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | June | July
TO-27-THU-STATCOM-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | Unknown | Unknown | 5 | Planned | June | July
TO-27-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | Unknown | Unknown | 60 | Reference (Planned) | June | September
TO-27-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | Unknown | Unknown | 3 | Planned | June | July
TO-27-DGY-FIN GIS-1-01 | 110kV FEEDER - DUNSOGHLY 110-FINGLAS GIS 110-1 | Unknown | Unknown | 3 | Planned | June | July
TO-27-DGY-T101-01 | GENERATOR TRANSFORMER - DUNSOGHLY 110-DUNSOGHLY 11-T101 | Unknown | Unknown | 3 | Planned | June | July
TO-27-DSN-MP GIS-1-04 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown | 58 | Planned | June | September
TO-27-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown |  | Planned | June | September
TO-27-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown | 58 | Planned | June | September
TO-27-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | Unknown | 100 | Planned | June | November
TO-27-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | Unknown |  | Planned | June | November
TO-27-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | Unknown | Unknown | 6 | Planned | June | July
TO-27-KBY-MAL-1-02 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | Unknown | Unknown | 70 | Planned | June | October
TO-27-110 kV A2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A2 | Unknown | Unknown | 2 | Planned | June | July
TO-27-110 kV B2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | Unknown | Unknown | 2 | Planned | June | July
TO-27-BVK-110K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 2 | Planned | June | July
TO-27-BVK-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | June | July
TO-27-BVK-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | June | July
TO-27-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | Unknown | Unknown | 2 | Planned | June | July
TO-27-110 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | Unknown | Unknown | 30 | Planned | June | August
TO-27-110 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | Unknown | Unknown | 30 | Planned | June | August
TO-27-BAN-110SA1-04 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown |  | Planned | July | September
TO-27-BAN-110SA2-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown |  | Planned | July | September
TO-27-BAN-T142-03 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | Unknown |  | Reference (Planned) | July | September
TO-27-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-110 kV A2 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-110 kV B2 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-KLN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-KLN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-KLN GIS-T2102-01 | TRANSFORMER - KILLONAN GIS 220-KILLONAN GIS 110-T2102 | Unknown | Unknown | 2 | Planned | July | July
TO-27-ATH-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | July | July
TO-27-ATH-SH-1-03 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 8 | Planned | July | July
TO-27-BAN-BRI-2-03 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 15 | Planned | July | July
TO-27-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown | 15 | Planned | July | July
TO-27-CKG-110K2-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K2 | Unknown | Unknown | 5 | Planned | July | July
TO-27-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | Unknown | 20 | Planned | July | July
TO-27-GRV-T121-02 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 5 | Planned | July | July
TO-27-GWE-T142-02 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-27-220 kV A1 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-220 kV A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-GI GIS-220K2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-GI GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-GI GIS-KLS-1-04 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-KYT-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SB1-3CB | Unknown | Unknown | 5 | Planned | July | July
TO-27-110 kV A2 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | Unknown | Unknown |  | Planned | July | July
TO-27-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-27-LA-MUL-1-01 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | Unknown | Unknown | 12 | Planned | July | July
TO-27-MP GIS-PRO-1-02 | 220kV FEEDER - MONEYPOINT GIS 220-PROSPECT 220-1 | Unknown | Unknown | 10 | Planned | July | July
TO-27-AHA-KLN-2-01 | 110kV FEEDER - AHANE 110-KILLONAN 110-2 | Unknown | Unknown | 50 | Reference (Planned) | July | September
TO-27-AHA-T102-01 | DISTRIBUTION TRANSFORMER - AHANE 110-AHANE 10-T102 | Unknown | Unknown | 50 | Reference (Planned) | July | September
TO-27-ATY-T102-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | Unknown | Unknown | 80 | Reference (Planned) | July | October
TO-27-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown | 3 | Planned | July | July
TO-27-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | 1 | 1 | 1 | Proposed | 06/07/2027 | 06/07/2027
TO-27-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | Unknown | 14 | Planned | July | July
TO-27-CUS-NEW-1-02 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | Unknown | 70 | Planned | July | October
TO-27-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 40 | Planned | July | August
TO-27-220 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-110 kV A1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | Unknown | Unknown | 40 | Planned | July | August
TO-27-110 kV B1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 9 | Planned | July | July
TO-27-FIN GIS-110K1-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | Unknown | Unknown | 9 | Planned | July | July
TO-27-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | Unknown | Unknown | 2 | Planned | July | July
TO-27-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | Unknown | Unknown | 33 | Planned | July | August
TO-27-ARK-BEG-1-02 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | Unknown | Unknown | 50 | Planned | July | September
TO-27-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | Unknown | 50 | Planned | July | September
TO-27-ARK-CKM GIS-1-03 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | Unknown | 50 | Planned | July | September
TO-27-220 kV A10 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A10 | Unknown | Unknown | 15 | Planned | July | July
TO-27-220 kV A10 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A10 | Unknown | Unknown | 17 | Planned | July | July
TO-27-220 kV B10 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B10 | Unknown | Unknown | 17 | Planned | July | July
TO-27-220 kV B10 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B10 | Unknown | Unknown | 15 | Planned | July | July
TO-27-INC-220K10-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K10 | Unknown | Unknown | 17 | Planned | July | July
TO-27-INC-220K10-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K10 | Unknown | Unknown | 15 | Planned | July | July
TO-27-INC-SA8-10CB-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA8-10CB | Unknown | Unknown | 15 | Planned | July | July
TO-27-INC-SA8-10CB-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA8-10CB | Unknown | Unknown | 17 | Planned | July | July
TO-27-INC-SB8-10CB-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB8-10CB | Unknown | Unknown | 15 | Planned | July | July
TO-27-INC-SB8-10CB-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB8-10CB | Unknown | Unknown | 17 | Planned | July | July
TO-27-KUD-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILMAHUD 110-KILMAHUD 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | July | July
TO-27-KRA-LYT-1-01 | 110kV FEEDER - KNOCKRAHA 110-LYSAGHTSTOWN 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-DLT-110SA1-01 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | Unknown | Unknown | 7 | Planned | July | July
TO-27-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | Unknown | Unknown | 7 | Planned | July | July
TO-27-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | Unknown | Unknown | 5 | Planned | July | July
TO-27-CKG-110K3-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | Unknown | Unknown | 5 | Planned | July | July
TO-27-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-27-CUS-T103/5-03 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 5 | Planned | July | July
TO-27-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-27-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | Unknown | Unknown | 55 | Planned | July | September
TO-27-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | Unknown | Unknown | 8 | Planned | July | July
TO-27-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | Unknown | Unknown | 10 | Planned | July | July
TO-27-MID-110SA1-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | Unknown | Unknown | 80 | Planned | July | November
TO-27-MID-110SA2-03 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | Unknown | Unknown | 80 | Planned | July | November
TO-27-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | Unknown | Unknown | 80 | Reference (Planned) | July | November
TO-27-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-MID-WHI-1-02 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | Unknown | Unknown | 80 | Planned | July | November
TO-27-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | Unknown | Unknown | 4 | Planned | July | July
TO-27-CDU-SNU-1-01 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | Unknown | Unknown | 9 | Planned | July | July
TO-27-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 6 | Reference (Planned) | July | July
TO-27-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 6 | Planned | July | July
TO-27-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | Unknown | 6 | Planned | July | July
TO-27-IKE,T-TMY1-01 | 110kV FEEDER - IKERRIN tee-TIMONEY 110-1 | Unknown | Unknown | 6 | Planned | July | July
TO-27-110 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown | 40 | Planned | July | September
TO-27-110 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown | 40 | Planned | July | September
TO-27-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | Unknown | 40 | Planned | July | September
TO-27-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-CSH-CLN-1-03 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | Unknown | 40 | Planned | July | September
TO-27-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-27-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | Unknown | Unknown | 1 | Planned | July | July
TO-27-LIM-MTN-1-06 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown |  | Planned | July | October
TO-27-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-27-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | Unknown | Unknown | 10 | Planned | July | July
TO-27-CKG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-27-FIN GIS-MCE-1-02 | 110kV FEEDER - FINGLAS GIS 110-MACETOWN 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-LIM-110SA2-02 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-27-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-LIM-MTN-1-03 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 59 | Planned | July | October
TO-27-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-27-MCE-110SA1-02 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-MCE-110SA2-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-MCE-T124-02 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | Unknown | Unknown | 2 | Planned | July | July
TO-27-BRA-NEW-1-01 | 110kV FEEDER - BRACKLONE 110-NEWBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-CUS-NEW-1-03 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | Unknown | 60 | Planned | July | October
TO-27-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 15 | Planned | July | August
TO-27-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 15 | Planned | July | August
TO-27-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | Unknown | Unknown | 18 | Planned | July | August
TO-27-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-LOU-220K1-2-03 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown |  | Planned | July | July
TO-27-NEW-110SA1-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-NEW-110SA2-02 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 3 | Planned | July | July
TO-27-NEW-T141-01 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-27-DER-TEN-1-02 | 110kV FEEDER - DERRYIRON 110-TIMAHOE 110-1 | Unknown | Unknown | 60 | Planned | July | October
TO-27-DER-TEN-1-01 | 110kV FEEDER - DERRYIRON 110-TIMAHOE 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-MCE-T101-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T101 | Unknown | Unknown | 120 | Reference (Planned) | July | January
TO-27-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | Unknown | Unknown | 1 | Planned | July | July
TO-27-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | Unknown | Unknown | 1 | Planned | July | July
TO-27-TRI-CAP1-01 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | Unknown | Unknown | 10 | Planned | July | August
TO-27-BGT-CNB-1-01 | 110kV FEEDER - BALLYRAGGET 110-COOLNABACKY 110-1 | Unknown | Unknown | 80 | Planned | July | November
TO-27-110 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-110 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-LOU-110K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown |  | Planned | July | July
TO-27-CKG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-27-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | Unknown | 14 | Planned | July | August
TO-27-GOL,T-CLO-1-02 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | Unknown | Unknown | 14 | Planned | July | August
TO-27-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | Unknown | 14 | Planned | July | August
TO-27-GOL,T-LET-1-02 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | Unknown | 14 | Planned | July | August
TO-27-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | Unknown | 9 | Planned | July | August
TO-27-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-PB-220SA1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | Unknown | Unknown | 5 | Planned | July | July
TO-27-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-220 kV A8 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A8 | Unknown | Unknown | 2 | Planned | July | July
TO-27-220 kV B8 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B8 | Unknown | Unknown | 2 | Planned | July | July
TO-27-INC-SA6-8CB-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA6-8CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-INC-SB6-8CB-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB6-8CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-DDK-LOU-1-02 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-27-110 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown | 1 | Planned | July | July
TO-27-LIM-MTN-1-04 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 50 | Planned | July | October
TO-27-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 4 | 4 | 4 | Proposed | 03/08/2027 | 06/08/2027
TO-27-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 3 | Planned | August | August
TO-27-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 4 | 4 | 4 | Proposed | 03/08/2027 | 06/08/2027
TO-27-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 4 | 4 | 4 | Proposed | 03/08/2027 | 06/08/2027
TO-27-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 4 | 4 | 4 | Reference (Proposed) | 03/08/2027 | 06/08/2027
TO-27-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 2 | Planned | August | August
TO-27-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 106 | Planned | August | December
TO-27-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 106 | Planned | August | December
TO-27-KRA-220K1-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | Unknown | Unknown | 106 | Planned | August | December
TO-27-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 106 | Planned | August | December
TO-27-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 106 | Planned | August | December
TO-27-110 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 2 | Planned | August | August
TO-27-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | Unknown | 6 | Planned | August | August
TO-27-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | Unknown | Unknown | 2 | Planned | August | August
TO-27-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 38 | Planned | August | September
TO-27-FIN-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 8 | Planned | August | August
TO-27-FIN-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 38 | Planned | August | September
TO-27-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | Unknown | Unknown | 12 | Planned | August | August
TO-27-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 8 | Planned | August | August
TO-27-INC-PB-2-03 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 2 | Planned | August | August
TO-27-AUG-CFM-2-03 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 10 | Planned | August | August
TO-27-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | Unknown | Unknown | 5 | Planned | August | August
TO-27-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-27-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-27-BAN-110SA2-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-BAN-BRI-2-05 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-27-BRI-T102-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown | 5 | Planned | August | August
TO-27-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | Unknown | Unknown | 10 | Planned | August | August
TO-27-COT-T132-02 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | Unknown | Unknown | 5 | Planned | August | August
TO-27-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | August | August
TO-27-CKG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 5 | Planned | August | August
TO-27-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | Unknown | 10 | Planned | August | August
TO-27-DGN-110SA2-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | Unknown | 10 | Planned | August | August
TO-27-DGN-RTH-1-01 | 110kV FEEDER - DUNGARVAN 110-RATHNASKILLOGE 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-27-DGN-T142-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | August | August
TO-27-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | Unknown | Unknown | 15 | Planned | August | August
TO-27-GOR-LOU-1-03 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 20 | Planned | August | September
TO-27-110 kV A2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | Unknown | Unknown | 40 | Planned | August | October
TO-27-110 kV B2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | Unknown | Unknown | 40 | Planned | August | October
TO-27-INC-PB-1-03 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | Unknown | Unknown | 83 | Planned | August | December
TO-27-ISH-220K1-2-02 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | Unknown | 50 | Planned | August | October
TO-27-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | Unknown | Unknown | 15 | Planned | August | August
TO-27-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | Unknown | Unknown | 18 | Planned | August | September
TO-27-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | Unknown | Unknown | 5 | Planned | August | August
TO-27-PB-220SB1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | Unknown | Unknown | 2 | Planned | August | August
TO-27-CBT-MAY-2-02 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-2 | Unknown | Unknown | 25 | Planned | August | September
TO-27-CTN-110SA1-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-27-CTN-110SA2-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-CTN-T142-02 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-27-CTN-T144-02 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-27-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-27-CKG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 5 | Planned | August | August
TO-27-CKG-T121-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T121 | Unknown | Unknown | 5 | Planned | August | August
TO-27-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | August | August
TO-27-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-27-GLR-T121-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T121 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-27-LIM-MTN-1-05 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 40 | Planned | August | October
TO-27-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown | 5 | Planned | August | August
TO-27-SNU-T104-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | Unknown | Unknown | 5 | Planned | August | August
TO-27-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | Unknown | Unknown | 2 | Planned | August | August
TO-27-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-27-BGT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-27-DND-T125-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T125 | Unknown | Unknown | 2 | Planned | August | August
TO-27-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | Unknown | Unknown | 8 | Planned | August | August
TO-27-CSH-GAL GIS-2-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | Unknown | Unknown | 1 | Planned | August | August
TO-27-PA-110SA1-03 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 15 | Planned | August | September
TO-27-PA-110SA2-03 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 15 | Planned | August | September
TO-27-PA-T101-03 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 15 | Planned | August | September
TO-27-STR-T141-03 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | August | September
TO-27-STR,T-PA-1-04 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-27-STR,T-STR-1-03 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-27-CSH-GAL GIS-4-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-4 | Unknown | Unknown | 5 | Planned | August | August
TO-27-CTN-110SA1-03 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | Unknown | Unknown | 4 | Planned | August | August
TO-27-CTN-110SA2-03 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | Unknown | Unknown | 4 | Planned | August | August
TO-27-CTN-T142-03 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | Unknown | Unknown | 4 | Reference (Planned) | August | August
TO-27-CTN-T144-03 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | Unknown | Unknown | 4 | Reference (Planned) | August | August
TO-27-CTN-TIP-1-03 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-27-CKG-T122-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T122 | Unknown | Unknown | 5 | Planned | August | August
TO-27-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-27-SNU-T131-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 33-T131 | Unknown | Unknown | 5 | Planned | August | August
TO-27-COL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-27-COL-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | August | August
TO-27-COL-CDU-1-02 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-27-COL-T103-02 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | Unknown | Unknown | 2 | Reference (Planned) | August | August
TO-27-FIN-220K1-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | Unknown | Unknown | 2 | Planned | August | August
TO-27-CKG-T123-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T123 | Unknown | Unknown | 5 | Planned | August | September
TO-27-SNU-T133-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 33-T133 | Unknown | Unknown | 5 | Planned | August | September
TO-27-TRL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | August | September
TO-27-TRL-T142-02 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | August | September
TO-27-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | Unknown | Unknown | 4 | Planned | August | September
TO-27-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | Unknown | Unknown | 8 | Planned | August | September
TO-27-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | Unknown | Unknown | 50 | Planned | August | November
TO-27-SHL-D2/CB1-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 50 | Planned | August | November
TO-27-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | Unknown | 50 | Planned | August | November
TO-27-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN-220K2-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV A1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV B1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110K1-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 50 | Planned | September | November
TO-27-110 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 50 | Planned | September | November
TO-27-110 kV B2 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-RAF-TBG-2-07 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-RAF-TBG-2-06 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV A1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-110 kV B1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 20 | Planned | September | September
TO-27-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown | 10 | Planned | September | September
TO-27-BRY-RAF-1-01 | 110kV FEEDER - BARNAHELY 110-RAFFEEN 110-1 | Unknown | Unknown |  | Reference (Planned) | September | November
TO-27-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-27-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | Unknown | Unknown | 5 | Planned | September | September
TO-27-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | Unknown | Unknown | 10 | Planned | September | September
TO-27-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-27-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-DEN-DRY-1-01 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-110 kV A4 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A4 | Unknown | Unknown | 7 | Planned | September | September
TO-27-110 kV B4 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B4 | Unknown | Unknown | 7 | Planned | September | September
TO-27-KLN GIS-110K4-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110K4 | Unknown | Unknown | 7 | Planned | September | September
TO-27-KLN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA2-4CB | Unknown | Unknown | 7 | Planned | September | September
TO-27-KLN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB2-4CB | Unknown | Unknown | 7 | Planned | September | September
TO-27-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | Unknown | Unknown | 10 | Planned | September | September
TO-27-PB-R2002-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown | 5 | Planned | September | September
TO-27-110 kV B1/B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1-B2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-RAF-110K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | Unknown | Unknown |  | Planned | September | September
TO-27-TBG-110K1-2-02 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | Unknown | Unknown | 7 | Planned | September | September
TO-27-BDA-T101-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | Unknown | Unknown | 7 | Planned | September | September
TO-27-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-27-GAL GIS-KNY-1-01 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-27-LSA-SKL-1-01 | 110kV FEEDER - LISLEA 110-SHANKILL 110-1 | Unknown | Unknown | 6 | Planned | September | September
TO-27-PB-T2007/8-01 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | Unknown | Unknown | 2 | Planned | September | September
TO-27-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | Unknown | Unknown | 9 | Planned | September | September
TO-27-CSH-GAL GIS-1-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-27-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | Unknown | Unknown | 7 | Planned | September | September
TO-27-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-400 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-400 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-110 kV A2 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV B2 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-KLN GIS-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-KLN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-KLN GIS-T2102-02 | TRANSFORMER - KILLONAN GIS 220-KILLONAN GIS 110-T2102 | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV A1/A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1-A2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-RAF-110K1-2-02 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | Unknown | Unknown | 24 | Planned | September | October
TO-27-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-27-BRA-NEW-1-02 | 110kV FEEDER - BRACKLONE 110-NEWBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-27-BRA-NEW-1-04 | 110kV FEEDER - BRACKLONE 110-NEWBRIDGE 110-1 | Unknown | Unknown | 20 | Planned | September | October
TO-27-NEW-110SA1-02 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | Unknown | Unknown | 3 | Planned | September | September
TO-27-NEW-110SA1-04 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | Unknown | Unknown | 20 | Planned | September | October
TO-27-NEW-110SA2-03 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 3 | Planned | September | September
TO-27-NEW-110SA2-05 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 20 | Planned | September | October
TO-27-NEW-T141-04 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | September | October
TO-27-NEW-T141-02 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-27-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-COL-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-COL-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-COL-CDU-1-03 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-COL-T121-02 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T121 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-27-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-27-COR-GWE-1-02 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | Unknown | Unknown | 15 | Planned | September | October
TO-27-CRA-WEX-1-04 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 13 | Planned | September | October
TO-27-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-27-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown | 5 | Planned | September | September
TO-27-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | Unknown | Unknown | 40 | Planned | September | November
TO-27-RAF-TBG-2-05 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-110 kV B1 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-WEX-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 13 | Planned | September | October
TO-27-WEX-CAP2-03 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 13 | Planned | September | October
TO-27-WEX-CAP4-03 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 13 | Planned | September | October
TO-27-WEX-T122-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown | 13 | Reference (Planned) | September | October
TO-27-WEX-T142-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown | 13 | Reference (Planned) | September | October
TO-27-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 50 | Planned | September | November
TO-27-GOR-LOU-1-04 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 60 | Planned | September | December
TO-27-220 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | Unknown | Unknown | 60 | Planned | September | December
TO-27-220 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | Unknown | Unknown | 60 | Planned | September | December
TO-27-COL-T122-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T122 | Unknown | Unknown | 55 | Reference (Planned) | September | December
TO-27-KLN-SH-1-04 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 57 | Planned | September | December
TO-27-110 kV A1 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | Unknown | Unknown | 3 | Planned | September | September
TO-27-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-27-COL-T122-02 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T122 | Unknown | Unknown | 10 | Reference (Planned) | September | October
TO-27-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | September | October
TO-27-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 5 | Planned | September | October
TO-27-FIN-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | September | October
TO-27-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 5 | Planned | September | October
TO-27-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-27-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-27-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown | 5 | Planned | September | October
TO-27-110 kV A2 @ KBY-04 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | Unknown | Unknown | 3 | Planned | September | September
TO-27-110 kV A1 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A1 | Unknown | Unknown | 7 | Planned | September | October
TO-27-110 kV B1 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B1 | Unknown | Unknown | 7 | Planned | September | October
TO-27-KLN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-2CB | Unknown | Unknown | 7 | Planned | September | October
TO-27-KLN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-3CB | Unknown | Unknown | 7 | Planned | September | October
TO-27-KLN GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-2CB | Unknown | Unknown | 7 | Planned | September | October
TO-27-KLN GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-3CB | Unknown | Unknown | 7 | Planned | September | October
TO-27-CBT-MAY-1-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | Unknown | Unknown | 19 | Planned | October | October
TO-27-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | Unknown | Unknown | 5 | Planned | October | October
TO-27-CUS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | October | October
TO-27-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 5 | Planned | October | October
TO-27-CUS-T103/5-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 3 | Planned | October | October
TO-27-DMY-MAC-1-01 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 15 | Planned | October | October
TO-27-110 kV A2 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-110 kV B2 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-KLN-LIM-1-04 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | Unknown | Unknown | 60 | Planned | October | December
TO-27-110 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | Unknown | Unknown | 60 | Planned | October | December
TO-27-LIM-110SA1-02 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-LIM-110SA1-03 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-LIM-110SA2-03 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-LIM-110SA2-04 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-LIM-T141-02 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | October | October
TO-27-LIM-T141-03 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | October | October
TO-27-BOG-110SA1-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA1 | Unknown | Unknown | 3 | Planned | October | October
TO-27-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | Unknown | Unknown | 3 | Reference (Planned) | October | October
TO-27-110 kV A2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | Unknown | Unknown | 1 | Planned | October | October
TO-27-KBY-MR-2-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 1 | Planned | October | October
TO-27-110 kV A1 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | Unknown | Unknown | 25 | Planned | October | November
TO-27-110 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | Unknown | Unknown | 25 | Planned | October | November
TO-27-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | October | October
TO-27-CHA-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | Unknown | Unknown | 20 | Planned | October | November
TO-27-CHA-GLE-1-03 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | Unknown | Unknown | 20 | Planned | October | November
TO-27-CHA-KLN-1-04 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 20 | Planned | October | November
TO-27-CHA-T141-02 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | October | November
TO-27-CRA-WEX-1-05 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-DRU-110SA1-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-DRU-110SA2-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-27-DRU-T141-01 | DISTRIBUTION TRANSFORMER - DRUMLINE 110-DRUMLINE 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-110 kV A1 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-110 kV B1 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-3CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-T2101-01 | TRANSFORMER - KILLONAN GIS 220-KILLONAN GIS 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-T2101-02 | TRANSFORMER - KILLONAN GIS 220-KILLONAN GIS 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-27-WEX-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-WEX-CAP2-04 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 2 | Planned | October | October
TO-27-WEX-CAP4-04 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 2 | Planned | October | October
TO-27-WEX-T122-03 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-WEX-T142-03 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-BOL-ENN-1-02 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 5 | 5 | 5 | Proposed | 11/10/2027 | 15/10/2027
TO-27-ENN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-220 kV A2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-220 kV B2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-MAY-220K1-2-02 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-MAY-T2102-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | Unknown | Unknown | 5 | Planned | October | October
TO-27-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-27-BRA-NEW-1-03 | 110kV FEEDER - BRACKLONE 110-NEWBRIDGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-27-NEW-110SA1-03 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | Unknown | Unknown | 1 | Planned | October | October
TO-27-NEW-110SA2-04 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 1 | Planned | October | October
TO-27-NEW-T141-03 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | Unknown | Unknown | 1 | Reference (Planned) | October | October
TO-27-BOL-ENN-1-03 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CSH-ENN-1-03 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ENN-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-ENN-T101-02 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-ENN-T141-02 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-DER-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | October | October
TO-27-DER-KIN-1-02 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-DER-KDN-1-01 | 110kV FEEDER - DERRYIRON 110-KNOCKDRIN 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-KDN-T131-01 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | Unknown | Unknown | 10 | Planned | October | October
TO-27-ARV-GWE-1-02 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-ARV-GWE-1-03 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-GWE-110SA1-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-GWE-110SA2-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | Unknown | Unknown | 10 | Planned | October | October
TO-27-GWE-T102-02 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | Unknown | Unknown | 10 | Planned | October | October
TO-27-GWE-T142-01 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | October | October
TO-27-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | Unknown | Unknown | 20 | Planned | October | November
TO-27-AGL-ENN-1-03 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | Unknown | Unknown | 42 | Planned | October | December
TO-27-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-27-ARK-BOG-1-02 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | Unknown | Unknown | 39 | Planned | October | December
TO-27-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | Unknown | 29 | Planned | October | November
TO-27-CRU-T224-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T224 | Unknown | Unknown | 5 | Planned | October | October
TO-27-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | Unknown | 10 | Planned | October | November
TO-27-220 kV A2 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 7 | Planned | October | October
TO-27-220 kV B2 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 7 | Planned | October | October
TO-27-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | Unknown | Unknown | 9 | Reference (Planned) | October | October
TO-27-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ATY-110SA1-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ATY-CNB-1-01 | 110kV FEEDER - ATHY 110-COOLNABACKY 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CSH-DLT-1-02 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-27-CUS-PHT-1-01 | 110kV FEEDER - CUSHALING 110-PHILIPSTOWN 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-27-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown | 3 | Planned | October | October
TO-27-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 9 | Planned | October | November
TO-27-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | Unknown | Unknown | 1 | Planned | October | October
TO-27-DND-T124-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | Unknown | Unknown | 1 | Planned | October | October
TO-27-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-27-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | Unknown | Unknown | 15 | Planned | November | November
TO-27-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-GOR-NAV-3-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | Unknown | Unknown | 10 | Planned | November | November
TO-27-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-27-MAY-TEN-1-01 | 110kV FEEDER - MAYNOOTH 110-TIMAHOE 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | Unknown | Unknown |  | Reference (Planned) | November | November
TO-27-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-OUG,T-KER-1-02 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown |  | Planned | November | November
TO-27-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | Unknown | Unknown | 3 | Planned | November | November
TO-27-OUG,T-OUG-1-02 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | Unknown | Unknown |  | Planned | November | November
TO-27-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-OUG,T-TRL-1-04 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV A2 @ RAT-01 | BUSBAR SECTION - RATHKEALE 110-RATHKEALE 110-110A2 | Unknown | Unknown | 3 | Planned | November | November
TO-27-RAT-110SA2-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA2 | Unknown | Unknown | 3 | Planned | November | November
TO-27-RAT-T141-01 | DISTRIBUTION TRANSFORMER - RATHKEALE 110-RATHKEALE 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | November | November
TO-27-BAR-T141-02 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | November | November
TO-27-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-BAR,T-CAH-1-02 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-BAR,T-KRA-1-02 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-220 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 3 | Planned | November | November
TO-27-220 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 3 | Planned | November | November
TO-27-LOU-220K1-2-04 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown | 3 | Planned | November | November
TO-27-DSN-MAY-2-04 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-110 kV A6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV B6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | Unknown | Unknown |  | Planned | November | November
TO-27-FIN GIS-110K6-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | Unknown |  | Planned | November | November
TO-27-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 10 | Planned | November | November
TO-27-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 10 | Planned | November | November
TO-27-220 kV A2 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-220 kV B2 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | Unknown | 3 | Planned | November | November
TO-27-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | Unknown | Unknown | 5 | Planned | November | November
TO-27-FIN GIS-GLA-1-01 | 110kV FEEDER - FINGLAS GIS 110-GLASMORE 110-1 | Unknown | Unknown | 5 | Reference (Planned) | November | November
TO-27-BGT-110K1-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-110kV A1 @ BGT-01 | BUSBAR SECTION - BALLYRAGGET 110-BALLYRAGGET 110-110A1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-BGT-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-27-220 kV A8 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A8 | Unknown | Unknown | 15 | Planned | November | December
TO-27-220 kV B8 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B8 | Unknown | Unknown | 15 | Planned | November | December
TO-27-INC-SA6-8CB-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA6-8CB | Unknown | Unknown | 15 | Planned | November | December
TO-27-INC-SA8-10CB-04 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA8-10CB | Unknown | Unknown | 15 | Planned | November | December
TO-27-INC-SB6-8CB-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB6-8CB | Unknown | Unknown | 15 | Planned | November | December
TO-27-INC-SB8-10CB-04 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB8-10CB | Unknown | Unknown | 15 | Planned | November | December
TO-27-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 15 | Planned | November | December
TO-27-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-DEN-DRY-1-02 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | Unknown | Unknown | 2 | Planned | November | November
TO-27-DRY-GOR-1-04 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-DGN-110SA1-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | Unknown | 10 | Planned | November | November
TO-27-DGN-110SA2-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | Unknown | 10 | Planned | November | November
TO-27-DGN-T141-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | November | November
TO-27-DGN-WOH-1-02 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-27-RAF-TBG-1-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown | Unknown | 1 | Planned | November | November
TO-27-110 kV A6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV B6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | Unknown | Unknown |  | Planned | November | November
TO-27-FIN GIS-110K6-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | Unknown |  | Planned | November | November
TO-27-FIN GIS-110SA4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 3 | Planned | November | November
TO-27-FIN GIS-110SB4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 3 | Planned | November | November
TO-27-FIN GIS-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2104 | Unknown | Unknown | 3 | Planned | November | November
TO-27-110 kV A2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-KBY-MR-2-04 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV A2 @ MR-02 | BUSBAR SECTION - MARINA 110-MARINA 110-110A2 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV B2 @ MR-02 | BUSBAR SECTION - MARINA 110-MARINA 110-110B2 | Unknown | Unknown |  | Planned | November | November
TO-27-CSH-CLN-1-04 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-CBR-CLN-1-03 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | Unknown | Unknown | 15 | Planned | November | December
TO-27-CLN-110SA1-02 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | Unknown | Unknown | 7 | Planned | November | November
TO-27-CLN-T141-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | November | November
TO-27-DER-KIN-1-05 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 10 | Planned | November | December
TO-27-FIN-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 10 | Planned | November | December
TO-27-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | November | December
TO-27-KIN-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | November | December
TO-27-KIN-RTN-03 | 110kV FEEDER - KINNEGAD 110-RATTIN 110-1 | Unknown | Unknown | 10 | Planned | November | December
TO-27-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | Unknown | 10 | Planned | November | December
TO-27-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-DFR,T-KIN-1-05 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 10 | Planned | December | December
TO-27-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | Unknown | Unknown | 10 | Planned | December | December
TO-27-KIN-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | December | December
TO-27-KIN-T102-03 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | Unknown | 10 | Planned | December | December
TO-27-CAH-TIP-1-05 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | Unknown | Unknown | 6 | Planned | December | December
TO-27-COL-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | December | December
TO-27-COL-FIN GIS-1-02 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | Unknown | Unknown | 2 | Planned | December | December
TO-27-TIP-110SA1-04 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | Unknown | Unknown | 6 | Planned | December | December
TO-27-TIP-110SA2-03 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | Unknown | Unknown | 6 | Planned | December | December
TO-27-FLA-LOU-1-04 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | Unknown | Unknown | 2 | Planned | December | December
TO-27-PB-R2002-04 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown | 5 | Planned | December | December
TO-27-CLT-MAY-1-01 | 220kV FEEDER - CASTLELOST 220-MAYNOOTH 220-1 | Unknown | Unknown | 5 | Planned | December | December
TO-27-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | Unknown | Unknown | 8 | Planned | December | January

## GEN_AreaSouthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-27-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 53 | 38 | 38 | Proposed | 04/01/2027 | 25/02/2027
TO-27-220 kV A1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220A1 | Unknown | Unknown | 40 | Planned | January | March
TO-27-220 kV B1 @ KLN-01 | BUSBAR SECTION - KILLONAN 220-KILLONAN 220-220B1 | Unknown | Unknown | 40 | Planned | January | March
TO-27-KLN-T2103-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2103 | Unknown | Unknown | 40 | Planned | January | March
TO-27-KPG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-3CB | 1 | 1 | 1 | Proposed | 13/01/2027 | 13/01/2027
TO-27-KPG-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 220-KILPADDOGE 220-220SB2-4CB | 1 | 1 | 1 | Proposed | 15/01/2027 | 15/01/2027
TO-27-BVK-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | 10 | 8 | 8 | Proposed | 18/01/2027 | 27/01/2027
TO-27-CAH-TIP-1-03 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | Unknown | Unknown | 8 | Planned | January | January
TO-27-TIP-110SA1-02 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | Unknown | Unknown | 8 | Planned | January | January
TO-27-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | Unknown | Unknown | 8 | Planned | January | January
TO-27-KNR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKANURE 110-KNOCKANURE 110-110SB1-2CB | 5 | 5 | 5 | Proposed | 25/01/2027 | 29/01/2027
TO-27-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Proposed | 26/01/2027 | 27/01/2027
TO-27-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-110 kV B2 @ AA GIS-01 | BUSBAR SECTION - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-110B2 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-AA GIS-ENN-1-02 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-AA GIS-T102-03 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-110 kV A2 @ ENN-01 | BUSBAR SECTION - ENNIS 110-ENNIS 110-110A2 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-ENN-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 99 | Planned | February | June
TO-27-KLN-SH-1-03 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 99 | Planned | February | June
TO-27-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | Unknown | Unknown | 2 | Planned | February | February
TO-27-DJG-KPG-1-01 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | Unknown | Unknown | 10 | Planned | February | February
TO-27-DJG-KPG-1-03 | 110kV FEEDER - DROMBEG 110-KILPADDOGE 110-1 | Unknown | Unknown | 10 | Planned | February | February
TO-27-AUG-KPG-1-02 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | Unknown | Unknown | 70 | Planned | February | May
TO-27-KLN-T2101-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2101 | Unknown | Unknown | 3 | Planned | February | February
TO-27-MP GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 110-MONEYPOINT GIS 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | February | February
TO-27-MP GIS-400SA1-2CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-2CB | Unknown | Unknown | 1 | Planned | February | February
TO-27-MP GIS-400SA1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA1-3CB | Unknown | Unknown | 1 | Planned | February | February
TO-27-CAH-TIP-1-04 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-TIP-110SA1-03 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-TIP-110SA2-02 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | Unknown | Unknown | 5 | Planned | February | February
TO-27-MP GIS-400SA2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SA2-4CB | Unknown | Unknown | 8 | Planned | February | February
TO-27-DJG-TRL-1-01 | 110kV FEEDER - DROMBEG 110-TRALEE 110-1 | Unknown | Unknown | 1 | Planned | February | February
TO-27-DJG-TRL-1-04 | 110kV FEEDER - DROMBEG 110-TRALEE 110-1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-MP GIS-400SB1-3CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB1-3CB | Unknown | Unknown | 8 | Planned | February | March
TO-27-DJG-T134-01 | GENERATOR TRANSFORMER - DROMBEG 110-DROMBEG 33-T134 | Unknown | Unknown | 5 | Planned | March | March
TO-27-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 20 | Planned | March | March
TO-27-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 20 | Planned | March | March
TO-27-220 kV A1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220A1 | Unknown | Unknown | 49 | Planned | March | May
TO-27-220 kV B1 @ TB-01 | BUSBAR SECTION - TARBERT 220-TARBERT 220-220B1 | Unknown | Unknown | 49 | Planned | March | May
TO-27-110 kV A2 @ BVK-03 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-110 kV B2 @ BVK-03 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-110K2-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | Unknown | 10 | Planned | March | March
TO-27-220 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-220 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-220K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | Unknown | Unknown | 10 | Planned | March | March
TO-27-BVK-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | Unknown | Unknown | 10 | Planned | March | March
TO-27-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-MP GIS-400SB2-4CB-01 | COUPLER/SECTIONALISING CB - MONEYPOINT GIS 400-MONEYPOINT GIS 400-400SB2-4CB | Unknown | Unknown | 8 | Planned | March | March
TO-27-BYH-BVK-1-01 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | Unknown | Unknown | 1 | Planned | March | March
TO-27-BYH-BVK-1-03 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-110 kV A2 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-110 kV B2 @ BVK-04 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-110K2-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-110SB1-2CB-04 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-220 kV A2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220A2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-220 kV B2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220B2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-220K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220K2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-BVK-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 220-BALLYVOUSKILL 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-DAL-T141-01 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | April | April
TO-27-DAL-T141-03 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | April | April
TO-27-DAL,T-DAL-1-03 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 24 | Planned | April | May
TO-27-KPG-T2101-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2101 | Unknown | Unknown | 10 | Planned | April | April
TO-27-AA GIS-T102-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G2-T102 | Unknown | Unknown | 2 | Planned | April | April
TO-27-TB-110K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 110-TARBERT 110-110K1-2 | Unknown | Unknown | 2 | Planned | April | April
TO-27-AA GIS-ENN-1-01 | 110kV FEEDER - ARDNACRUSHA GIS 110-ENNIS 110-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-KLN-SH-1-05 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 52 | Planned | April | June
TO-27-TB-T101-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G1-T101 | Unknown | Unknown | 2 | Planned | April | April
TO-27-CKN-KER-1-01 | 110kV FEEDER - CLONKEEN 110-KNOCKEARAGH 110-1 | Unknown | Unknown | 1 | Planned | April | April
TO-27-AUG-KPG-1-01 | 110kV FEEDER - AUGHINISH 110-KILPADDOGE 110-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-TB-T102-01 | GENERATOR TRANSFORMER - TARBERT 110-TARBERT G2-T102 | Unknown | Unknown | 8 | Planned | April | April
TO-27-BVK-GRO-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-GARROW 110-1 | Unknown | Unknown | 18 | Planned | April | May
TO-27-CTN-110SA1-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | Unknown | Unknown | 8 | Planned | April | May
TO-27-CTN-110SA2-01 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | Unknown | Unknown | 8 | Planned | April | May
TO-27-CTN-T142-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | April | May
TO-27-CTN-T144-01 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | Unknown | Unknown | 8 | Reference (Planned) | April | May
TO-27-CTN-TIP-1-01 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | Unknown | Unknown | 8 | Planned | April | May
TO-27-TB-220K1-2-01 | COUPLER/SECTIONALISING CB - TARBERT 220-TARBERT 220-220K1-2 | Unknown | Unknown | 4 | Planned | April | April
TO-27-KPG-TB-1-01 | 220kV FEEDER - KILPADDOGE 220-TARBERT 220-1 | Unknown | Unknown | 7 | Planned | May | May
TO-27-CLH-T122-01 | GENERATOR TRANSFORMER - CLAHANE 110-CLAHANE 20-T122 | Unknown | Unknown | 1 | Planned | May | May
TO-27-DAL-T141-02 | DISTRIBUTION TRANSFORMER - DALLOW 110-DALLOW 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | May | May
TO-27-DAL,T-DAL-1-04 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-KNR-TRI-2-01 | 110kV FEEDER - KNOCKANURE 110-TRIEN 110-2 | Unknown | Unknown | 2 | Planned | May | May
TO-27-AUG-SK-3-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-3 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MP GIS-T121-02 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MP GIS-T121-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 20-T121 | Unknown | Unknown | 7 | Planned | May | May
TO-27-MP GIS-T2102-01 | TRANSFORMER - MONEYPOINT GIS 220-MONEYPOINT GIS 110-T2102 | Unknown | Unknown | 5 | Planned | May | May
TO-27-SH-TMY-1-02 | 110kV FEEDER - SHANNONBRIDGE 110-TIMONEY 110-1 | Unknown | Unknown | 15 | Planned | May | May
TO-27-SH-TMY-1-03 | 110kV FEEDER - SHANNONBRIDGE 110-TIMONEY 110-1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-AUG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | May | May
TO-27-AUG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - AUGHINISH 110-AUGHINISH 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | May | May
TO-27-AUG-CFM-2-01 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 2 | Planned | May | May
TO-27-AUG-SK-4-02 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 2 | Planned | May | May
TO-27-CFM-T102-02 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 2 | Reference (Planned) | May | May
TO-27-SK-T104-03 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 2 | Planned | May | May
TO-27-SK-T104-01 | GENERATOR TRANSFORMER - SEALROCK 110-SEALROCK G4-T104 | Unknown | Unknown | 4 | Planned | May | May
TO-27-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 6 | Planned | May | May
TO-27-COT-FILTER1-01 | CAPACITOR/SVC/REACTOR - COOMATAGGART 110-COOMATAGGART 110-FILTER1 | Unknown | Unknown | 10 | Planned | May | May
TO-27-KPG-MP GIS-1-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-1 | Unknown | Unknown | 10 | Planned | May | May
TO-27-MTN-MUN-1-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MUN-T101-01 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T101 | Unknown | Unknown | 5 | Reference (Planned) | May | May
TO-27-PRO-TB-1-01 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-110 kV B2 @ KPG-01 | BUSBAR SECTION - KILPADDOGE 110-KILPADDOGE 110-110B2 | Unknown | Unknown | 3 | Planned | May | May
TO-27-KPG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB1-2CB | Unknown | Unknown | 3 | Planned | May | May
TO-27-KPG-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILPADDOGE 110-KILPADDOGE 110-110SB2-4CB | Unknown | Unknown | 3 | Planned | May | May
TO-27-KPG-T2102-02 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | Unknown | Unknown | 3 | Planned | May | May
TO-27-KLN-NEN-1-02 | 110kV FEEDER - KILLONAN 110-NENAGH 110-1 | Unknown | Unknown | 20 | Reference (Planned) | May | June
TO-27-KLN-NEN-1-01 | 110kV FEEDER - KILLONAN 110-NENAGH 110-1 | Unknown | Unknown | 30 | Reference (Planned) | May | July
TO-27-NEN-T141-01 | DISTRIBUTION TRANSFORMER - NENAGH 110-NENAGH 38-T141 | Unknown | Unknown | 30 | Reference (Planned) | May | July
TO-27-NEN-T141-02 | DISTRIBUTION TRANSFORMER - NENAGH 110-NENAGH 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | May | June
TO-27-DRU-CAP2-01 | CAPACITOR/SVC/REACTOR - DRUMLINE 110-DRUMLINE 110-CAP2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-LIM-RAT-1-01 | 110kV FEEDER - LIMERICK 110-RATHKEALE 110-1 | Unknown | Unknown | 10 | Planned | May | June
TO-27-BYH-GLE-1-01 | 110kV FEEDER - BALLYNAHULLA 110-GLENLARA 110-1 | Unknown | Unknown | 2 | Planned | May | May
TO-27-AUG-SK-4-01 | 110kV FEEDER - AUGHINISH 110-SEALROCK 110-4 | Unknown | Unknown | 2 | Planned | May | June
TO-27-CHA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-GLE-1-01 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-27-CHA-GLE-1-02 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-KLN-1-01 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-KLN-1-03 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-27-CHA-T141-01 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | June | June
TO-27-CHA-T142-01 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | June | June
TO-27-KPG-MP GIS-2-01 | 220kV FEEDER - KILPADDOGE 220-MONEYPOINT GIS 220-2 | Unknown | Unknown | 10 | Planned | June | June
TO-27-KLN-LIM-1-03 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 90 | Planned | June | October
TO-27-ATE-T121-01 | GENERATOR TRANSFORMER - ATHEA 110-ATHEA 20-T121 | Unknown | Unknown | 3 | Planned | June | June
TO-27-CFM-T101-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T101 | Unknown | Unknown | 4 | Reference (Planned) | June | June
TO-27-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-CKN-GRO-1-01 | 110kV FEEDER - CLONKEEN 110-GARROW 110-1 | Unknown | Unknown | 26 | Planned | June | July
TO-27-AA GIS-CAP1-01 | CAPACITOR/SVC/REACTOR - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS 110-CAP1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown | 20 | Planned | June | July
TO-27-CBA-TRI-1-01 | 110kV FEEDER - CLOGHBOOLA 110-TRIEN 110-1 | Unknown | Unknown |  | Planned | June | July
TO-27-220 kV A2 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 220-KILLONAN GIS 220-220A2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-220 kV B2 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 220-KILLONAN GIS 220-220B2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-KLN GIS-220K2-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220K2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-KLN GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-KLN GIS-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-REM-T141-01 | DISTRIBUTION TRANSFORMER - REAMORE 110-REAMORE 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | June | July
TO-27-REM-TRL-1-01 | 110kV FEEDER - REAMORE 110-TRALEE 110-1 | Unknown | Unknown | 20 | Planned | June | July
TO-27-KLN-LIM-1-01 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 6 | Planned | June | June
TO-27-KLN-LIM-1-02 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 80 | Planned | June | October
TO-27-110 kV A2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-110 kV B2 @ BVK-01 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-BVK-110K2-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-BVK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-BVK-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-MTN-MUN-2-01 | 110kV FEEDER - MONETEEN 110-MUNGRET 110-2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-MUN-T102-02 | TSO CUSTOMER TRANSFORMER - MUNGRET 110-MUNGRET 10-T102 | Unknown | Unknown | 5 | Reference (Planned) | June | June
TO-27-KNR-T2102-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2102 | Unknown | Unknown | 9 | Planned | June | July
TO-27-DRU-ENN-1-02 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | Unknown | Unknown | 80 | Planned | June | October
TO-27-DRU-ENN-1-01 | 110kV FEEDER - DRUMLINE 110-ENNIS 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-110 kV A4 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A4 | Unknown | Unknown |  | Planned | June | July
TO-27-110 kV B4 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B4 | Unknown | Unknown | 7 | Planned | June | July
TO-27-KLN GIS-110K4-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110K4 | Unknown | Unknown | 7 | Planned | June | July
TO-27-KLN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA2-4CB | Unknown | Unknown | 7 | Planned | June | July
TO-27-KLN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB2-4CB | Unknown | Unknown | 7 | Planned | June | July
TO-27-220 kV A2 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 220-KILLONAN GIS 220-220A2 | Unknown | Unknown | 2 | Planned | June | June
TO-27-220 kV B2 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 220-KILLONAN GIS 220-220B2 | Unknown | Unknown | 2 | Planned | June | June
TO-27-KLN GIS-220K2-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220K2 | Unknown | Unknown | 2 | Planned | June | June
TO-27-KLN GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | June | June
TO-27-KLN GIS-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 220-KILLONAN GIS 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | June | June
TO-27-KLN-KLN GIS-1-220-01 | 220kV FEEDER - KILLONAN 220-KILLONAN GIS 220-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-BYH-BVK-1-02 | 220kV FEEDER - BALLYNAHULLA 220-BALLYVOUSKILL 220-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-THU-STATCOM-01 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | Unknown | Unknown | 5 | Planned | June | July
TO-27-CGL-T121-01 | GENERATOR TRANSFORMER - COOMAGEARLAHY 110-COOMAGEARLAHY 20-T121 | Unknown | Unknown | 3 | Planned | June | July
TO-27-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown | 58 | Planned | June | September
TO-27-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown |  | Planned | June | September
TO-27-DSN-MP GIS-1-04 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown | 58 | Planned | June | September
TO-27-110 kV A2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110A2 | Unknown | Unknown | 2 | Planned | June | July
TO-27-110 kV B2 @ BVK-02 | BUSBAR SECTION - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110B2 | Unknown | Unknown | 2 | Planned | June | July
TO-27-BVK-110K2-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110K2 | Unknown | Unknown | 2 | Planned | June | July
TO-27-BVK-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | June | July
TO-27-BVK-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYVOUSKILL 110-BALLYVOUSKILL 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | June | July
TO-27-BVK-T2102-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2102 | Unknown | Unknown | 2 | Planned | June | July
TO-27-110 kV A2 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-110 kV B2 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-KLN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-KLN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-KLN GIS-T2102-01 | TRANSFORMER - KILLONAN GIS 220-KILLONAN GIS 110-T2102 | Unknown | Unknown | 2 | Planned | July | July
TO-27-MP GIS-PRO-1-02 | 220kV FEEDER - MONEYPOINT GIS 220-PROSPECT 220-1 | Unknown | Unknown | 10 | Planned | July | July
TO-27-AHA-KLN-2-01 | 110kV FEEDER - AHANE 110-KILLONAN 110-2 | Unknown | Unknown | 50 | Reference (Planned) | July | September
TO-27-AHA-T102-01 | DISTRIBUTION TRANSFORMER - AHANE 110-AHANE 10-T102 | Unknown | Unknown | 50 | Reference (Planned) | July | September
TO-27-KNR-T2101-01 | TRANSFORMER - KNOCKANURE 220-KNOCKANURE 110-T2101 | Unknown | Unknown | 9 | Planned | July | July
TO-27-MP GIS-ST101-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 110-MONEYPOINT GIS 10-ST101 | Unknown | Unknown | 2 | Planned | July | July
TO-27-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-IKE-T141-01 | DISTRIBUTION TRANSFORMER - IKERRIN 110-IKERRIN 38-T141 | Unknown | Unknown | 6 | Reference (Planned) | July | July
TO-27-IKE,T-IKE-1-01 | 110kV FEEDER - IKERRIN tee-IKERRIN 110-1 | Unknown | Unknown | 6 | Planned | July | July
TO-27-IKE,T-THU-1-01 | 110kV FEEDER - IKERRIN tee-THURLES 110-1 | Unknown | Unknown | 6 | Planned | July | July
TO-27-IKE,T-TMY1-01 | 110kV FEEDER - IKERRIN tee-TIMONEY 110-1 | Unknown | Unknown | 6 | Planned | July | July
TO-27-ENN-SLC-1-01 | 110kV FEEDER - ENNIS 110-SLIEVECALLAN 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-27-SLC-T121-01 | GENERATOR TRANSFORMER - SLIEVECALLAN 110-SLIEVECALLAN 20-T121 | Unknown | Unknown | 1 | Planned | July | July
TO-27-LIM-MTN-1-06 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown |  | Planned | July | October
TO-27-BYH-CDL-1-01 | 110kV FEEDER - BALLYNAHULLA 110-CORDAL 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-27-BYH-T2101-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2101 | Unknown | Unknown | 10 | Planned | July | July
TO-27-LIM-110SA1-01 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-LIM-110SA2-02 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 5 | Planned | July | July
TO-27-LIM-MTN-1-03 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 59 | Planned | July | October
TO-27-LIM-MTN-1-01 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-LIM-T141-01 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-27-TRI-CAP1-01 | CAPACITOR/SVC/REACTOR - TRIEN 110-TRIEN 110-CAP1 | Unknown | Unknown | 10 | Planned | July | August
TO-27-LIM-MTN-1-04 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 50 | Planned | July | October
TO-27-GRO-T122-01 | GENERATOR TRANSFORMER - GARROW 110-GARROW 20-T122 | Unknown | Unknown | 3 | Planned | August | August
TO-27-BVK-T2101-01 | TRANSFORMER - BALLYVOUSKILL 220-BALLYVOUSKILL 110-T2101 | Unknown | Unknown | 2 | Planned | August | August
TO-27-KPG-T2102-01 | TRANSFORMER - KILPADDOGE 220-KILPADDOGE 110-T2102 | Unknown | Unknown | 12 | Planned | August | August
TO-27-AUG-CFM-2-03 | 110kV FEEDER - AUGHINISH 110-CASTLEFARM 110-2 | Unknown | Unknown | 10 | Planned | August | August
TO-27-BYH-T2102-01 | TRANSFORMER - BALLYNAHULLA 220-BALLYNAHULLA 110-T2102 | Unknown | Unknown | 5 | Planned | August | August
TO-27-BVK-COT-1-01 | 110kV FEEDER - BALLYVOUSKILL 110-COOMATAGGART 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-27-COT-T132-02 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | Unknown | Unknown | 5 | Planned | August | August
TO-27-COT-T132-01 | GENERATOR TRANSFORMER - COOMATAGGART 110-COOMATAGGART 33-T132 | Unknown | Unknown | 10 | Planned | August | August
TO-27-COT-T141-01 | DISTRIBUTION TRANSFORMER - COOMATAGGART 110-COOMATAGGART 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | August | August
TO-27-GLE-KCR-1-01 | 110kV FEEDER - GLENLARA 110-KNOCKACUMMER 110-1 | Unknown | Unknown | 15 | Planned | August | August
TO-27-KCR-T121-01 | GENERATOR TRANSFORMER - KNOCKACUMMER 110-KNOCKACUMMER 20-T121 | Unknown | Unknown | 15 | Planned | August | August
TO-27-MP GIS-T4002-01 | GENERATOR TRANSFORMER - MONEYPOINT GIS 400-MONEYPOINT GIS G2-T4002 | Unknown | Unknown | 2 | Planned | August | August
TO-27-CTN-110SA1-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-27-CTN-110SA2-02 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-CTN-T142-02 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-27-CTN-T144-02 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-27-CTN-TIP-1-02 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-27-LIM-MTN-1-05 | 110kV FEEDER - LIMERICK 110-MONETEEN 110-1 | Unknown | Unknown | 40 | Planned | August | October
TO-27-CTN-110SA1-03 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA1 | Unknown | Unknown | 4 | Planned | August | August
TO-27-CTN-110SA2-03 | SECTIONALISING DISCONNECT - CAUTEEN 110-CAUTEEN 110-110SA2 | Unknown | Unknown | 4 | Planned | August | August
TO-27-CTN-T142-03 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T142 | Unknown | Unknown | 4 | Reference (Planned) | August | August
TO-27-CTN-T144-03 | DISTRIBUTION TRANSFORMER - CAUTEEN 110-CAUTEEN 38-T144 | Unknown | Unknown | 4 | Reference (Planned) | August | August
TO-27-CTN-TIP-1-03 | 110kV FEEDER - CAUTEEN 110-TIPPERARY 110-1 | Unknown | Unknown | 4 | Planned | August | August
TO-27-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | Unknown | Unknown | 5 | Planned | August | August
TO-27-TRL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - TRALEE 110-TRALEE 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | August | September
TO-27-TRL-T142-02 | DISTRIBUTION TRANSFORMER - TRALEE 110-TRALEE 38-T142 | Unknown | Unknown | 3 | Reference (Planned) | August | September
TO-27-110 kV A4 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A4 | Unknown | Unknown | 7 | Planned | September | September
TO-27-110 kV B4 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B4 | Unknown | Unknown | 7 | Planned | September | September
TO-27-KLN GIS-110K4-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110K4 | Unknown | Unknown | 7 | Planned | September | September
TO-27-KLN GIS-110SA2-4CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA2-4CB | Unknown | Unknown | 7 | Planned | September | September
TO-27-KLN GIS-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB2-4CB | Unknown | Unknown | 7 | Planned | September | September
TO-27-CFM-T102-01 | TSO CUSTOMER TRANSFORMER - CASTLEFARM 110-CASTLEFARM 10-T102 | Unknown | Unknown | 4 | Reference (Planned) | September | September
TO-27-AA GIS-T103-01 | GENERATOR TRANSFORMER - ARDNACRUSHA GIS 110-ARDNACRUSHA GIS G3-T103 | Unknown | Unknown | 7 | Planned | September | September
TO-27-110 kV A2 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV B2 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-KLN GIS-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-KLN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-KLN GIS-T2102-02 | TRANSFORMER - KILLONAN GIS 220-KILLONAN GIS 110-T2102 | Unknown | Unknown | 2 | Planned | September | September
TO-27-KLN-SH-1-04 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 57 | Planned | September | December
TO-27-110 kV A1 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A1 | Unknown | Unknown | 7 | Planned | September | October
TO-27-110 kV B1 @ KLN GIS-01 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B1 | Unknown | Unknown | 7 | Planned | September | October
TO-27-KLN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-2CB | Unknown | Unknown | 7 | Planned | September | October
TO-27-KLN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-3CB | Unknown | Unknown | 7 | Planned | September | October
TO-27-KLN GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-2CB | Unknown | Unknown | 7 | Planned | September | October
TO-27-KLN GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-3CB | Unknown | Unknown | 7 | Planned | September | October
TO-27-KLN-LIM-1-04 | 110kV FEEDER - KILLONAN 110-LIMERICK 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-LIM-110SA1-02 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-LIM-110SA1-03 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-LIM-110SA2-03 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-LIM-110SA2-04 | SECTIONALISING DISCONNECT - LIMERICK 110-LIMERICK 110-110SA2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-LIM-T141-02 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | October | October
TO-27-LIM-T141-03 | DISTRIBUTION TRANSFORMER - LIMERICK 110-LIMERICK 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | October | October
TO-27-CHA-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - CHARLEVILLE 110-CHARLEVILLE 110-110SA1-2CB | Unknown | Unknown | 20 | Planned | October | November
TO-27-CHA-GLE-1-03 | 110kV FEEDER - CHARLEVILLE 110-GLENLARA 110-1 | Unknown | Unknown | 20 | Planned | October | November
TO-27-CHA-KLN-1-04 | 110kV FEEDER - CHARLEVILLE 110-KILLONAN 110-1 | Unknown | Unknown | 20 | Planned | October | November
TO-27-CHA-T141-02 | DISTRIBUTION TRANSFORMER - CHARLEVILLE 110-CHARLEVILLE 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | October | November
TO-27-DRU-110SA1-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-DRU-110SA2-01 | SECTIONALISING DISCONNECT - DRUMLINE 110-DRUMLINE 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-27-DRU-T141-01 | DISTRIBUTION TRANSFORMER - DRUMLINE 110-DRUMLINE 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-110 kV A1 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110A1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-110 kV B1 @ KLN GIS-02 | BUSBAR SECTION - KILLONAN GIS 110-KILLONAN GIS 110-110B1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - KILLONAN GIS 110-KILLONAN GIS 110-110SB1-3CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-T2101-01 | TRANSFORMER - KILLONAN GIS 220-KILLONAN GIS 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-27-KLN GIS-T2101-02 | TRANSFORMER - KILLONAN GIS 220-KILLONAN GIS 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-27-BOL-ENN-1-02 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ENN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-ENN-T101-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-ENN-T141-01 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-BOL-ENN-1-03 | 110kV FEEDER - BOOLTIAGH 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CSH-ENN-1-03 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ENN-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ENNIS 110-ENNIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-ENN-T101-02 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-ENN-T141-02 | DISTRIBUTION TRANSFORMER - ENNIS 110-ENNIS 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | Unknown | Unknown | 20 | Planned | October | November
TO-27-AGL-ENN-1-03 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | Unknown | Unknown | 42 | Planned | October | December
TO-27-TBK-T141-01 | DISTRIBUTION TRANSFORMER - TULLABRACK 110-TULLABRACK 38-T141 | Unknown | Unknown | 9 | Reference (Planned) | October | October
TO-27-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 9 | Planned | October | November
TO-27-KPG-RAT-1-01 | 110kV FEEDER - KILPADDOGE 110-RATHKEALE 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-27-OUG-T141-01 | DISTRIBUTION TRANSFORMER - OUGHTRAGH 110-OUGHTRAGH 38-T141 | Unknown | Unknown |  | Reference (Planned) | November | November
TO-27-OUG,T-KER-1-01 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-OUG,T-KER-1-02 | 110kV FEEDER - OUGHTRAGH tee-KNOCKEARAGH 110-1 | Unknown | Unknown |  | Planned | November | November
TO-27-OUG,T-OUG-1-02 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | Unknown | Unknown |  | Planned | November | November
TO-27-OUG,T-OUG-1-01 | 110kV FEEDER - OUGHTRAGH tee-OUGHTRAGH 110-1 | Unknown | Unknown | 3 | Planned | November | November
TO-27-OUG,T-TRL-1-01 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-OUG,T-TRL-1-04 | 110kV FEEDER - OUGHTRAGH tee-TRALEE 110-1 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV A2 @ RAT-01 | BUSBAR SECTION - RATHKEALE 110-RATHKEALE 110-110A2 | Unknown | Unknown | 3 | Planned | November | November
TO-27-RAT-110SA2-01 | SECTIONALISING DISCONNECT - RATHKEALE 110-RATHKEALE 110-110SA2 | Unknown | Unknown | 3 | Planned | November | November
TO-27-RAT-T141-01 | DISTRIBUTION TRANSFORMER - RATHKEALE 110-RATHKEALE 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | November | November
TO-27-AUG-MTN-1-01 | 110kV FEEDER - AUGHINISH 110-MONETEEN 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-CAH-TIP-1-05 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | Unknown | Unknown | 6 | Planned | December | December
TO-27-TIP-110SA1-04 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | Unknown | Unknown | 6 | Planned | December | December
TO-27-TIP-110SA2-03 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | Unknown | Unknown | 6 | Planned | December | December

## GEN_SouthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-27-TTU-131-01 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | 2 | 2 | 2 | Proposed | 05/01/2027 | 06/01/2027
TO-27-ATY-CLW-1-01 | 110kV FEEDER - ATHY 110-CARLOW 110-1 | 1 | 1 | 1 | Proposed | 06/01/2027 | 06/01/2027
TO-27-BLK-T142-01 | DISTRIBUTION TRANSFORMER - BLAKE 110-BLAKE 38-T142 | 19 | 15 | 15 | Reference (Proposed) | 11/01/2027 | 29/01/2027
TO-27-BLK,T-BLK-1-01 | 110kV FEEDER - BLAKE tee-BLAKE 110-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-BLK,T-NEW-1-01 | 110kV FEEDER - BLAKE tee-NEWBRIDGE 110-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-CAH-TIP-1-03 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | Unknown | Unknown | 8 | Planned | January | January
TO-27-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | 2 | 2 | 2 | Proposed | 26/01/2027 | 27/01/2027
TO-27-GI GIS-220K2-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | 1 | 1 | 1 | Proposed | 27/01/2027 | 27/01/2027
TO-27-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | Unknown | Unknown | 1 | Planned | February | February
TO-27-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | February | February
TO-27-BGT-KKY-1-01 | 110kV FEEDER - BALLYRAGGET 110-KILKENNY 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-BGT-141-01 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | February | February
TO-27-BGT-141-02 | DISTRIBUTION TRANSFORMER - BALLYRAGGET 110-BALLYRAGGET 38-T141 | Unknown | Unknown | 30 | Reference (Planned) | February | March
TO-27-ROP-WEX-1-01 | 110kV FEEDER - ROSSPILE 110-WEXFORD 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-BDA-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | Unknown | Unknown | 15 | Planned | February | February
TO-27-BDA-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BARODA 110-BARODA 110-110SA1-2CB | Unknown | Unknown | 25 | Planned | February | March
TO-27-BDA-MON-1-02 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-BDA-MON-1-03 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 25 | Planned | February | March
TO-27-BDA-T102-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 25 | Planned | February | March
TO-27-BDA-T102-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T102 | Unknown | Unknown | 25 | Planned | February | March
TO-27-CAH-TIP-1-04 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-GI GIS-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | Unknown | Unknown | 4 | Planned | February | February
TO-27-ARK-220K1-2-01 | COUPLER/SECTIONALISING CB - ARKLOW 220-ARKLOW 220-220K1-2 | Unknown | Unknown | 1 | Planned | February | February
TO-27-BOG-TTU-1-01 | 110kV FEEDER - BANOGE 110-TULLABEG 110-1 | Unknown | Unknown | 1 | Planned | February | February
TO-27-ATY-T101-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T101 | Unknown | Unknown | 80 | Reference (Planned) | March | June
TO-27-CRA-WEX-1-02 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-ROP-T131-01 | GENERATOR TRANSFORMER - ROSSPILE 110-ROSSPILE 33-T131 | Unknown | Unknown | 4 | Planned | March | March
TO-27-LWD-T2102-01 | TRANSFORMER - LODGEWOOD 220-LODGEWOOD 110-T2102 | Unknown | Unknown | 5 | Planned | March | March
TO-27-BGT-110K1-03 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-110kV B1 @ BGT-01 | BUSBAR SECTION - BALLYRAGGET 110-BALLYRAGGET 110-110B1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BGT-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | March | March
TO-27-CRA-LWD-1-01 | 110kV FEEDER - CRANE 110-LODGEWOOD 110-1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-BOG-110SA2-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA2 | Unknown | Unknown | 1 | Planned | March | March
TO-27-BOG-T121-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T121 | Unknown | Unknown | 1 | Reference (Planned) | March | March
TO-27-CRA-110SA1-01 | SECTIONALISING DISCONNECT - CRANE 110-CRANE 110-110SA1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-CRA-T141-01 | DISTRIBUTION TRANSFORMER - CRANE 110-CRANE 38-T141 | Unknown | Unknown | 4 | Reference (Planned) | March | March
TO-27-CRA-TTU-1-01 | 110kV FEEDER - CRANE 110-TULLABEG 110-1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-PHT-PLS-1-01 | 110kV FEEDER - PHILIPSTOWN 110-PORTLAOISE 110-1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-CUL-RTH-1-01 | 110kV FEEDER - CULLENAGH 110-RATHNASKILLOGE 110-1 | Unknown | Unknown | 1 | Planned | March | March
TO-27-CRA-WEX-1-03 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 9 | Planned | March | April
TO-27-CRA-WEX-1-01 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 6 | Planned | March | April
TO-27-WEX-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | March | March
TO-27-WEX-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 9 | Planned | March | April
TO-27-WEX-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | March | April
TO-27-WEX-CAP2-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 9 | Planned | March | April
TO-27-WEX-CAP4-02 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 9 | Planned | March | April
TO-27-WEX-T122-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown | 9 | Reference (Planned) | March | April
TO-27-WEX-T142-01 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown | 9 | Reference (Planned) | March | April
TO-27-ARK-LWD-1-01 | 220kV FEEDER - ARKLOW 220-LODGEWOOD 220-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-CLW-KLS-1-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-CLW-KLS-1-02 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-CLW-KLS-1-03 | 110kV FEEDER - CARLOW 110-KELLIS 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-DAL-1-03 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 24 | Planned | April | May
TO-27-DAL,T-STN-1-01 | 110kV FEEDER - DALLOW tee-STONESTOWN 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-STN-1-03 | 110kV FEEDER - DALLOW tee-STONESTOWN 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-GI GIS-LON-1-01 | 220kV FEEDER - GREAT ISLAND GIS 220-LOUGHTOWN 220-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-STR-T141-01 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | April | April
TO-27-STR,T-CLW-1-02 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-CLW-1-01 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-STR-1-01 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-GI-T2102-01 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 15 | Planned | April | April
TO-27-GI-T2102-03 | TRANSFORMER - GREAT ISLAND GIS 220-GREAT ISLAND 110-T2102 | Unknown | Unknown | 60 | Planned | April | July
TO-27-110 kV A1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-110 kV B1 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-110 kV A1 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-110 kV B1 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-WOH-T122-01 | GENERATOR TRANSFORMER - WOODHOUSE 110-WOODHOUSE 20-T122 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CLW-110SA1-01 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-CLW-110SA2-02 | SECTIONALISING DISCONNECT - CARLOW 110-CARLOW 110-110SA2 | Unknown | Unknown | 80 | Planned | April | August
TO-27-CLW-KLS-2-03 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown | 10 | Planned | April | May
TO-27-CLW-KLS-2-04 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown | 80 | Planned | April | August
TO-27-CLW-KLS-2-01 | 110kV FEEDER - CARLOW 110-KELLIS 110-2 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CLW-T142-01 | DISTRIBUTION TRANSFORMER - CARLOW 110-CARLOW 38-T142 | Unknown | Unknown | 80 | Reference (Planned) | April | August
TO-27-STR-T141-02 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 80 | Reference (Planned) | April | August
TO-27-STR,T-CLW-1-03 | 110kV FEEDER - STRATFORD tee-CARLOW 110-1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-STR,T-PA-1-03 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-STR,T-STR-1-02 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-110 kV A2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-110 kV B2 @ KLS-01 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-DAL,T-DAL-1-04 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-DAL,T-STN-1-04 | 110kV FEEDER - DALLOW tee-STONESTOWN 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-BDN-110SA2-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-DOO-1-01 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-MRK3-02 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK3 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-110SA1-01 | SECTIONALISING DISCONNECT - BALLYDINE 110-BALLYDINE 110-110SA1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-CUL-1-01 | 110kV FEEDER - BALLYDINE 110-CULLENAGH 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-MRK1-01 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-MRK1-03 | TSO CUSTOMER TRANSFORMER - BALLYDINE 110-BALLYDINE 10-MRK1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDN-T141-02 | DISTRIBUTION TRANSFORMER - BALLYDINE 110-BALLYDINE 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | May | May
TO-27-BDA-NEW-1-02 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | May | June
TO-27-KIR-T131-01 | GENERATOR TRANSFORMER - KILCUMBER 110-KILCUMBER 33-T131 | Unknown | Unknown | 1 | Planned | June | June
TO-27-CDK-T121-01 | GENERATOR TRANSFORMER - CASTLEDOCKRELL 110-CASTLEDOCKRELL 20-T121 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-27-ANR-DOO-1-01 | 110kV FEEDER - ANNER 110-DOON 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-ANR-T101-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T101 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-27-ANR-T103-02 | TSO CUSTOMER TRANSFORMER - ANNER 110-ANNER 10-T103 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-27-BDN-DOO-1-03 | 110kV FEEDER - BALLYDINE 110-DOON 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-CAH-KHL-1-01 | 110kV FEEDER - CAHIR 110-KILL HILL 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-DEY-PLS-1-01 | 110kV FEEDER - DERRYCARNEY 110-PORTLAOISE 110-1 | Unknown | Unknown | 15 | Planned | June | June
TO-27-DOO-110SA1-01 | SECTIONALISING DISCONNECT - DOON 110-DOON 110-110SA1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-CAH-DOO-1-01 | 110kV FEEDER - CAHIR 110-DOON 110-1 | Unknown | Unknown | 10 | Planned | June | June
TO-27-WEX-CAP2-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 3 | Planned | June | June
TO-27-STN-T131-01 | GENERATOR TRANSFORMER - STONESTOWN 110-STONESTOWN 33-T131 | Unknown | Unknown | 1 | Planned | June | June
TO-27-WEX-CAP4-01 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 3 | Planned | June | June
TO-27-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-DGN-WOH-1-01 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | Unknown | 20 | Planned | July | July
TO-27-220 kV A1 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-220 kV A2 @ GI GIS-01 | BUSBAR SECTION - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220A2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-GI GIS-220K1-01 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-GI GIS-220K2-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220K2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-GI GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-GI GIS-KLS-1-04 | 220kV FEEDER - GREAT ISLAND GIS 220-KELLIS 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-ATY-T102-01 | DISTRIBUTION TRANSFORMER - ATHY 110-ATHY 10-T102 | Unknown | Unknown | 80 | Reference (Planned) | July | October
TO-27-CUS-NEW-1-01 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | Unknown | 14 | Planned | July | July
TO-27-CUS-NEW-1-02 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | Unknown | 70 | Planned | July | October
TO-27-ARK-BEG-1-02 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | Unknown | Unknown | 50 | Planned | July | September
TO-27-ARK-BEG-1-01 | 110kV FEEDER - ARKLOW 110-BALLYBEG 110-1 | Unknown | Unknown | 33 | Planned | July | August
TO-27-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | Unknown | 50 | Planned | July | September
TO-27-ARK-CKM GIS-1-03 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | Unknown | 50 | Planned | July | September
TO-27-CUL-WAT-1-01 | 110kV FEEDER - CULLENAGH 110-WATERFORD 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-CUS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-27-CUS-T103/5-03 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 5 | Planned | July | July
TO-27-BRA-NEW-1-01 | 110kV FEEDER - BRACKLONE 110-NEWBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-CUS-NEW-1-03 | 110kV FEEDER - CUSHALING 110-NEWBRIDGE 110-1 | Unknown | Unknown | 60 | Planned | July | October
TO-27-KTN-WAT-1-01 | 110kV FEEDER - KILLOTERAN 110-WATERFORD 110-1 | Unknown | Unknown | 18 | Planned | July | August
TO-27-NEW-110SA1-01 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-NEW-110SA2-02 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 3 | Planned | July | July
TO-27-NEW-T141-01 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | July | July
TO-27-BGT-CNB-1-01 | 110kV FEEDER - BALLYRAGGET 110-COOLNABACKY 110-1 | Unknown | Unknown | 80 | Planned | July | November
TO-27-DGN-110SA1-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | Unknown | 10 | Planned | August | August
TO-27-DGN-110SA2-01 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | Unknown | 10 | Planned | August | August
TO-27-DGN-RTH-1-01 | 110kV FEEDER - DUNGARVAN 110-RATHNASKILLOGE 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-27-DGN-T142-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | August | August
TO-27-110 kV A2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110A2 | Unknown | Unknown | 40 | Planned | August | October
TO-27-110 kV B2 @ GI-02 | BUSBAR SECTION - GREAT ISLAND 110-GREAT ISLAND 110-110B2 | Unknown | Unknown | 40 | Planned | August | October
TO-27-BGT-110K1-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | Unknown | Unknown | 2 | Planned | August | August
TO-27-BGT-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-27-BGT-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-27-GI-WAT-1-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-1 | Unknown | Unknown | 8 | Planned | August | August
TO-27-STR-T141-03 | DISTRIBUTION TRANSFORMER - STRATFORD 110-STRATFORD 38-T141 | Unknown | Unknown | 15 | Reference (Planned) | August | September
TO-27-STR,T-PA-1-04 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-27-STR,T-STR-1-03 | 110kV FEEDER - STRATFORD tee-STRATFORD 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-27-BUT-110SA1-01 | SECTIONALISING DISCONNECT - BUTLERSTOWN 110-BUTLERSTOWN 110-110SA1 | Unknown | Unknown | 4 | Planned | August | September
TO-27-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | Unknown | Unknown | 8 | Planned | August | September
TO-27-110 kV A1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-110 kV B1 @ KLS-03 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-BDA-T101-02 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | Unknown | Unknown | 7 | Planned | September | September
TO-27-BDA-T101-01 | TSO CUSTOMER TRANSFORMER - BARODA 110-BARODA 10-T101 | Unknown | Unknown | 7 | Planned | September | September
TO-27-ARK-T2102-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2102 | Unknown | Unknown | 24 | Planned | September | October
TO-27-BRA-NEW-1-02 | 110kV FEEDER - BRACKLONE 110-NEWBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | September | September
TO-27-BRA-NEW-1-04 | 110kV FEEDER - BRACKLONE 110-NEWBRIDGE 110-1 | Unknown | Unknown | 20 | Planned | September | October
TO-27-NEW-110SA1-02 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | Unknown | Unknown | 3 | Planned | September | September
TO-27-NEW-110SA1-04 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | Unknown | Unknown | 20 | Planned | September | October
TO-27-NEW-110SA2-03 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 3 | Planned | September | September
TO-27-NEW-110SA2-05 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 20 | Planned | September | October
TO-27-NEW-T141-02 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | Unknown | Unknown | 3 | Reference (Planned) | September | September
TO-27-NEW-T141-04 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | September | October
TO-27-CRA-WEX-1-04 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 13 | Planned | September | October
TO-27-WEX-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 13 | Planned | September | October
TO-27-WEX-CAP2-03 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 13 | Planned | September | October
TO-27-WEX-CAP4-03 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 13 | Planned | September | October
TO-27-WEX-T122-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown | 13 | Reference (Planned) | September | October
TO-27-WEX-T142-02 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown | 13 | Reference (Planned) | September | October
TO-27-KLS-KKY-1-01 | 110kV FEEDER - KELLIS 110-KILKENNY 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-27-CUS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CUSHALING 110-CUSHALING 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | October | October
TO-27-CUS-T103/5-01 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 5 | Planned | October | October
TO-27-CUS-T103/5-02 | GENERATOR TRANSFORMER - CUSHALING 110-CUSHALING G3/5-T103/5 | Unknown | Unknown | 3 | Planned | October | October
TO-27-110 kV A2 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110A2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-110 kV B2 @ KLS-02 | BUSBAR SECTION - KELLIS 110-KELLIS 110-110B2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-BOG-110SA1-01 | SECTIONALISING DISCONNECT - BANOGE 110-BANOGE 110-110SA1 | Unknown | Unknown | 3 | Planned | October | October
TO-27-BOG-T122-01 | DISTRIBUTION TRANSFORMER - BANOGE 110-BANOGE 20-T122 | Unknown | Unknown | 3 | Reference (Planned) | October | October
TO-27-CRA-WEX-1-05 | 110kV FEEDER - CRANE 110-WEXFORD 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-WEX-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - WEXFORD 110-WEXFORD 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | October | October
TO-27-WEX-CAP2-04 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP2 | Unknown | Unknown | 2 | Planned | October | October
TO-27-WEX-CAP4-04 | CAPACITOR/SVC/REACTOR - WEXFORD 110-WEXFORD 110-CAP4 | Unknown | Unknown | 2 | Planned | October | October
TO-27-WEX-T122-03 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 20-T122 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-WEX-T142-03 | DISTRIBUTION TRANSFORMER - WEXFORD 110-WEXFORD 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | October | October
TO-27-ARK-T2101-01 | TRANSFORMER - ARKLOW 220-ARKLOW 110-T2101 | Unknown | Unknown | 2 | Planned | October | October
TO-27-BRA-NEW-1-03 | 110kV FEEDER - BRACKLONE 110-NEWBRIDGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-27-NEW-110SA1-03 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA1 | Unknown | Unknown | 1 | Planned | October | October
TO-27-NEW-110SA2-04 | SECTIONALISING DISCONNECT - NEWBRIDGE 110-NEWBRIDGE 110-110SA2 | Unknown | Unknown | 1 | Planned | October | October
TO-27-NEW-T141-03 | DISTRIBUTION TRANSFORMER - NEWBRIDGE 110-NEWBRIDGE 38-T141 | Unknown | Unknown | 1 | Reference (Planned) | October | October
TO-27-ARK-BOG-1-02 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | Unknown | Unknown | 39 | Planned | October | December
TO-27-ARK-BOG-1-01 | 110kV FEEDER - ARKLOW 110-BANOGE 110-1 | Unknown | Unknown | 1 | Planned | October | October
TO-27-GI-KKY-1-01 | 110kV FEEDER - GREAT ISLAND 110-KILKENNY 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ATY-110SA1-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ATY-110SA2-02 | SECTIONALISING DISCONNECT - ATHY 110-ATHY 110-110SA2 | Unknown | Unknown | 2 | Planned | October | October
TO-27-ATY-CNB-1-01 | 110kV FEEDER - ATHY 110-COOLNABACKY 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CUS-PHT-1-01 | 110kV FEEDER - CUSHALING 110-PHILIPSTOWN 110-1 | Unknown | Unknown | 4 | Planned | October | October
TO-27-GI-WAT-2-01 | 110kV FEEDER - GREAT ISLAND 110-WATERFORD 110-2 | Unknown | Unknown | 3 | Planned | October | October
TO-27-BAR,T-CAH-1-02 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-BGT-110K1-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110K1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-110kV A1 @ BGT-01 | BUSBAR SECTION - BALLYRAGGET 110-BALLYRAGGET 110-110A1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-BGT-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - BALLYRAGGET 110-BALLYRAGGET 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | November | November
TO-27-DGN-110SA1-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA1 | Unknown | Unknown | 10 | Planned | November | November
TO-27-DGN-110SA2-02 | SECTIONALISING DISCONNECT - DUNGARVAN 110-DUNGARVAN 110-110SA2 | Unknown | Unknown | 10 | Planned | November | November
TO-27-DGN-T141-01 | DISTRIBUTION TRANSFORMER - DUNGARVAN 110-DUNGARVAN 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | November | November
TO-27-DGN-WOH-1-02 | 110kV FEEDER - DUNGARVAN 110-WOODHOUSE 110-1 | Unknown | Unknown | 10 | Planned | November | November
TO-27-CAH-TIP-1-05 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | Unknown | Unknown | 6 | Planned | December | December
TO-27-ARK-SHE-2-01 | 110kV FEEDER - ARKLOW 110-SHELTON ABBEY 110-2 | Unknown | Unknown | 8 | Planned | December | January

## GEN_NorthWest
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-27-CSH-PRO-1-01 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | 53 | 38 | 38 | Proposed | 04/01/2027 | 25/02/2027
TO-27-CSH-220K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 220-CASHLA 220-220K1-2 | 12 | 10 | 10 | Proposed | 18/01/2027 | 29/01/2027
TO-27-CF-CLO-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-1 | 5 | 3 | 3 | Proposed | 22/01/2027 | 26/01/2027
TO-27-BK-CBR-1-01 | 110kV FEEDER - BELLACORICK 110-CASTLEBAR 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-FLA-110K1-2-01 | COUPLER/SECTIONALISING CB - FLAGFORD 110-FLAGFORD 110-110K1-2 | Unknown | Unknown | 1 | Planned | February | February
TO-27-CSH-PRO-1-02 | 220kV FEEDER - CASHLA 220-PROSPECT 220-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-CUN-GLR-1-01 | 110kV FEEDER - CUNGHILL 110-GLENREE 110-1 | Unknown | Unknown | 8 | Planned | February | February
TO-27-COS-FLA-1-01 | 110kV FEEDER - CARRICK ON SHANNON 110-FLAGFORD 110-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-CSH-T2102-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2102 | Unknown | Unknown | 17 | Planned | February | March
TO-27-CF-CLO-2-01 | 110kV FEEDER - CATHALEENS FALL 110-CLOGHER 110-2 | Unknown | Unknown | 3 | Planned | March | March
TO-27-CUN-SLI-1-01 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-CUN-SLI-1-02 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-FLA-SLI-1-02 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-FLA-T2102-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2102 | Unknown | Unknown | 9 | Planned | March | March
TO-27-SLI-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | March | March
TO-27-SLI-SRA-2-01 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 9 | Planned | March | March
TO-27-SLI-SRA-2-03 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 40 | Planned | March | May
TO-27-SLI-SRA-2-04 | 110kV FEEDER - SLIGO 110-SRANANAGH 110-2 | Unknown | Unknown | 60 | Planned | March | June
TO-27-SLI-T142-01 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | March | March
TO-27-GAL GIS-SAL-1-01 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | Unknown | Unknown | 12 | Planned | March | April
TO-27-GAL GIS-SAL-1-02 | 110kV FEEDER - GALWAY GIS 110-SALTHILL 110-1 | Unknown | Unknown | 40 | Planned | March | May
TO-27-LLA-TIV-1-01 | 110kV FEEDER - LENALEA 110-TIEVEBRACK 110-1 | Unknown | Unknown | 9 | Planned | March | April
TO-27-CF-T103-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G3-T103 | Unknown | Unknown | 3 | Planned | April | April
TO-27-CUN-SLI-1-03 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 14 | Planned | April | April
TO-27-FLA-SLI-1-01 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 14 | Planned | April | April
TO-27-FLA-SLI-1-03 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 14 | Planned | April | April
TO-27-SLI-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 14 | Planned | April | April
TO-27-SLI-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 14 | Planned | April | April
TO-27-SLI-T142-02 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 14 | Reference (Planned) | April | April
TO-27-CF-T104-01 | GENERATOR TRANSFORMER - CATHALEENS FALL 110-CATHALEENS FALL G4-T104 | Unknown | Unknown | 5 | Planned | April | April
TO-27-GAL GIS-T101-01 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 10-T101 | Unknown | Unknown | 5 | Planned | May | May
TO-27-CUN-T121-01 | GENERATOR TRANSFORMER - CUNGHILL 110-CUNGHILL 20-T121 | Unknown | Unknown | 3 | Planned | May | May
TO-27-KLH-KNY-1-01 | 110kV FEEDER - KNOCKALOUGH 110-KNOCKRANNY 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-KLH-T121-01 | GENERATOR TRANSFORMER - KNOCKALOUGH 110-KNOCKALOUGH 20-T121 | Unknown | Unknown | 5 | Planned | May | May
TO-27-CLO-CRD-1-01 | 110kV FEEDER - CLOGHER 110-CROAGHONAGH 110-1 | Unknown | Unknown | 4 | Planned | May | May
TO-27-CRD-T131-01 | GENERATOR TRANSFORMER - CROAGHONAGH 110-CROAGHONAGH 33-T131 | Unknown | Unknown | 4 | Planned | May | May
TO-27-GAL GIS-T103-01 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 10-T103 | Unknown | Unknown | 2 | Planned | May | May
TO-27-BK-SKY-1-01 | 110kV FEEDER - BELLACORICK 110-SRAHNAKILLY 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-SKY-T131-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | Unknown | Unknown | 3 | Planned | May | May
TO-27-SKY-T131-02 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T131 | Unknown | Unknown | 5 | Planned | May | May
TO-27-SKY-T132-01 | GENERATOR TRANSFORMER - SRAHNAKILLY 110-SRAHNAKILLY 33-T132 | Unknown | Unknown | 5 | Planned | May | May
TO-27-GAL GIS-T142-01 | DISTRIBUTION TRANSFORMER - GALWAY GIS 110-GALWAY 38-T142 | Unknown | Unknown | 3 | Planned | May | May
TO-27-KNY-UGL-1-01 | 110kV FEEDER - KNOCKRANNY 110-UGGOOL 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-CSH-SAL-1-01 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | Unknown | Unknown | 10 | Planned | May | June
TO-27-CSH-SAL-1-04 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | Unknown | Unknown | 40 | Planned | May | July
TO-27-CSH-SAL-1-03 | 110kV FEEDER - CASHLA 110-SALTHILL 110-1 | Unknown | Unknown | 55 | Planned | May | August
TO-27-CSH-110K1-2-01 | COUPLER/SECTIONALISING CB - CASHLA 110-CASHLA 110-110K1-2 | Unknown | Unknown | 5 | Planned | May | June
TO-27-CUN-SLI-1-04 | 110kV FEEDER - CUNGHILL 110-SLIGO 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-FLA-SLI-1-04 | 110kV FEEDER - FLAGFORD 110-SLIGO 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-SLI-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - SLIGO 110-SLIGO 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | June | June
TO-27-SLI-T142-03 | DISTRIBUTION TRANSFORMER - SLIGO 110-SLIGO 38-T142 | Unknown | Unknown | 2 | Reference (Planned) | June | June
TO-27-UGL-T131-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T131 | Unknown | Unknown | 3 | Planned | June | June
TO-27-BIN-CF-1-01 | 110kV FEEDER - BINBANE 110-CATHALEENS FALL 110-1 | Unknown | Unknown | 14 | Planned | June | June
TO-27-CLO-MRY-1-01 | 110kV FEEDER - CLOGHER 110-MULREAVY 110-1 | Unknown | Unknown | 7 | Planned | June | June
TO-27-MRY-T131-01 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | Unknown | Unknown | 7 | Planned | June | June
TO-27-UGL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - UGGOOL 110-UGGOOL 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | June | June
TO-27-UGL-T132-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T132 | Unknown | Unknown | 1 | Planned | June | June
TO-27-UGL-T134-01 | GENERATOR TRANSFORMER - UGGOOL 110-UGGOOL 33-T134 | Unknown | Unknown | 1 | Planned | June | June
TO-27-CSH-CAP1-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-DYN-T121-01 | GENERATOR TRANSFORMER - DERRYBRIEN 110-DERRYBRIEN 20-T121 | Unknown | Unknown | 5 | Reference (Planned) | June | June
TO-27-FLA-T2101-01 | TRANSFORMER - FLAGFORD 220-FLAGFORD 110-T2101 | Unknown | Unknown | 5 | Planned | June | June
TO-27-MOY-TAW-2-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-2 | Unknown | Unknown | 8 | Planned | June | June
TO-27-MRY-T131-02 | GENERATOR TRANSFORMER - MULREAVY 110-MULREAVY 33-T131 | Unknown | Unknown | 2 | Planned | June | June
TO-27-SLI-CAP1-01 | CAPACITOR/SVC/REACTOR - SLIGO 110-SLIGO 110-CAP1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-TAW-T3-01 | GENERATOR TRANSFORMER - TAWNAGHMORE 110-TAWNAGHMORE 10-T3 | Unknown | Unknown | 3 | Planned | June | June
TO-27-CSH-CAP2-01 | CAPACITOR/SVC/REACTOR - CASHLA 110-CASHLA 110-CAP2 | Unknown | Unknown | 5 | Planned | June | June
TO-27-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-CSH-GAL GIS-1-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-MOY-TAW-1-01 | 110kV FEEDER - MOY 110-TAWNAGHMORE 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | Unknown | Unknown | 59 | Planned | June | September
TO-27-CBG-CBR-1-01 | 110kV FEEDER - CARROWBEG 110-CASTLEBAR 110-1 | Unknown | Unknown | 8 | Reference (Planned) | June | July
TO-27-CBG-T142-01 | DISTRIBUTION TRANSFORMER - CARROWBEG 110-CARROWBEG 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | June | July
TO-27-CBR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAR 110-CASTLEBAR 110-110SA1-2CB | Unknown | Unknown | 8 | Planned | June | July
TO-27-CBR-CAP2-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-CAP2 | Unknown | Unknown | 8 | Planned | June | July
TO-27-CBR-DLT-1-01 | 110kV FEEDER - CASTLEBAR 110-DALTON 110-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-CBR-T142-01 | DISTRIBUTION TRANSFORMER - CASTLEBAR 110-CASTLEBAR 38-T142 | Unknown | Unknown | 8 | Reference (Planned) | June | July
TO-27-BIN-TIV-1-01 | 110kV FEEDER - BINBANE 110-TIEVEBRACK 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-CF-110K1-2-01 | COUPLER/SECTIONALISING CB - CATHALEENS FALL 110-CATHALEENS FALL 110-110K1-2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-GRV-T121-02 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | Unknown | Unknown | 5 | Planned | July | July
TO-27-CSH-T2101-01 | TRANSFORMER - CASHLA 220-CASHLA 110-T2101 | Unknown | Unknown | 3 | Planned | July | July
TO-27-DLT-110SA1-01 | SECTIONALISING DISCONNECT - DALTON 110-DALTON 110-110SA1 | Unknown | Unknown | 7 | Planned | July | July
TO-27-DLT-CAP1-01 | CAPACITOR/SVC/REACTOR - DALTON 110-DALTON 110-CAP1 | Unknown | Unknown | 7 | Planned | July | July
TO-27-CF-CAP2-01 | CAPACITOR/SVC/REACTOR - CATHALEENS FALL 110-CATHALEENS FALL 110-CAP2 | Unknown | Unknown | 5 | Planned | July | July
TO-27-DRM-LET-1-01 | 110kV FEEDER - DRUMKEEN 110-LETTERKENNY 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-27-110 kV A1 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110A1 | Unknown | Unknown | 40 | Planned | July | September
TO-27-110 kV B1 @ CSH-01 | BUSBAR SECTION - CASHLA 110-CASHLA 110-110B1 | Unknown | Unknown | 40 | Planned | July | September
TO-27-CSH-CLN-1-02 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-CSH-CLN-1-03 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | Unknown | 40 | Planned | July | September
TO-27-CSH-CLN-1-01 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | Unknown | 40 | Planned | July | September
TO-27-SKY-110SA1-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA1 | Unknown | Unknown | 1 | Planned | July | July
TO-27-SKY-110SA2-01 | SECTIONALISING DISCONNECT - SRAHNAKILLY 110-SRAHNAKILLY 110-110SA2 | Unknown | Unknown | 1 | Planned | July | July
TO-27-GOL-T101-01 | GENERATOR TRANSFORMER - GOLAGH 110-GOLAGH 10-T101 | Unknown | Unknown | 14 | Planned | July | August
TO-27-GOL,T-CLO-1-02 | 110kV FEEDER - GOLAGH tee-CLOGHER 110-1 | Unknown | Unknown | 14 | Planned | July | August
TO-27-GOL,T-GOL-1-01 | 110kV FEEDER - GOLAGH tee-GOLAGH 110-1 | Unknown | Unknown | 14 | Planned | July | August
TO-27-GOL,T-LET-1-02 | 110kV FEEDER - GOLAGH tee-LETTERKENNY 110-1 | Unknown | Unknown | 14 | Planned | July | August
TO-27-MOY-CAP1-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-CDY-GRV-1-01 | 110kV FEEDER - CORDERRY 110-GARVAGH 110-1 | 4 | 4 | 4 | Proposed | 03/08/2027 | 06/08/2027
TO-27-GRV-110K1-01 | COUPLER/SECTIONALISING CB - GARVAGH 110-GARVAGH 110-110K1 | 4 | 4 | 4 | Proposed | 03/08/2027 | 06/08/2027
TO-27-GRV-T121-01 | GENERATOR TRANSFORMER - GARVAGH 110-GARVAGH 20-T121 | 4 | 4 | 4 | Proposed | 03/08/2027 | 06/08/2027
TO-27-GRV-T141-01 | DISTRIBUTION TRANSFORMER - GARVAGH 110-GARVAGH 20-T141 | 4 | 4 | 4 | Reference (Proposed) | 03/08/2027 | 06/08/2027
TO-27-MOY-CAP2-01 | CAPACITOR/SVC/REACTOR - MOY 110-MOY 110-CAP2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-GLR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GLENREE 110-GLENREE 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | August | August
TO-27-GLR-MOY-1-01 | 110kV FEEDER - GLENREE 110-MOY 110-1 | Unknown | Unknown | 10 | Planned | August | August
TO-27-GLR-T121-01 | DISTRIBUTION TRANSFORMER - GLENREE 110-GLENREE 38-T121 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-27-CSH-GAL GIS-2-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-2 | Unknown | Unknown | 1 | Planned | August | August
TO-27-CSH-GAL GIS-4-01 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-4 | Unknown | Unknown | 5 | Planned | August | August
TO-27-CF-CL-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CLIFF 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-CL-T101-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G1-T101 | Unknown | Unknown | 5 | Planned | September | September
TO-27-CL-T102-01 | GENERATOR TRANSFORMER - CLIFF 110-CLIFF G2-T102 | Unknown | Unknown | 5 | Planned | September | September
TO-27-LET-CAP2-01 | CAPACITOR/SVC/REACTOR - LETTERKENNY 110-LETTERKENNY 110-CAP2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-GAL GIS-KNY-1-01 | 110kV FEEDER - GALWAY GIS 110-KNOCKRANNY 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-27-CSH-GAL GIS-1-02 | 110kV FEEDER - CASHLA 110-GALWAY GIS 110-1 | Unknown | Unknown | 1 | Planned | September | September
TO-27-FLA-GIL-1-01 | 110kV FEEDER - FLAGFORD 110-GILRA 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-GIL-T121-01 | TSO CUSTOMER TRANSFORMER - GILRA 110-GILRA 20-T121 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-27-BK-110SA1-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-110SA1-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA1 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-110SA2-01 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-110SA2-02 | SECTIONALISING DISCONNECT - BELLACORICK 110-BELLACORICK 110-110SA2 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-MOY-1-01 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-MOY-1-02 | 110kV FEEDER - BELLACORICK 110-MOY 110-1 | Unknown | Unknown | 7 | Planned | October | October
TO-27-BK-T141-01 | DISTRIBUTION TRANSFORMER - BELLACORICK 110-BELLACORICK 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | October | October
TO-27-CSH-ENN-1-01 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CSH-ENN-1-02 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-CSH-ENN-1-03 | 110kV FEEDER - CASHLA 110-ENNIS 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-CSH-DLT-1-02 | 110kV FEEDER - CASHLA 110-DALTON 110-1 | Unknown | Unknown | 14 | Planned | October | November
TO-27-CLO-DRM-1-01 | 110kV FEEDER - CLOGHER 110-DRUMKEEN 110-1 | Unknown | Unknown | 15 | Planned | November | November
TO-27-CDY-SRA-1-01 | 110kV FEEDER - CORDERRY 110-SRANANAGH 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-CBR-CLN-1-01 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 15 | Planned | November | December
TO-27-CBR-CLN-1-02 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-CSH-CLN-1-04 | 110kV FEEDER - CASHLA 110-CLOON 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-CBR-CLN-1-03 | 110kV FEEDER - CASTLEBAR 110-CLOON 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | Unknown | Unknown | 15 | Planned | November | December
TO-27-CLN-110SA1-02 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-CLN-110SA2-01 | SECTIONALISING DISCONNECT - CLOON 110-CLOON 110-110SA2 | Unknown | Unknown | 7 | Planned | November | November
TO-27-CLN-T141-01 | DISTRIBUTION TRANSFORMER - CLOON 110-CLOON 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | November | November
TO-27-FLA-LOU-1-04 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | Unknown | Unknown | 2 | Planned | December | December

## GEN_NorthEast
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-27-AGL-SH-1-02 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 26 | 20 | 20 | Proposed | 04/01/2027 | 29/01/2027
TO-27-110 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 142 | Planned | January | July
TO-27-110 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown | 142 | Planned | January | July
TO-27-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | Unknown | Unknown | 145 | Planned | January | August
TO-27-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | Unknown | Unknown | 145 | Planned | January | August
TO-27-LOU-T2102-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | 18 | 14 | 14 | Proposed | 05/01/2027 | 22/01/2027
TO-27-LOU-T2102-02 | TRANSFORMER - LOUTH 220-LOUTH 110-T2102 | Unknown | Unknown |  | Planned | January | August
TO-27-GOR-NAV-2-01 | 110kV FEEDER - GORMAN 110-NAVAN 110-2 | 5 | 5 | 5 | Proposed | 11/01/2027 | 15/01/2027
TO-27-RRU-SKL-1-01 | 110kV FEEDER - RATRUSSAN 110-SHANKILL 110-1 | 12 | 10 | 10 | Proposed | 18/01/2027 | 29/01/2027
TO-27-OBE-110K1-01 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K1 | 1 | 1 | 1 | Proposed | 19/01/2027 | 19/01/2027
TO-27-GAR-PLA-1-01 | 110kV FEEDER - GARBALLAGH 110-PLATIN 110-1 | 2 | 2 | 2 | Proposed | 26/01/2027 | 27/01/2027
TO-27-AGL-ENN-1-02 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-AGL-SH-1-03 | 110kV FEEDER - AGANNYGAL 110-SHANNONBRIDGE 110-1 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-CDA-SH-2-01 | 110kV FEEDER - CLONDELARA 110-SHANNONBRIDGE 110-2 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-CDA-T102/4-01 | GENERATOR TRANSFORMER - CLONDELARA 110-CLONDELARA G2/4-T102/4 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-110 kV A2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110A2 | 1 | 0 | 0 | Proposed | 31/01/2027 | 31/01/2027
TO-27-ARV-SKL-1-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-GAR-GOR-1-01 | 110kV FEEDER - GARBALLAGH 110-GORMAN 110-1 | Unknown | Unknown | 9 | Planned | February | February
TO-27-KLN-SH-1-01 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 99 | Planned | February | June
TO-27-KLN-SH-1-03 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 99 | Planned | February | June
TO-27-220 kV A2 @ LOU-04 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | Unknown | Unknown | 95 | Planned | February | June
TO-27-220 kV B2 @ LOU-03 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | Unknown | Unknown | 95 | Planned | February | June
TO-27-MUL-RTN-01 | 110kV FEEDER - MULLINGAR 110-RATTIN 110-1 | Unknown | Unknown | 9 | Planned | February | February
TO-27-110 kV B2 @ SH-01 | BUSBAR SECTION - SHANNONBRIDGE 110-SHANNONBRIDGE 110-110B2 | Unknown | Unknown | 0 | Planned | February | February
TO-27-ARV-SKL-2-01 | 110kV FEEDER - ARVA 110-SHANKILL 110-2 | Unknown | Unknown | 10 | Planned | February | February
TO-27-DER-T132-01 | GENERATOR TRANSFORMER - DERRYIRON 110-DERRYIRON 33-T132 | 2 | 2 | 2 | Proposed | 08/02/2027 | 09/02/2027
TO-27-DEY-T132-01 | GENERATOR TRANSFORMER - DERRYCARNEY 110-DERRYCARNEY 33-T132 | 5 | 5 | 5 | Proposed | 15/02/2027 | 19/02/2027
TO-27-LOU-MLN-1-01 | 110kV FEEDER - LOUTH 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 2 | Planned | February | February
TO-27-GOR-MTH-1-01 | 110kV FEEDER - GORMAN 110-MEATH HILL 110-1 | Unknown | Unknown | 9 | Planned | February | March
TO-27-KIN-RTN-01 | 110kV FEEDER - KINNEGAD 110-RATTIN 110-1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-LIS-110SA1-07 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-110SA1-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-110SA2-01 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-110SA2-07 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-CAP2-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-CAP2-04 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-LSA-1-01 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-LIS-LSA-1-03 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-LSA-1-06 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 24 | Planned | February | March
TO-27-LIS-T142-04 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | Unknown | Unknown | 24 | Reference (Planned) | February | March
TO-27-LIS-T142-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | Unknown | Unknown | 24 | Reference (Planned) | February | March
TO-27-GAR-110K1-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110K1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-GAR-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | February | February
TO-27-GAR-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - GARBALLAGH 110-GARBALLAGH 110-110SB1-2CB | Unknown | Unknown | 3 | Planned | February | February
TO-27-DER-KIN-1-01 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-DER-KIN-1-03 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-DDK-LOU-1-01 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-KIN-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | March | March
TO-27-KIN-RTN-02 | 110kV FEEDER - KINNEGAD 110-RATTIN 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-KIN-T101-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | Unknown | 5 | Planned | March | March
TO-27-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 20 | Planned | March | March
TO-27-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 20 | Planned | March | March
TO-27-SH-220K1-2-01 | COUPLER/SECTIONALISING CB - SHANNONBRIDGE 220-SHANNONBRIDGE 220-220K1-2 | Unknown | Unknown | 14 | Planned | March | March
TO-27-LOU-220K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-DFR,T-KIN-1-03 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-KIN-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | March | March
TO-27-KIN-T102-01 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | Unknown | 1 | Planned | March | March
TO-27-KIN-T102-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | Unknown | 5 | Planned | March | March
TO-27-MLC-TSB-1-01 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | Unknown | Unknown | 9 | Planned | March | March
TO-27-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-DDK-MLN-1-01 | 110kV FEEDER - DUNDALK 110-MULLAGHARLIN 110-1 | Unknown | Unknown | 3 | Planned | March | March
TO-27-BAL-DEN-1-01 | 110kV FEEDER - BALTRASNA 110-DEENES 110-1 | Unknown | Unknown | 10 | Planned | March | March
TO-27-TEN-T132-01 | GENERATOR TRANSFORMER - TIMAHOE 110-TIMAHOE 33-T132 | Unknown | Unknown | 1 | Planned | March | March
TO-27-MLC-TSB-1-02 | 110kV FEEDER - MOUNTLUCAS 110-THORNSBERRY 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-TSB-110SA1-02 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-TSB-110SA1-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA1 | Unknown | Unknown | 1 | Planned | March | March
TO-27-TSB-110SA2-01 | SECTIONALISING DISCONNECT - THORNSBERRY 110-THORNSBERRY 110-110SA2 | Unknown | Unknown | 5 | Planned | March | March
TO-27-TSB-T141-01 | DISTRIBUTION TRANSFORMER - THORNSBERRY 110-THORNSBERRY 38-T141 | Unknown | Unknown | 5 | Reference (Planned) | March | March
TO-27-LIS-T131-01 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | Unknown | Unknown | 29 | Planned | March | April
TO-27-GOR-MAY-1-02 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 7 | Planned | March | March
TO-27-GOR-MAY-1-03 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 7 | Planned | March | March
TO-27-SH-T2101-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2101 | Unknown | Unknown | 5 | Planned | March | March
TO-27-LIS-110SA1-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 59 | Planned | March | June
TO-27-LIS-110SA2-02 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 59 | Planned | March | June
TO-27-LIS-110SA1-03 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-110SA2-03 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-CAP1-01 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | Unknown | Unknown | 3 | Planned | March | April
TO-27-LIS-CAP1-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-LOU-1-01 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-LOU-1-02 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-LIS-T141-01 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | March | April
TO-27-SH-T2102-01 | TRANSFORMER - SHANNONBRIDGE 220-SHANNONBRIDGE 110-T2102 | Unknown | Unknown | 2 | Planned | March | April
TO-27-DAL,T-DAL-1-01 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-DAL-1-03 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-DAL,T-SH-1-01 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-DAL,T-SH-1-03 | 110kV FEEDER - DALLOW tee-SHANNONBRIDGE 110-1 | Unknown | Unknown | 24 | Planned | April | May
TO-27-DER-KIN-1-04 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DFR-T122-01 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | Unknown | Unknown | 2 | Reference (Planned) | April | April
TO-27-DFR-T122-02 | DISTRIBUTION TRANSFORMER - DUNFIRTH 110-DUNFIRTH 20-T122 | Unknown | Unknown | 60 | Reference (Planned) | April | July
TO-27-DFR,T-DFR-1-01 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DFR,T-DFR-1-02 | 110kV FEEDER - DUNFIRTH tee-DUNFIRTH 110-1 | Unknown | Unknown | 60 | Planned | April | July
TO-27-DFR,T-KIN-1-01 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 20 | Planned | April | May
TO-27-DFR,T-KIN-1-04 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DFR,T-KIN-1-06 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 60 | Planned | April | July
TO-27-DFR,T-RNW-1-05 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 60 | Planned | April | July
TO-27-DFR,T-RNW-1-04 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 6 | Planned | April | April
TO-27-DFR,T-RNW-1-07 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-GLN-PLA-1-01 | 110kV FEEDER - GALLANSTOWN 110-PLATIN 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 50 | Planned | April | June
TO-27-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 50 | Planned | April | June
TO-27-RRU-T122-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T122 | Unknown | Unknown | 4 | Planned | April | April
TO-27-KLN-SH-1-05 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 52 | Planned | April | June
TO-27-KUR-NAV-1-01 | 110kV FEEDER - KNOCKUMBER 110-NAVAN 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-KUR-T3-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T3 | Unknown | Unknown | 3 | Reference (Planned) | April | April
TO-27-KUR-T4-01 | TSO CUSTOMER TRANSFORMER - KNOCKUMBER 110-KNOCKUMBER 10-T4 | Unknown | Unknown | 3 | Reference (Planned) | April | April
TO-27-110 kV A2 @ OBE-01 | BUSBAR SECTION - OLDBRIDGE 110-OLDBRIDGE 110-110A2 | Unknown | Unknown | 20 | Planned | April | May
TO-27-110 kV B2 @ OBE-01 | BUSBAR SECTION - OLDBRIDGE 110-OLDBRIDGE 110-110B2 | Unknown | Unknown | 20 | Planned | April | May
TO-27-OBE-110K2-02 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110K2 | Unknown | Unknown | 20 | Planned | April | May
TO-27-OBE-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SA1-2CB | Unknown | Unknown | 20 | Planned | April | May
TO-27-OBE-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - OLDBRIDGE 110-OLDBRIDGE 110-110SB1-2CB | Unknown | Unknown | 20 | Planned | April | May
TO-27-ATH-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | April | April
TO-27-ATH-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | April | April
TO-27-ATH-SH-1-01 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | April | April
TO-27-ATH-SH-1-02 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-ATH-T142-01 | DISTRIBUTION TRANSFORMER - ATHLONE 110-ATHLONE 38-T142 | Unknown | Unknown | 51 | Reference (Planned) | April | July
TO-27-DRY-OBE-1-02 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-LIS-110SA1-04 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 14 | Planned | April | May
TO-27-LIS-110SA2-04 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 14 | Planned | April | May
TO-27-LIS-CAP2-02 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | Unknown | Unknown | 14 | Planned | April | May
TO-27-LIS-LSA-1-04 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 14 | Planned | April | May
TO-27-LIS-T142-02 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | Unknown | Unknown | 14 | Reference (Planned) | April | May
TO-27-DAL,T-DAL-1-04 | 110kV FEEDER - DALLOW tee-DALLOW 110-1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-MUL-CAP1-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-RRU-T121-01 | GENERATOR TRANSFORMER - RATRUSSAN 110-RATRUSSAN 20-T121 | Unknown | Unknown | 5 | Planned | May | May
TO-27-SLB-T132-01 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 8 | Planned | May | May
TO-27-MLC-T121-01 | GENERATOR TRANSFORMER - MOUNTLUCAS 110-MOUNTLUCAS 20-T121 | Unknown | Unknown | 2 | Planned | May | May
TO-27-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | Unknown | Unknown | 40 | Planned | May | July
TO-27-SLB-T132-02 | GENERATOR TRANSFORMER - SLIABH BAWN 110-SLIABH BAWN 33-T132 | Unknown | Unknown | 2 | Planned | May | May
TO-27-DRY-OBE-1-03 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | Unknown | Unknown |  | Planned | May | May
TO-27-LSA-T131-01 | GENERATOR TRANSFORMER - LISLEA 110-LISLEA 33-T131 | Unknown | Unknown | 2 | Planned | May | May
TO-27-LOU-CAP1-01 | CAPACITOR/SVC/REACTOR - LOUTH 110-LOUTH 110-CAP1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MLN-T124-01 | TSO CUSTOMER TRANSFORMER - MULLAGHARLIN 110-MULLAGHARLIN 20-T124 | Unknown | Unknown | 5 | Planned | May | May
TO-27-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | Unknown | Unknown | 3 | Planned | May | May
TO-27-LIS-110SA1-05 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-110SA2-05 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-CAP1-03 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-LOU-1-03 | 110kV FEEDER - LISDRUM 110-LOUTH 110-1 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-T131-02 | GENERATOR TRANSFORMER - LISDRUM 110-LISDRUM 33-T131 | Unknown | Unknown | 20 | Planned | May | June
TO-27-LIS-T141-02 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T141 | Unknown | Unknown | 20 | Reference (Planned) | May | June
TO-27-PLA-T105-01 | TSO CUSTOMER TRANSFORMER - PLATIN 110-PLATIN 10-T105 | Unknown | Unknown | 5 | Planned | May | May
TO-27-LOU-AT1-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT1 | Unknown | Unknown | 3 | Planned | May | May
TO-27-LOU-AT2-01 | TRANSFORMER - LOUTH 220-LOUTH 275-AT2 | Unknown | Unknown | 5 | Planned | May | June
TO-27-COR-PST-01 | TRANSFORMER - CORRACLASSY 110-ENNISKILLEN 110-PST | Unknown | Unknown | 10 | Planned | June | June
TO-27-LIS-110SA1-06 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA1 | Unknown | Unknown | 4 | Planned | June | June
TO-27-LIS-110SA2-06 | SECTIONALISING DISCONNECT - LISDRUM 110-LISDRUM 110-110SA2 | Unknown | Unknown | 4 | Planned | June | June
TO-27-LIS-CAP2-03 | CAPACITOR/SVC/REACTOR - LISDRUM 110-LISDRUM 110-CAP2 | Unknown | Unknown | 4 | Planned | June | June
TO-27-LIS-LSA-1-05 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-27-LIS-T142-03 | DISTRIBUTION TRANSFORMER - LISDRUM 110-LISDRUM 38-T142 | Unknown | Unknown | 4 | Reference (Planned) | June | June
TO-27-CSH-TY-1-01 | 220kV FEEDER - CASHLA 220-TYNAGH 220-1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-DRY-GOR-1-03 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 45 | Planned | June | August
TO-27-DRY-GOR-1-01 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-DRY-T142-01 | DISTRIBUTION TRANSFORMER - DRYBRIDGE 110-DRYBRIDGE 38-T142 | Unknown | Unknown | 105 | Reference (Planned) | June | November
TO-27-LOU-110K1-2-01 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown | 10 | Planned | June | July
TO-27-ARV-COS-1-01 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-ARV-COS-1-03 | 110kV FEEDER - ARVA 110-CARRICK ON SHANNON 110-1 | Unknown | Unknown | 59 | Planned | June | September
TO-27-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-GOR-MAY-1-04 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-ATH-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - ATHLONE 110-ATHLONE 110-110SA1-2CB | Unknown | Unknown | 3 | Planned | July | July
TO-27-ATH-SH-1-03 | 110kV FEEDER - ATHLONE 110-SHANNONBRIDGE 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-GWE-T142-02 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | July | July
TO-27-LA-MUL-1-01 | 110kV FEEDER - LANESBORO 110-MULLINGAR 110-1 | Unknown | Unknown | 12 | Planned | July | July
TO-27-CFN-SH-1-01 | 220kV FEEDER - CLONIFFEEN 220-SHANNONBRIDGE 220-1 | 1 | 1 | 1 | Proposed | 06/07/2027 | 06/07/2027
TO-27-OST-TY-1-01 | 220kV FEEDER - OLDSTREET 220-TYNAGH 220-1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-TY-T2001/2-01 | GENERATOR TRANSFORMER - TYNAGH 220-TYNAGH G1/2-T2001/2 | Unknown | Unknown | 4 | Planned | July | July
TO-27-220 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-220 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-LOU-220K1-2-03 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown |  | Planned | July | July
TO-27-DER-TEN-1-01 | 110kV FEEDER - DERRYIRON 110-TIMAHOE 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-DER-TEN-1-02 | 110kV FEEDER - DERRYIRON 110-TIMAHOE 110-1 | Unknown | Unknown | 60 | Planned | July | October
TO-27-110 kV A1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-110 kV B1 @ LOU-01 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-LOU-110K1-2-02 | COUPLER/SECTIONALISING CB - LOUTH 110-LOUTH 110-110K1-2 | Unknown | Unknown |  | Planned | July | July
TO-27-DDK-LOU-1-02 | 110kV FEEDER - DUNDALK 110-LOUTH 110-1 | Unknown | Unknown | 1 | Planned | July | July
TO-27-110 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110B2 | Unknown | Unknown | 1 | Planned | July | July
TO-27-GOR-LOU-1-02 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 2 | Planned | August | August
TO-27-110 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 110-LOUTH 110-110A2 | Unknown | Unknown | 2 | Planned | August | August
TO-27-ATH-M/CAP1-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | Unknown | Unknown | 6 | Planned | August | August
TO-27-GOR-LOU-1-03 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 20 | Planned | August | September
TO-27-LOU-AT3-02 | TRANSFORMER - LOUTH 220-LOUTH 275-AT3 | Unknown | Unknown | 5 | Planned | August | August
TO-27-ATH-CAP3-01 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-CAP3 | Unknown | Unknown | 10 | Planned | September | September
TO-27-DEN-DRY-1-01 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-LOU-T2101-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2101 | Unknown | Unknown | 10 | Planned | September | September
TO-27-LSA-SKL-1-01 | 110kV FEEDER - LISLEA 110-SHANKILL 110-1 | Unknown | Unknown | 6 | Planned | September | September
TO-27-ATH-LA-1-01 | 110kV FEEDER - ATHLONE 110-LANESBORO 110-1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-COR-GWE-1-02 | 110kV FEEDER - CORRACLASSY 110-GORTAWEE 110-1 | Unknown | Unknown | 15 | Planned | September | October
TO-27-LOU-T2103-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2103 | Unknown | Unknown | 5 | Planned | September | September
TO-27-GOR-LOU-1-01 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 50 | Planned | September | November
TO-27-GOR-LOU-1-04 | 220kV FEEDER - GORMAN 220-LOUTH 220-1 | Unknown | Unknown | 60 | Planned | September | December
TO-27-220 kV A2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | Unknown | Unknown | 60 | Planned | September | December
TO-27-220 kV B2 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | Unknown | Unknown | 60 | Planned | September | December
TO-27-KLN-SH-1-04 | 220kV FEEDER - KILLONAN 220-SHANNONBRIDGE 220-1 | Unknown | Unknown | 57 | Planned | September | December
TO-27-LA-SLB-1-01 | 110kV FEEDER - LANESBORO 110-SLIABH BAWN 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-27-LOU-T2104-01 | TRANSFORMER - LOUTH 220-LOUTH 110-T2104 | Unknown | Unknown | 5 | Planned | September | October
TO-27-FLA-SLB-1-01 | 110kV FEEDER - FLAGFORD 110-SLIABH BAWN 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-DER-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DERRYIRON 110-DERRYIRON 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | October | October
TO-27-DER-KIN-1-02 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-DER-KDN-1-01 | 110kV FEEDER - DERRYIRON 110-KNOCKDRIN 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-KDN-T131-01 | GENERATOR TRANSFORMER - KNOCKDRIN 110-KNOCKDRIN 33-T131 | Unknown | Unknown | 10 | Planned | October | October
TO-27-ARV-GWE-1-02 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-ARV-GWE-1-03 | 110kV FEEDER - ARVA 110-GORTAWEE 110-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-GWE-110SA1-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-GWE-110SA2-01 | SECTIONALISING DISCONNECT - GORTAWEE 110-GORTAWEE 110-110SA2 | Unknown | Unknown | 10 | Planned | October | October
TO-27-GWE-T102-02 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | Unknown | Unknown | 10 | Planned | October | October
TO-27-GWE-T142-01 | DISTRIBUTION TRANSFORMER - GORTAWEE 110-GORTAWEE 38-T142 | Unknown | Unknown | 10 | Reference (Planned) | October | October
TO-27-AGL-ENN-1-01 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | Unknown | Unknown | 20 | Planned | October | November
TO-27-AGL-ENN-1-03 | 110kV FEEDER - AGANNYGAL 110-ENNIS 110-1 | Unknown | Unknown | 42 | Planned | October | December
TO-27-CLN-LA-1-01 | 110kV FEEDER - CLOON 110-LANESBORO 110-1 | Unknown | Unknown | 2 | Planned | October | October
TO-27-MP GIS-OST-1-01 | 400kV FEEDER - MONEYPOINT GIS 400-OLDSTREET 400-1 | Unknown | Unknown | 9 | Planned | October | November
TO-27-GOR-NAV-3-02 | 110kV FEEDER - GORMAN 110-NAVAN 110-3 | Unknown | Unknown | 10 | Planned | November | November
TO-27-MAY-TEN-1-01 | 110kV FEEDER - MAYNOOTH 110-TIMAHOE 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-220 kV A1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A1 | Unknown | Unknown | 3 | Planned | November | November
TO-27-220 kV B1 @ LOU-02 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B1 | Unknown | Unknown | 3 | Planned | November | November
TO-27-LOU-220K1-2-04 | COUPLER/SECTIONALISING CB - LOUTH 220-LOUTH 220-220K1-2 | Unknown | Unknown | 3 | Planned | November | November
TO-27-CUS-MLC-1-01 | 110kV FEEDER - CUSHALING 110-MOUNTLUCAS 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-DEN-DRY-1-02 | 110kV FEEDER - DEENES 110-DRYBRIDGE 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-DRY-110SA1-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-DRY-110SA2-01 | SECTIONALISING DISCONNECT - DRYBRIDGE 110-DRYBRIDGE 110-110SA2 | Unknown | Unknown | 2 | Planned | November | November
TO-27-DRY-GOR-1-04 | 110kV FEEDER - DRYBRIDGE 110-GORMAN 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-CF-COR-1-01 | 110kV FEEDER - CATHALEENS FALL 110-CORRACLASSY 110-1 | Unknown | Unknown | 15 | Planned | November | December
TO-27-DER-KIN-1-05 | 110kV FEEDER - DERRYIRON 110-KINNEGAD 110-1 | Unknown | Unknown | 10 | Planned | November | December
TO-27-KIN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | November | December
TO-27-KIN-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | November | December
TO-27-KIN-RTN-03 | 110kV FEEDER - KINNEGAD 110-RATTIN 110-1 | Unknown | Unknown | 10 | Planned | November | December
TO-27-KIN-T101-02 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T101 | Unknown | Unknown | 10 | Planned | November | December
TO-27-LOU-RRU-1-01 | 110kV FEEDER - LOUTH 110-RATRUSSAN 110-1 | Unknown | Unknown | 2 | Planned | November | November
TO-27-DFR,T-KIN-1-05 | 110kV FEEDER - DUNFIRTH tee-KINNEGAD 110-1 | Unknown | Unknown | 10 | Planned | December | December
TO-27-KIN-110SA1-2CB-05 | COUPLER/SECTIONALISING CB - KINNEGAD 110-KINNEGAD 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | December | December
TO-27-KIN-T102-03 | TSO CUSTOMER TRANSFORMER - KINNEGAD 110-KINNEGAD 10-T102 | Unknown | Unknown | 10 | Planned | December | December
TO-27-FLA-LOU-1-04 | 220kV FEEDER - FLAGFORD 220-LOUTH 220-1 | Unknown | Unknown | 2 | Planned | December | December
TO-27-CLT-MAY-1-01 | 220kV FEEDER - CASTLELOST 220-MAYNOOTH 220-1 | Unknown | Unknown | 5 | Planned | December | December

## GEN_Dublin
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-27-DND-T121-02 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | Unknown | Unknown |  | Planned | January | March
TO-27-110 kV A1 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A1 | Unknown | Unknown | 9 | Planned | January | January
TO-27-110 kV B1 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B1 | Unknown | Unknown | 9 | Planned | January | January
TO-27-CKG-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-2CB | Unknown | Unknown | 9 | Planned | January | January
TO-27-CKG-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 9 | Planned | January | January
TO-27-CKG-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-2CB | Unknown | Unknown | 9 | Planned | January | January
TO-27-CKG-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 9 | Planned | January | January
TO-27-NW-PB-1-02 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | 5 | 5 | 5 | Proposed | 04/01/2027 | 08/01/2027
TO-27-CKM GIS-R2001-01 | CAPACITOR/SVC/REACTOR - CARRICKMINES GIS 220-CARRICKMINES GIS 220-R2001 | 29 | 20 | 20 | Proposed | 06/01/2027 | 03/02/2027
TO-27-FIN-NW-1-04 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | 2 | 0 | 0 | Proposed | 09/01/2027 | 10/01/2027
TO-27-110 kV A1 @ BAG-01 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110A1 | 5 | 5 | 5 | Proposed | 11/01/2027 | 15/01/2027
TO-27-110 kV B1 @ BAG-01 | BUSBAR SECTION - BARNAGEERAGH 110-BARNAGEERAGH 110-110B1 | 5 | 5 | 5 | Proposed | 11/01/2027 | 15/01/2027
TO-27-BAG-110K1-01 | COUPLER/SECTIONALISING CB - BARNAGEERAGH 110-BARNAGEERAGH 110-110K1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-BLK,T-MAY-1-01 | 110kV FEEDER - BLAKE tee-MAYNOOTH 110-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-CKM-PB-1-01 | 220kV FEEDER - CARRICKMINES 220-POOLBEG 220-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-CKM-PST2201-01 | TRANSFORMER - CARRICKMINES 220-CARRICKMINES 220-PST2201 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-DSN-400K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 400-DUNSTOWN 400-400K1-2 | 12 | 10 | 10 | Proposed | 11/01/2027 | 22/01/2027
TO-27-AUN-T123-01 | TSO CUSTOMER TRANSFORMER - AUNGIERSTOWN 110-AUNGIERSTOWN 20-T123 | 2 | 2 | 2 | Proposed | 12/01/2027 | 13/01/2027
TO-27-CBT-CKG-2-01 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-2 | Unknown | Unknown | 2 | Planned | January | January
TO-27-400 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | Unknown | Unknown | 25 | Planned | January | February
TO-27-BAG-CLG-1-01 | 110kV FEEDER - BARNAGEERAGH 110-CLOGHRAN 110-1 | 3 | 3 | 3 | Proposed | 19/01/2027 | 21/01/2027
TO-27-WOO-T4204-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | 22 | 15 | 15 | Proposed | 19/01/2027 | 09/02/2027
TO-27-WOO-T4204-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 60 | Planned | January | April
TO-27-BNK-CBT-2-01 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | 1 | 1 | 1 | Proposed | 20/01/2027 | 20/01/2027
TO-27-BNK-T121-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T121 | Unknown | Unknown | 2 | Planned | January | January
TO-27-MAY-TH-1-01 | 220kV FEEDER - MAYNOOTH 220-TURLOUGH HILL 220-1 | 43 | 30 | 30 | Proposed | 21/01/2027 | 04/03/2027
TO-27-BRT-220K2-01 | COUPLER/SECTIONALISING CB - BRACETOWN 220-BRACETOWN 220-220K2 | 5 | 5 | 5 | Proposed | 25/01/2027 | 29/01/2027
TO-27-FIN GIS-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | 12 | 9 | 9 | Proposed | 25/01/2027 | 05/02/2027
TO-27-KUD-T102-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T102 | 2 | 2 | 2 | Proposed | 25/01/2027 | 26/01/2027
TO-27-BLU-T131-01 | GENERATOR TRANSFORMER - BLUNDELSTOWN 110-BLUNDELSTOWN 33-T131 | 2 | 2 | 2 | Proposed | 26/01/2027 | 27/01/2027
TO-27-MCE-T102-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T102 | Unknown | Unknown | 120 | Reference (Planned) | January | July
TO-27-BEG-CKM GIS-1-01 | 110kV FEEDER - BALLYBEG 110-CARRICKMINES GIS 110-1 | Unknown | Unknown | 1 | Planned | February | February
TO-27-BDA-NEW-1-01 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | Unknown | Unknown | 4 | Planned | February | February
TO-27-CBT-220K2-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220K2 | Unknown | Unknown | 4 | Planned | February | February
TO-27-CDU-FIN-1-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-1 | Unknown | Unknown | 9 | Planned | February | February
TO-27-CBT-INC-1-01 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | Unknown | Unknown | 20 | Planned | February | March
TO-27-CBT-INC-1-02 | 220kV FEEDER - CASTLEBAGOT 220-INCHICORE 220-1 | Unknown | Unknown | 35 | Planned | February | March
TO-27-BDA-MON-1-02 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-BDA-MON-1-03 | 110kV FEEDER - BARODA 110-MONREAD 110-1 | Unknown | Unknown | 25 | Planned | February | March
TO-27-BRT-CLE-2-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-2 | Unknown | Unknown | 5 | Planned | February | February
TO-27-FIN GIS-110K2-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K2 | Unknown | Unknown | 10 | Planned | February | February
TO-27-FIN GIS-110K5-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K5 | Unknown | Unknown | 10 | Planned | February | February
TO-27-FIN GIS-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA2-4CB | Unknown | Unknown | 10 | Planned | February | February
TO-27-MAY-220K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | Unknown | Unknown | 5 | Planned | February | February
TO-27-PB-R2002-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown | 5 | Planned | February | February
TO-27-INC-220K2-4-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K2-4 | Unknown | Unknown | 10 | Planned | February | February
TO-27-BRT-CLE-4-01 | 220kV FEEDER - BRACETOWN 220-CLONEE 220-4 | Unknown | Unknown | 5 | Planned | February | February
TO-27-CDU-FIN-2-02 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 10 | Planned | February | February
TO-27-CDU-GLN-1-01 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | Unknown | Unknown | 3 | Planned | February | February
TO-27-110 kV A1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110A1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-110 kV B1 @ DND-01 | BUSBAR SECTION - DARNDALE 110-DARNDALE 110-110B1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-DND-110K1-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | Unknown | Unknown | 10 | Planned | February | March
TO-27-DND-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | Unknown | Unknown | 10 | Planned | February | March
TO-27-DND-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | Unknown | Unknown | 10 | Planned | February | March
TO-27-DND-T121-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | Unknown | Unknown | 5 | Planned | February | February
TO-27-BRT-T222-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T222 | Unknown | Unknown | 5 | Planned | February | February
TO-27-FIN GIS-110SA3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA3-5CB | Unknown | Unknown | 10 | Planned | February | March
TO-27-KYT-MAY-1-01 | 220kV FEEDER - KELLYSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-SHL-D2/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 5 | Planned | February | February
TO-27-BLC-DND-1-01 | 110kV FEEDER - BELCAMP 110-DARNDALE 110-1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-BRT-T224-01 | TSO CUSTOMER TRANSFORMER - BRACETOWN 220-BRACETOWN 20-T224 | Unknown | Unknown | 5 | Planned | March | March
TO-27-110 kV A3 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110A3 | Unknown | Unknown | 9 | Planned | March | March
TO-27-110 kV B3 @ CKG-01 | BUSBAR SECTION - CORKAGH 110-CORKAGH 110-110B3 | Unknown | Unknown | 9 | Planned | March | March
TO-27-CKG-110K3-02 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | Unknown | Unknown | 9 | Planned | March | March
TO-27-CKG-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 9 | Planned | March | March
TO-27-CKG-110SB1-3CB-03 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 9 | Planned | March | March
TO-27-DSN-220K1-2-01 | COUPLER/SECTIONALISING CB - DUNSTOWN 220-DUNSTOWN 220-220K1-2 | Unknown | Unknown | 10 | Planned | March | March
TO-27-INC-PB-1-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | Unknown | Unknown | 10 | Planned | March | March
TO-27-OST-WOO-1-03 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 20 | Planned | March | March
TO-27-OST-WOO-1-02 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 20 | Planned | March | March
TO-27-BAG-T101-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T101 | Unknown | Unknown | 4 | Planned | March | March
TO-27-220 kV A8 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A8 | Unknown | Unknown | 15 | Planned | March | March
TO-27-220 kV B8 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B8 | Unknown | Unknown | 15 | Planned | March | March
TO-27-INC-SA6-8CB-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA6-8CB | Unknown | Unknown | 15 | Planned | March | March
TO-27-INC-SA8-10CB-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA8-10CB | Unknown | Unknown | 15 | Planned | March | March
TO-27-INC-SB6-8CB-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB6-8CB | Unknown | Unknown | 15 | Planned | March | March
TO-27-INC-SB8-10CB-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB8-10CB | Unknown | Unknown | 15 | Planned | March | March
TO-27-NW-PB-1-01 | 220kV FEEDER - NORTH WALL 220-POOLBEG 220-1 | Unknown | Unknown | 7 | Planned | March | March
TO-27-CBT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 220-CASTLEBAGOT 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | March | March
TO-27-FIN GIS-110SA4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 9 | Planned | March | March
TO-27-OST-WOO-1-04 | 400kV FEEDER - OLDSTREET 400-WOODLAND 400-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-SHL-D2/CB2-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB2 | Unknown | Unknown | 5 | Planned | March | March
TO-27-WOO-400K1-2-03 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown | 5 | Planned | March | March
TO-27-WOO-T4202-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 5 | Planned | March | March
TO-27-WOO-T4204-04 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | Unknown | Unknown | 5 | Planned | March | March
TO-27-BAG-T103-01 | TSO CUSTOMER TRANSFORMER - BARNAGEERAGH 110-BARNAGEERAGH 11-T103 | Unknown | Unknown | 4 | Planned | March | March
TO-27-TH-T2001/2-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2001/2 | Unknown | Unknown | 2 | Planned | March | March
TO-27-CBT-CKG-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CORKAGH 110-1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-220 kV A2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 33 | Planned | March | April
TO-27-220 kV B2 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 33 | Planned | March | April
TO-27-BAL-DEN-1-01 | 110kV FEEDER - BALTRASNA 110-DEENES 110-1 | Unknown | Unknown | 10 | Planned | March | March
TO-27-TH-T2003/4-01 | GENERATOR TRANSFORMER - TURLOUGH HILL 220-TURLOUGH HILL G1-T2003/4 | Unknown | Unknown | 2 | Planned | March | March
TO-27-CBT-KUD-1-01 | 110kV FEEDER - CASTLEBAGOT 110-KILMAHUD 110-1 | Unknown | Unknown | 2 | Planned | March | March
TO-27-GOR-MAY-1-02 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 7 | Planned | March | March
TO-27-GOR-MAY-1-03 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 7 | Planned | March | March
TO-27-DSN-T4201-01 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | Unknown | Unknown | 15 | Planned | March | April
TO-27-DSN-T4201-02 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | Unknown | Unknown | 123 | Planned | March | September
TO-27-BAL-110SA1-01 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA1 | Unknown | Unknown | 6 | Planned | March | March
TO-27-CLG-T122-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T122 | Unknown | Unknown | 2 | Planned | March | March
TO-27-CBT-KSG-1-01 | 110kV FEEDER - CASTLEBAGOT 110-KISHOGE 110-1 | Unknown | Unknown | 1 | Planned | March | March
TO-27-CBT-CLU-1-01 | 110kV FEEDER - CASTLEBAGOT 110-CLUTTERLAND 110-1 | Unknown | Unknown | 4 | Planned | March | March
TO-27-FIN GIS-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 8 | Planned | March | April
TO-27-BAL-110SA2-01 | SECTIONALISING DISCONNECT - BALTRASNA 110-BALTRASNA 110-110SA2 | Unknown | Unknown | 6 | Planned | March | April
TO-27-BAL-CDU-1-01 | 110kV FEEDER - BALTRASNA 110-CORDUFF 110-1 | Unknown | Unknown | 6 | Planned | March | April
TO-27-BAL-T122-01 | DISTRIBUTION TRANSFORMER - BALTRASNA 110-BALTRASNA 20-T122 | Unknown | Unknown | 6 | Reference (Planned) | March | April
TO-27-CBT-T2102-01 | TRANSFORMER - CASTLEBAGOT 220-CASTLEBAGOT 110-T2102 | Unknown | Unknown | 9 | Planned | March | April
TO-27-DSN-MAY-2-02 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 7 | Planned | March | April
TO-27-220 kV A1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 4 | Planned | March | April
TO-27-FIN-220K1-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | Unknown | Unknown |  | Planned | March | October
TO-27-FIN-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 4 | Planned | March | April
TO-27-FIN-NW-1-01 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 88 | Planned | March | August
TO-27-FIN-NW-1-02 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown |  | Planned | March | August
TO-27-400 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400A2 | Unknown | Unknown | 5 | Planned | March | April
TO-27-400 kV B2 @ WOO-02 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B2 | Unknown | Unknown | 5 | Planned | March | April
TO-27-220 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220A1 | Unknown | Unknown | 115 | Planned | March | September
TO-27-220 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 220-DUNSTOWN 220-220B1 | Unknown | Unknown | 115 | Planned | March | September
TO-27-400 kV A1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | Unknown | Unknown | 115 | Planned | March | September
TO-27-400 kV B1 @ DSN-01 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | Unknown | Unknown | 115 | Planned | March | September
TO-27-DSN-T4201-04 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | Unknown | Unknown | 115 | Planned | March | September
TO-27-INC-PB-1-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | Unknown | Unknown | 15 | Planned | March | April
TO-27-INC-PB-2-01 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 15 | Planned | March | April
TO-27-INC-PB-2-02 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 87 | Planned | March | August
TO-27-KTL-MON-1-01 | 110kV FEEDER - KILTEEL 110-MONREAD 110-1 | Unknown | Unknown | 2 | Planned | March | April
TO-27-220 kV B1 @ FIN-01 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 84 | Planned | April | August
TO-27-FIN-220SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 84 | Planned | April | August
TO-27-GLN-T133-03 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | Unknown | Unknown | 5 | Planned | April | April
TO-27-PA-110SA1-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-PA-110SA2-01 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 15 | Planned | April | April
TO-27-PA-T101-01 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-PA-1-01 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-STR,T-PA-1-02 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-220 kV A2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220A2 | Unknown | Unknown | 5 | Planned | April | April
TO-27-220 kV B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B2 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CDU-GLN-1-02 | 110kV FEEDER - CORDUFF 110-GALLANSTOWN 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-DFR,T-RNW-1-01 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 6 | Planned | April | April
TO-27-DFR,T-RNW-1-07 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-DFR,T-RNW-1-05 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 60 | Planned | April | July
TO-27-DFR,T-RNW-1-04 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-DFR,T-RNW-1-03 | 110kV FEEDER - DUNFIRTH tee-RINAWADE 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-GLN-110K1-01 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-GLN-PLA-1-01 | 110kV FEEDER - GALLANSTOWN 110-PLATIN 110-1 | Unknown | Unknown | 3 | Planned | April | April
TO-27-MAY-RNW-1-01 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | Unknown | 14 | Planned | April | April
TO-27-MAY-RNW-1-03 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-MAY-RNW-1-04 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-MAY-RYB GIS-1-01 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | Unknown | 10 | Planned | April | April
TO-27-MAY-RYB GIS-1-02 | 110kV FEEDER - MAYNOOTH 110-RYEBROOK GIS 110-1 | Unknown | Unknown | 44 | Planned | April | June
TO-27-FIN GIS-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB2-4CB | Unknown | Unknown | 1 | Planned | April | April
TO-27-LOU-WOO-1-01 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 50 | Planned | April | June
TO-27-LOU-WOO-1-02 | 220kV FEEDER - LOUTH 220-WOODLAND 220-1 | Unknown | Unknown | 50 | Planned | April | June
TO-27-CKM GIS-DSN-1-01 | 220kV FEEDER - CARRICKMINES GIS 220-DUNSTOWN 220-1 | Unknown | Unknown | 15 | Planned | April | April
TO-27-CLG-CDU-1-01 | 110kV FEEDER - CLOGHRAN 110-CORDUFF 110-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CLG-T126-01 | TSO CUSTOMER TRANSFORMER - CLOGHRAN 110-CLOGHRAN 20-T126 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CDU-HN-1-01 | 220kV FEEDER - CORDUFF 220-HUNTSTOWN 220-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-DND-T123-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T123 | Unknown | Unknown | 5 | Planned | April | April
TO-27-FIN GIS-110SB3-5CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB3-5CB | Unknown | Unknown | 10 | Planned | April | April
TO-27-HN-T2002-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G2-T2002 | Unknown | Unknown | 5 | Planned | April | April
TO-27-110 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-MAY-T2101-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CLE-T221-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T221 | Unknown | Unknown | 5 | Planned | April | April
TO-27-CLU-KUD-1-01 | 110kV FEEDER - CLUTTERLAND 110-KILMAHUD 110-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-DSN-TH-1-01 | 220kV FEEDER - DUNSTOWN 220-TURLOUGH HILL 220-1 | Unknown | Unknown | 2 | Planned | April | April
TO-27-INC-T2102-01 | TRANSFORMER - INCHICORE 220-INCHICORE 110-T2102 | Unknown | Unknown | 75 | Reference (Planned) | April | August
TO-27-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | Unknown | Unknown | 5 | Planned | April | April
TO-27-PRN-T4301-02 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | Unknown | Unknown | 5 | Planned | April | April
TO-27-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | Unknown | Unknown |  | Planned | April | April
TO-27-WOO-400K1-2-02 | COUPLER/SECTIONALISING CB - WOODLAND 400-WOODLAND 400-400K1-2 | Unknown | Unknown |  | Planned | April | April
TO-27-WOO-T4201-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown | 5 | Planned | April | April
TO-27-WOO-T4201-03 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4201 | Unknown | Unknown |  | Planned | April | April
TO-27-CLE-T222-01 | TSO CUSTOMER TRANSFORMER - CLONEE 220-CLONEE 20-T222 | Unknown | Unknown | 5 | Planned | April | April
TO-27-FIN GIS-110SB4-6CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | 12 | 9 | 9 | Proposed | 26/04/2027 | 07/05/2027
TO-27-PA-110SA1-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-PA-110SA2-02 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 80 | Planned | April | August
TO-27-PA-T101-02 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 80 | Planned | April | August
TO-27-STR,T-PA-1-03 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 80 | Planned | April | August
TO-27-MAY-RNW-1-02 | 110kV FEEDER - MAYNOOTH 110-RINAWADE 110-1 | Unknown | Unknown | 30 | Planned | April | June
TO-27-MAY-T2104-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2104 | Unknown | Unknown | 20 | Planned | May | June
TO-27-PB-R223-4-01 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R223-4 | Unknown | Unknown | 6 | Planned | May | May
TO-27-PB-SHL-1-01 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-PB-SHL-1-02 | 220kV FEEDER - POOLBEG 220-SHELLYBANKS 220-1 | Unknown | Unknown | 30 | Planned | May | June
TO-27-SHL-D1/CB3-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | Unknown | 8 | Planned | May | May
TO-27-SHL-D1/CB3-02 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB3 | Unknown | Unknown | 30 | Planned | May | June
TO-27-SHL-D2/CB3-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB3 | Unknown | Unknown | 30 | Planned | May | June
TO-27-FIN GIS-MCE-1-01 | 110kV FEEDER - FINGLAS GIS 110-MACETOWN 110-1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-PB-R2002-02 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown | 5 | Planned | May | May
TO-27-WOO-T4202-01 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4202 | Unknown | Unknown | 10 | Planned | May | May
TO-27-GLN-T133-01 | GENERATOR TRANSFORMER - GALLANSTOWN 110-GALLANSTOWN 33-T133 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BDA-NEW-1-02 | 110kV FEEDER - BARODA 110-NEWBRIDGE 110-1 | Unknown | Unknown | 10 | Planned | May | June
TO-27-KYT-220K2-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-CDU-110K1-3-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-3 | Unknown | Unknown | 1 | Planned | May | May
TO-27-COL-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | Unknown | Unknown | 9 | Planned | May | June
TO-27-CDU-110K1-2-01 | COUPLER/SECTIONALISING CB - CORDUFF 110-CORDUFF 110-110K1-2 | Unknown | Unknown | 9 | Planned | May | June
TO-27-KYT-220K3-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220K3 | Unknown | Unknown | 5 | Planned | May | June
TO-27-GRI-T141-01 | DISTRIBUTION TRANSFORMER - GRIFFINRATH 110-GRIFFINRATH 38-T141 | Unknown | Unknown | 60 | Reference (Planned) | June | August
TO-27-GRI,T-GCA-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | Unknown | 4 | Planned | June | June
TO-27-GRI,T-GCA-1-02 | 110kV FEEDER - GRIFFINRATH tee-GRANGE CASTLE 110-1 | Unknown | Unknown | 60 | Planned | June | August
TO-27-GRI,T-GRI-1-01 | 110kV FEEDER - GRIFFINRATH tee-GRIFFINRATH 110-1 | Unknown | Unknown | 60 | Planned | June | August
TO-27-GRI,T-MAY-1-01 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | Unknown | 6 | Planned | June | June
TO-27-GRI,T-MAY-1-02 | 110kV FEEDER - GRIFFINRATH tee-MAYNOOTH 110-1 | Unknown | Unknown | 60 | Planned | June | August
TO-27-RNW-T121-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T121 | Unknown | Unknown | 57 | Planned | June | August
TO-27-RNW-T122-01 | TSO CUSTOMER TRANSFORMER - RINAWADE 110-RINAWADE 20-T122 | Unknown | Unknown | 57 | Planned | June | August
TO-27-FIN-HN-1-01 | 220kV FEEDER - FINGLAS 220-HUNTSTOWN 220-1 | Unknown | Unknown | 20 | Planned | June | July
TO-27-KUD-T101-01 | TSO CUSTOMER TRANSFORMER - KILMAHUD 110-KILMAHUD 10-T101 | Unknown | Unknown | 2 | Planned | June | June
TO-27-220 kV A4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220A4 | Unknown | Unknown | 5 | Planned | June | June
TO-27-220 kV B4 @ PB-01 | BUSBAR SECTION - POOLBEG 220-POOLBEG 220-220B4 | Unknown | Unknown | 5 | Planned | June | June
TO-27-COL-T121-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T121 | Unknown | Unknown | 55 | Reference (Planned) | June | August
TO-27-CDU-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - CORDUFF 220-CORDUFF 220-220SB2-4CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-KYT-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-DSN-T4201-03 | TRANSFORMER - DUNSTOWN 400-DUNSTOWN 220-T4201 | Unknown | Unknown | 60 | Planned | June | September
TO-27-CDU-MCE-1-01 | 110kV FEEDER - CORDUFF 110-MACETOWN 110-1 | Unknown | Unknown | 25 | Planned | June | July
TO-27-HN-T2010/11-01 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 10 | Planned | June | July
TO-27-HN-T2010/11-02 | GENERATOR TRANSFORMER - HUNTSTOWN 220-HUNTSTOWN G10/11-T2010/11 | Unknown | Unknown | 10 | Planned | June | July
TO-27-KYT-220SA1-3CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SA1-3CB | Unknown | Unknown | 5 | Planned | June | June
TO-27-MCE-110SA1-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | Unknown | Unknown | 5 | Planned | June | June
TO-27-MCE-T121-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T121 | Unknown | Unknown | 7 | Planned | June | June
TO-27-220 kV A2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 25 | Planned | June | July
TO-27-220 kV B2 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 25 | Planned | June | July
TO-27-COL-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | Unknown | Unknown | 10 | Planned | June | July
TO-27-COL-FIN GIS-1-01 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-COL-T103-04 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | Unknown | Unknown | 10 | Reference (Planned) | June | July
TO-27-COL-T121-03 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T121 | Unknown | Unknown | 10 | Reference (Planned) | June | July
TO-27-GOR-MAY-1-01 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-GOR-MAY-1-04 | 220kV FEEDER - GORMAN 220-MAYNOOTH 220-1 | Unknown | Unknown | 15 | Planned | June | July
TO-27-KYT-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | June | July
TO-27-COL-T103-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | Unknown | Unknown | 60 | Reference (Planned) | June | September
TO-27-DGY-FIN GIS-1-01 | 110kV FEEDER - DUNSOGHLY 110-FINGLAS GIS 110-1 | Unknown | Unknown | 3 | Planned | June | July
TO-27-DGY-T101-01 | GENERATOR TRANSFORMER - DUNSOGHLY 110-DUNSOGHLY 11-T101 | Unknown | Unknown | 3 | Planned | June | July
TO-27-DSN-MP GIS-1-01 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown | 58 | Planned | June | September
TO-27-DSN-MP GIS-1-02 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown |  | Planned | June | September
TO-27-DSN-MP GIS-1-04 | 400kV FEEDER - DUNSTOWN 400-MONEYPOINT GIS 400-1 | Unknown | Unknown | 58 | Planned | June | September
TO-27-110 kV A1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | Unknown | Unknown | 30 | Planned | June | August
TO-27-110 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | Unknown | Unknown | 30 | Planned | June | August
TO-27-CKG-110K2-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K2 | Unknown | Unknown | 5 | Planned | July | July
TO-27-KYT-220SB1-3CB-01 | COUPLER/SECTIONALISING CB - KELLYSTOWN 220-KELLYSTOWN 220-220SB1-3CB | Unknown | Unknown | 5 | Planned | July | July
TO-27-KTL-MAY-1-01 | 110kV FEEDER - KILTEEL 110-MAYNOOTH 110-1 | Unknown | Unknown | 10 | Planned | July | July
TO-27-220 kV A2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 40 | Planned | July | August
TO-27-220 kV B2 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN-220K2-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN-220SA1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN-220SB1-2CB-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-110 kV A1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | Unknown | Unknown | 40 | Planned | July | August
TO-27-110 kV B1 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110K1-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 9 | Planned | July | July
TO-27-FIN GIS-110K1-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110SA1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110SB1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-FIN GIS-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | Unknown | Unknown | 40 | Planned | July | August
TO-27-ARK-CKM GIS-1-03 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | Unknown | 50 | Planned | July | September
TO-27-ARK-CKM GIS-1-01 | 220kV FEEDER - ARKLOW 220-CARRICKMINES GIS 220-1 | Unknown | Unknown | 50 | Planned | July | September
TO-27-220 kV A10 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A10 | Unknown | Unknown | 15 | Planned | July | July
TO-27-220 kV A10 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A10 | Unknown | Unknown | 17 | Planned | July | July
TO-27-220 kV B10 @ INC-01 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B10 | Unknown | Unknown | 15 | Planned | July | July
TO-27-220 kV B10 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B10 | Unknown | Unknown | 17 | Planned | July | July
TO-27-INC-220K10-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K10 | Unknown | Unknown | 17 | Planned | July | July
TO-27-INC-220K10-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K10 | Unknown | Unknown | 15 | Planned | July | July
TO-27-INC-SA8-10CB-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA8-10CB | Unknown | Unknown | 15 | Planned | July | July
TO-27-INC-SA8-10CB-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA8-10CB | Unknown | Unknown | 17 | Planned | July | July
TO-27-INC-SB8-10CB-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB8-10CB | Unknown | Unknown | 15 | Planned | July | July
TO-27-INC-SB8-10CB-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB8-10CB | Unknown | Unknown | 17 | Planned | July | July
TO-27-KUD-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - KILMAHUD 110-KILMAHUD 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | July | July
TO-27-CKG-110K3-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110K3 | Unknown | Unknown | 5 | Planned | July | July
TO-27-MCE-T124-01 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | Unknown | Unknown | 8 | Planned | July | July
TO-27-MAY-110K1-2-01 | COUPLER/SECTIONALISING CB - MAYNOOTH 110-MAYNOOTH 110-110K1-2 | Unknown | Unknown | 10 | Planned | July | July
TO-27-CDU-SNU-1-01 | 110kV FEEDER - CORDUFF 110-SNUGBOROUGH 110-1 | Unknown | Unknown | 9 | Planned | July | July
TO-27-CKG-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-27-FIN GIS-MCE-1-02 | 110kV FEEDER - FINGLAS GIS 110-MACETOWN 110-1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-MCE-110SA1-02 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA1 | Unknown | Unknown | 2 | Planned | July | July
TO-27-MCE-110SA2-01 | SECTIONALISING DISCONNECT - MACETOWN 110-MACETOWN 110-110SA2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-MCE-T124-02 | TSO CUSTOMER TRANSFORMER - MACETOWN 110-MACETOWN 20-T124 | Unknown | Unknown | 2 | Planned | July | July
TO-27-DSN-MAY-2-03 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 15 | Planned | July | August
TO-27-DSN-MAY-2-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 15 | Planned | July | August
TO-27-MCE-T101-01 | DISTRIBUTION TRANSFORMER - MACETOWN 110-MACETOWN 10-T101 | Unknown | Unknown | 120 | Reference (Planned) | July | January
TO-27-CKG-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-2CB | Unknown | Unknown | 5 | Planned | July | July
TO-27-MAY-T2101-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2101 | Unknown | Unknown | 9 | Planned | July | August
TO-27-PB-220SA1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SA1-2 | Unknown | Unknown | 5 | Planned | July | July
TO-27-FIN-220K2-02 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 2 | Planned | July | July
TO-27-220 kV A8 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A8 | Unknown | Unknown | 2 | Planned | July | July
TO-27-220 kV B8 @ INC-03 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B8 | Unknown | Unknown | 2 | Planned | July | July
TO-27-INC-SA6-8CB-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA6-8CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-INC-SB6-8CB-02 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB6-8CB | Unknown | Unknown | 2 | Planned | July | July
TO-27-220 kV A1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A1 | Unknown | Unknown | 38 | Planned | August | September
TO-27-FIN-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 38 | Planned | August | September
TO-27-FIN-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 8 | Planned | August | August
TO-27-WOO-220K1-2-01 | COUPLER/SECTIONALISING CB - WOODLAND 220-WOODLAND 220-220K1-2 | Unknown | Unknown | 8 | Planned | August | August
TO-27-INC-PB-2-03 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-2 | Unknown | Unknown | 2 | Planned | August | August
TO-27-CKG-110SB1-3CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SB1-3CB | Unknown | Unknown | 5 | Planned | August | August
TO-27-INC-PB-1-03 | 220kV FEEDER - INCHICORE 220-POOLBEG 220-1 | Unknown | Unknown | 83 | Planned | August | December
TO-27-ISH-220K1-2-02 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | Unknown | 50 | Planned | August | October
TO-27-MAY-T2102-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | Unknown | Unknown | 18 | Planned | August | September
TO-27-NW-T2004/5-01 | GENERATOR TRANSFORMER - NORTH WALL 220-NORTH WALL G4/5-T2004/5 | Unknown | Unknown | 5 | Planned | August | August
TO-27-PB-220SB1-2-01 | SECTIONALISING DISCONNECT - POOLBEG 220-POOLBEG 220-220SB1-2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-CBT-MAY-2-02 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-2 | Unknown | Unknown | 25 | Planned | August | September
TO-27-CKG-110SA1-3CB-01 | COUPLER/SECTIONALISING CB - CORKAGH 110-CORKAGH 110-110SA1-3CB | Unknown | Unknown | 5 | Planned | August | August
TO-27-CKG-T121-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T121 | Unknown | Unknown | 5 | Planned | August | August
TO-27-SNU-T104-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 10-T104 | Unknown | Unknown | 5 | Planned | August | August
TO-27-DND-T125-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T125 | Unknown | Unknown | 2 | Planned | August | August
TO-27-PA-110SA1-03 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA1 | Unknown | Unknown | 15 | Planned | August | September
TO-27-PA-110SA2-03 | SECTIONALISING DISCONNECT - POLLAPHUCA 110-POLLAPHUCA 110-110SA2 | Unknown | Unknown | 15 | Planned | August | September
TO-27-PA-T101-03 | GENERATOR TRANSFORMER - POLLAPHUCA 110-POLLAPHUCA G1-T101 | Unknown | Unknown | 15 | Planned | August | September
TO-27-STR,T-PA-1-04 | 110kV FEEDER - STRATFORD tee-POLLAPHUCA 110-1 | Unknown | Unknown | 15 | Planned | August | September
TO-27-CKG-T122-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T122 | Unknown | Unknown | 5 | Planned | August | August
TO-27-SNU-T131-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 33-T131 | Unknown | Unknown | 5 | Planned | August | August
TO-27-COL-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | August | August
TO-27-COL-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | August | August
TO-27-COL-CDU-1-02 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | Unknown | Unknown | 2 | Planned | August | August
TO-27-COL-T103-02 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 10-T103 | Unknown | Unknown | 2 | Reference (Planned) | August | August
TO-27-FIN-220K1-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K1 | Unknown | Unknown | 2 | Planned | August | August
TO-27-CKG-T123-01 | TSO CUSTOMER TRANSFORMER - CORKAGH 110-CORKAGH 20-T123 | Unknown | Unknown | 5 | Planned | August | September
TO-27-SNU-T133-01 | TSO CUSTOMER TRANSFORMER - SNUGBOROUGH 110-SNUGBOROUGH 33-T133 | Unknown | Unknown | 5 | Planned | August | September
TO-27-SHL-D1/CB1-01 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D1/CB1 | Unknown | Unknown | 50 | Planned | August | November
TO-27-SHL-D2/CB1-03 | COUPLER/SECTIONALISING CB - SHELLYBANKS 220-SHELLYBANKS 220-D2/CB1 | Unknown | Unknown | 50 | Planned | August | November
TO-27-SHL-T2016-01 | GENERATOR TRANSFORMER - SHELLYBANKS 220-SHELLYBANKS G6-T2016 | Unknown | Unknown | 50 | Planned | August | November
TO-27-CDU-FIN-2-01 | 220kV FEEDER - CORDUFF 220-FINGLAS 220-2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-220 kV A2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN-220K2-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN-220SB1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV A1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV B1 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110K1-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110SA1-2CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110SA1-3CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-FIN GIS-110SB1-3CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB1-3CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-MAY-T2103-01 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2103 | Unknown | Unknown | 20 | Planned | September | September
TO-27-CLE-CDU-1-01 | 220kV FEEDER - CLONEE 220-CORDUFF 220-1 | Unknown | Unknown | 10 | Planned | September | September
TO-27-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-PB-R2002-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown | 5 | Planned | September | September
TO-27-PB-T2007/8-01 | GENERATOR TRANSFORMER - POOLBEG 220-POOLBEG G7/8-T2007/8 | Unknown | Unknown | 2 | Planned | September | September
TO-27-TH-220K1-2-01 | COUPLER/SECTIONALISING CB - TURLOUGH HILL 220-TURLOUGH HILL 220-220K1-2 | Unknown | Unknown | 9 | Planned | September | September
TO-27-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-400 kV A1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400A1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-400 kV B1 @ DSN-02 | BUSBAR SECTION - DUNSTOWN 400-DUNSTOWN 400-400B1 | Unknown | Unknown | 5 | Planned | September | September
TO-27-COL-110SA1-2CB-03 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-COL-110SA1-3CB-04 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-3CB | Unknown | Unknown | 2 | Planned | September | September
TO-27-COL-CDU-1-03 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-COL-T121-02 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T121 | Unknown | Unknown | 2 | Reference (Planned) | September | September
TO-27-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | September | September
TO-27-COL-T122-01 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T122 | Unknown | Unknown | 55 | Reference (Planned) | September | December
TO-27-COL-CDU-1-01 | 110kV FEEDER - COLLEGE PARK 110-CORDUFF 110-1 | Unknown | Unknown | 10 | Planned | September | October
TO-27-COL-T122-02 | DISTRIBUTION TRANSFORMER - COLLEGE PARK 110-COLLEGE PARK 20-T122 | Unknown | Unknown | 10 | Reference (Planned) | September | October
TO-27-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | September | October
TO-27-220 kV B1 @ FIN-02 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B1 | Unknown | Unknown | 5 | Planned | September | October
TO-27-FIN-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | September | October
TO-27-FIN-NW-1-03 | 220kV FEEDER - FINGLAS 220-NORTH WALL 220-1 | Unknown | Unknown | 5 | Planned | September | October
TO-27-CBT-MAY-1-01 | 220kV FEEDER - CASTLEBAGOT 220-MAYNOOTH 220-1 | Unknown | Unknown | 19 | Planned | October | October
TO-27-CLE-WOO-1-01 | 220kV FEEDER - CLONEE 220-WOODLAND 220-1 | Unknown | Unknown | 10 | Planned | October | October
TO-27-CRU-T221-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T221 | Unknown | Unknown | 5 | Planned | October | October
TO-27-DSN-MAY-1-01 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-1 | Unknown | Unknown | 15 | Planned | October | October
TO-27-110 kV A1 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110A1 | Unknown | Unknown | 25 | Planned | October | November
TO-27-110 kV B1 @ MAY-02 | BUSBAR SECTION - MAYNOOTH 110-MAYNOOTH 110-110B1 | Unknown | Unknown | 25 | Planned | October | November
TO-27-CRU-T223-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T223 | 5 | 5 | 5 | Proposed | 11/10/2027 | 15/10/2027
TO-27-220 kV A1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-220 kV A2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-220 kV B1 @ MAY-01 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-220 kV B2 @ MAY-03 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-MAY-220K1-2-02 | COUPLER/SECTIONALISING CB - MAYNOOTH 220-MAYNOOTH 220-220K1-2 | Unknown | Unknown | 5 | Planned | October | October
TO-27-MAY-T2102-02 | TRANSFORMER - MAYNOOTH 220-MAYNOOTH 110-T2102 | Unknown | Unknown | 5 | Planned | October | October
TO-27-CDU-WOO-1-01 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | Unknown | Unknown | 29 | Planned | October | November
TO-27-CRU-T224-01 | TSO CUSTOMER TRANSFORMER - CRUISERATH 220-CRUISERATH 20-T224 | Unknown | Unknown | 5 | Planned | October | October
TO-27-ISH-220K1-2-01 | COUPLER/SECTIONALISING CB - IRISHTOWN 220-IRISHTOWN 220-220K1-2 | Unknown | Unknown | 10 | Planned | October | November
TO-27-220 kV A2 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 7 | Planned | October | October
TO-27-220 kV B2 @ MAY-04 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 7 | Planned | October | October
TO-27-DND-T122-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T122 | Unknown | Unknown | 1 | Planned | October | October
TO-27-DND-T124-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T124 | Unknown | Unknown | 1 | Planned | October | October
TO-27-DND-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SA1-2CB | Unknown | Unknown | 1 | Planned | October | October
TO-27-DND-110K1-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110K1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-MAY-TEN-1-01 | 110kV FEEDER - MAYNOOTH 110-TIMAHOE 110-1 | Unknown | Unknown | 5 | Planned | November | November
TO-27-DSN-MAY-2-04 | 220kV FEEDER - DUNSTOWN 220-MAYNOOTH 220-2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-110 kV A6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV B6 @ FIN GIS-01 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | Unknown | Unknown |  | Planned | November | November
TO-27-FIN GIS-110K6-01 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | Unknown |  | Planned | November | November
TO-27-FIN GIS-110SA4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 10 | Planned | November | November
TO-27-FIN GIS-110SB4-6CB-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 10 | Planned | November | November
TO-27-220 kV A2 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220A2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-220 kV B2 @ MAY-05 | BUSBAR SECTION - MAYNOOTH 220-MAYNOOTH 220-220B2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-DND-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - DARNDALE 110-DARNDALE 110-110SB1-2CB | Unknown | Unknown | 5 | Planned | November | November
TO-27-FIN GIS-GLA-1-01 | 110kV FEEDER - FINGLAS GIS 110-GLASMORE 110-1 | Unknown | Unknown | 5 | Reference (Planned) | November | November
TO-27-220 kV A8 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220A8 | Unknown | Unknown | 15 | Planned | November | December
TO-27-220 kV B8 @ INC-02 | BUSBAR SECTION - INCHICORE 220-INCHICORE 220-220B8 | Unknown | Unknown | 15 | Planned | November | December
TO-27-INC-SA6-8CB-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA6-8CB | Unknown | Unknown | 15 | Planned | November | December
TO-27-INC-SA8-10CB-04 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SA8-10CB | Unknown | Unknown | 15 | Planned | November | December
TO-27-INC-SB6-8CB-03 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB6-8CB | Unknown | Unknown | 15 | Planned | November | December
TO-27-INC-SB8-10CB-04 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220SB8-10CB | Unknown | Unknown | 15 | Planned | November | December
TO-27-110 kV A6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110A6 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV B6 @ FIN GIS-02 | BUSBAR SECTION - FINGLAS GIS 110-FINGLAS GIS 110-110B6 | Unknown | Unknown |  | Planned | November | November
TO-27-FIN GIS-110K6-02 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110K6 | Unknown | Unknown |  | Planned | November | November
TO-27-FIN GIS-110SA4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SA4-6CB | Unknown | Unknown | 3 | Planned | November | November
TO-27-FIN GIS-110SB4-6CB-03 | COUPLER/SECTIONALISING CB - FINGLAS GIS 110-FINGLAS GIS 110-110SB4-6CB | Unknown | Unknown | 3 | Planned | November | November
TO-27-FIN GIS-T2104-01 | TRANSFORMER - FINGLAS 220-FINGLAS GIS 110-T2104 | Unknown | Unknown | 3 | Planned | November | November
TO-27-FIN-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | Unknown | Unknown | 10 | Planned | November | December
TO-27-INC-220K4-6-01 | COUPLER/SECTIONALISING CB - INCHICORE 220-INCHICORE 220-220K4-6 | Unknown | Unknown | 10 | Planned | December | December
TO-27-COL-110SA1-2CB-04 | COUPLER/SECTIONALISING CB - COLLEGE PARK 110-COLLEGE PARK 110-110SA1-2CB | Unknown | Unknown | 2 | Planned | December | December
TO-27-COL-FIN GIS-1-02 | 110kV FEEDER - COLLEGE PARK 110-FINGLAS GIS 110-1 | Unknown | Unknown | 2 | Planned | December | December
TO-27-PB-R2002-04 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2002 | Unknown | Unknown | 5 | Planned | December | December

## GEN_Cork
Outage ID | Feeder ID | Calendar Day Duration | Working Day Duration | Work Days | Outage Status | Start | Finish
TO-27-KRA-220K1-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | 5 | 5 | 5 | Proposed | 04/01/2027 | 08/01/2027
TO-27-CLA-KRA-1-01 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | 19 | 15 | 15 | Proposed | 11/01/2027 | 29/01/2027
TO-27-LYT-T132-01 | GENERATOR TRANSFORMER - LYSAGHTSTOWN 110-LYSAGHTSTOWN 33-T132 | 2 | 2 | 2 | Proposed | 11/01/2027 | 12/01/2027
TO-27-KRA-220K4-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K4 | 4 | 4 | 4 | Proposed | 12/01/2027 | 15/01/2027
TO-27-LYT-MID-1-01 | 110kV FEEDER - LYSAGHTSTOWN 110-MIDLETON 110-1 | 176 | 120 | 120 | Proposed | 12/01/2027 | 06/07/2027
TO-27-LYT-MID-1-02 | 110kV FEEDER - LYSAGHTSTOWN 110-MIDLETON 110-1 | Unknown | Unknown | 120 | Planned | January | July
TO-27-MID-110SA1-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | Unknown | Unknown | 120 | Planned | January | July
TO-27-MID-110SA2-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | Unknown | Unknown | 120 | Planned | January | July
TO-27-MID-T101-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T101 | Unknown | Unknown | 120 | Reference (Planned) | January | July
TO-27-MID-T141-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 38-T141 | Unknown | Unknown | 120 | Reference (Planned) | January | July
TO-27-KRA-220SA2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA2-4CB | 4 | 4 | 4 | Proposed | 18/01/2027 | 21/01/2027
TO-27-CLA-MAC-2-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-2 | 1 | 1 | 1 | Proposed | 22/01/2027 | 22/01/2027
TO-27-CLA-KRA-1-02 | 220kV FEEDER - CLASHAVOON 220-KNOCKRAHA 220-1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-CLA-MAC-1-01 | 110kV FEEDER - CLASHAVOON 110-MACROOM 110-1 | Unknown | Unknown | 14 | Planned | January | February
TO-27-220 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-220 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-KRA-220K1-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | Unknown | Unknown | 5 | Planned | January | January
TO-27-KRA-220SA1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 5 | Planned | January | January
TO-27-KRA-220SB1-2CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 5 | Planned | January | January
TO-27-KRA-T2101-01 | TRANSFORMER - KNOCKRAHA 220-KNOCKRAHA 110-T2101 | Unknown | Unknown | 5 | Planned | January | January
TO-27-AD-220K1-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | 2 | 2 | 2 | Proposed | 02/02/2027 | 03/02/2027
TO-27-KRA-220SB2-4CB-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB2-4CB | Unknown | Unknown | 4 | Planned | February | February
TO-27-BAR-T141-01 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 2 | Reference (Planned) | February | February
TO-27-KRA-110K1-2-01 | COUPLER/SECTIONALISING CB - KNOCKRAHA 110-KNOCKRAHA 110-110K1-2 | Unknown | Unknown | 6 | Planned | February | February
TO-27-AD-SA1-2CB-01 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220SA1-2CB | Unknown | Unknown | 1 | Planned | February | February
TO-27-BAN-110SA1-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 7 | Planned | February | February
TO-27-BAN-110SA2-06 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 7 | Planned | February | February
TO-27-BAN-BRI-1-01 | 110kV FEEDER - BANDON 110-BRINNY 110-1 | Unknown | Unknown | 7 | Planned | February | February
TO-27-BAN-DMY-1-01 | 110kV FEEDER - BANDON 110-DUNMANWAY 110-1 | Unknown | Unknown | 15 | Planned | February | March
TO-27-BAN-T141-02 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | February | February
TO-27-CD-MAC-1-01 | 110kV FEEDER - CARRIGADROHID 110-MACROOM 110-1 | Unknown | Unknown | 2 | Planned | February | February
TO-27-220 kV A1 @ AD-02 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A1 | Unknown | Unknown | 0 | Planned | February | February
TO-27-220 kV A2 @ AD-01 | BUSBAR SECTION - AGHADA 220-AGHADA 220-220A2 | Unknown | Unknown | 0 | Planned | February | February
TO-27-AD-220K1-03 | COUPLER/SECTIONALISING CB - AGHADA 220-AGHADA 220-220K1 | Unknown | Unknown | 0 | Planned | February | February
TO-27-AD-GGO-1-04 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 0 | Planned | February | February
TO-27-AD-T2014-02 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 0 | Planned | February | February
TO-27-220 kV B1 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220B1 | Unknown | Unknown | 0 | Planned | February | February
TO-27-220 kV B2 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220B2 | Unknown | Unknown | 0 | Planned | February | February
TO-27-GGO-T2001-05 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 0 | Planned | February | February
TO-27-CVW-KRA-1-01 | 110kV FEEDER - CASTLEVIEW 110-KNOCKRAHA 110-1 | Unknown | Unknown | 5 | Planned | March | March
TO-27-AD-GGO-1-01 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-AD-GGO-1-02 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-AD-GGO-1-03 | 220kV FEEDER - AGHADA 220-GLANAGOW 220-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-220 kV A1/A2 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220A1-A2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-220 kV B1/B2 @ GGO-01 | BUSBAR SECTION - GLANAGOW 220-GLANAGOW 220-220B1-B2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | Unknown | 8 | Planned | March | March
TO-27-GGO-220K1-2-02 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-220K1-2-03 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-RAF-1-01 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | Unknown | Unknown | 19 | Planned | March | April
TO-27-GGO-RAF-1-02 | 220kV FEEDER - GLANAGOW 220-RAFFEEN 220-1 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-T2001-01 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 5 | Planned | March | March
TO-27-GGO-T2001-03 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 20 | Planned | March | April
TO-27-GGO-T2001-04 | GENERATOR TRANSFORMER - GLANAGOW 220-GLANAGOW G1-T2001 | Unknown | Unknown | 20 | Planned | March | April
TO-27-CLA-T2101-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2101 | Unknown | Unknown | 10 | Planned | March | March
TO-27-TBG-T141-01 | DISTRIBUTION TRANSFORMER - TRABEG 110-TRABEG 38-T141 | Unknown | Unknown | 129 | Reference (Planned) | March | September
TO-27-COW-RAF-1-01 | 110kV FEEDER - COW CROSS 110-RAFFEEN 110-1 | Unknown | Unknown | 5 | Planned | March | April
TO-27-AD-T2011/12-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G11/12-T2011/12 | Unknown | Unknown | 3 | Planned | March | April
TO-27-CLA-T2102-01 | TRANSFORMER - CLASHAVOON 220-CLASHAVOON 110-T2102 | Unknown | Unknown | 8 | Planned | March | April
TO-27-IA-MAC-1-01 | 110kV FEEDER - INNISCARRA 110-MACROOM 110-1 | Unknown | Unknown | 8 | Planned | April | April
TO-27-AD-RAF-1-01 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | Unknown | Unknown |  | Planned | April | May
TO-27-AD-RAF-1-02 | 220kV FEEDER - AGHADA 220-RAFFEEN 220-1 | Unknown | Unknown |  | Planned | April | April
TO-27-KRA-RAF-1-01 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | Unknown | Unknown | 5 | Planned | April | April
TO-27-KRA-RAF-1-02 | 220kV FEEDER - KNOCKRAHA 220-RAFFEEN 220-1 | Unknown | Unknown |  | Planned | April | April
TO-27-BAN-RAF-1-01 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown | 100 | Planned | April | September
TO-27-110 kV A1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | Unknown | Unknown | 111 | Planned | April | September
TO-27-110 kV A2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A2 | Unknown | Unknown | 111 | Planned | April | September
TO-27-110 kV B1 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | Unknown | Unknown | 111 | Planned | April | September
TO-27-110 kV B2 @ TBG-01 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B2 | Unknown | Unknown | 111 | Planned | April | September
TO-27-RAF-TBG-2-02 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 13 | Planned | April | May
TO-27-RAF-TBG-2-04 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 8 | Planned | April | April
TO-27-BAN-BRI-2-04 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown |  | Planned | May | September
TO-27-BAN-RAF-1-02 | 110kV FEEDER - BANDON 110-RAFFEEN 110-1 | Unknown | Unknown |  | Planned | May | September
TO-27-BRI-T102-03 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown |  | Planned | May | September
TO-27-BAN-110SA1-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BAN-110SA2-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 5 | Planned | May | May
TO-27-BAN-T142-02 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | May | May
TO-27-CHA-MAL-1-01 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | Unknown | Unknown | 6 | Planned | May | May
TO-27-CGG-DMY-1-01 | 110kV FEEDER - CARRIGDANGAN 110-DUNMANWAY 110-1 | Unknown | Unknown | 8 | Planned | May | May
TO-27-CGG-T131-01 | GENERATOR TRANSFORMER - CARRIGDANGAN 110-CARRIGDANGAN 33-T131 | Unknown | Unknown | 8 | Planned | May | May
TO-27-AD-T2014-01 | GENERATOR TRANSFORMER - AGHADA 220-AGHADA G14-T2014 | Unknown | Unknown | 2 | Planned | May | June
TO-27-110 kV A2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110A2 | Unknown | Unknown | 22 | Planned | June | July
TO-27-110 kV B2 @ MR-01 | BUSBAR SECTION - MARINA 110-MARINA 110-110B2 | Unknown | Unknown | 22 | Planned | June | July
TO-27-KBY-KRA-1-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-1 | Unknown | Unknown | 2 | Planned | June | June
TO-27-110 kV B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | Unknown | Unknown | 25 | Planned | June | July
TO-27-RAF-CAP2-01 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | Unknown | Unknown | 10 | Planned | June | June
TO-27-RAF-CAP2-02 | CAPACITOR/SVC/REACTOR - RAFFEEN 110-RAFFEEN 110-CAP2 | Unknown | Unknown | 25 | Planned | June | July
TO-27-BAR-T141-03 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 10 | Reference (Planned) | June | July
TO-27-BAR,T-BAR-1-02 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-BAR,T-CAH-1-01 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 10 | Planned | June | July
TO-27-BAR,T-KRA-1-01 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | Unknown | 5 | Planned | June | July
TO-27-KBY-KRA-2-01 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | Unknown | 100 | Planned | June | November
TO-27-KBY-KRA-2-02 | 110kV FEEDER - KILBARRY 110-KNOCKRAHA 110-2 | Unknown | Unknown |  | Planned | June | November
TO-27-KBY-MAL-1-01 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | Unknown | Unknown | 6 | Planned | June | July
TO-27-KBY-MAL-1-02 | 110kV FEEDER - KILBARRY 110-MALLOW 110-1 | Unknown | Unknown | 70 | Planned | June | October
TO-27-BAN-110SA1-04 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown |  | Planned | July | September
TO-27-BAN-110SA2-03 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown |  | Planned | July | September
TO-27-BAN-T142-03 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | Unknown |  | Reference (Planned) | July | September
TO-27-BAN-BRI-2-01 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 8 | Planned | July | July
TO-27-BAN-BRI-2-03 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 15 | Planned | July | July
TO-27-BRI-T102-01 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown | 15 | Planned | July | July
TO-27-110 kV A2 @ KBY-03 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | Unknown | Unknown |  | Planned | July | July
TO-27-KRA-LYT-1-01 | 110kV FEEDER - KNOCKRAHA 110-LYSAGHTSTOWN 110-1 | Unknown | Unknown | 3 | Planned | July | July
TO-27-110 kV B2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110B2 | Unknown | Unknown | 55 | Planned | July | September
TO-27-MID-110SA1-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | Unknown | Unknown | 80 | Planned | July | November
TO-27-MID-110SA2-03 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | Unknown | Unknown | 80 | Planned | July | November
TO-27-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | Unknown | Unknown | 80 | Reference (Planned) | July | November
TO-27-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | Unknown | Unknown | 5 | Planned | July | July
TO-27-MID-WHI-1-02 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | Unknown | Unknown | 80 | Planned | July | November
TO-27-220 kV A1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220A1 | Unknown | Unknown | 106 | Planned | August | December
TO-27-220 kV B1 @ KRA-02 | BUSBAR SECTION - KNOCKRAHA 220-KNOCKRAHA 220-220B1 | Unknown | Unknown | 106 | Planned | August | December
TO-27-KRA-220K1-04 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220K1 | Unknown | Unknown | 106 | Planned | August | December
TO-27-KRA-220SA1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SA1-2CB | Unknown | Unknown | 106 | Planned | August | December
TO-27-KRA-220SB1-2CB-03 | COUPLER/SECTIONALISING CB - KNOCKRAHA 220-KNOCKRAHA 220-220SB1-2CB | Unknown | Unknown | 106 | Planned | August | December
TO-27-BAN-110SA1-02 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA1 | Unknown | Unknown | 5 | Planned | August | August
TO-27-BAN-110SA2-01 | SECTIONALISING DISCONNECT - BANDON 110-BANDON 110-110SA2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-BAN-BRI-2-05 | 110kV FEEDER - BANDON 110-BRINNY 110-2 | Unknown | Unknown | 5 | Planned | August | August
TO-27-BAN-T142-01 | DISTRIBUTION TRANSFORMER - BANDON 110-BANDON 38-T142 | Unknown | Unknown | 5 | Reference (Planned) | August | August
TO-27-BRI-T102-02 | TSO CUSTOMER TRANSFORMER - BRINNY 110-BRINNY 10-T102 | Unknown | Unknown | 5 | Planned | August | August
TO-27-110 kV A2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A2 | Unknown | Unknown | 50 | Planned | September | November
TO-27-110 kV B2 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B2 | Unknown | Unknown | 50 | Planned | September | November
TO-27-110 kV B2 @ RAF-03 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV B2 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-RAF-TBG-2-06 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-RAF-TBG-2-07 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 2 | Planned | September | September
TO-27-BRY-RAF-1-01 | 110kV FEEDER - BARNAHELY 110-RAFFEEN 110-1 | Unknown | Unknown |  | Reference (Planned) | September | November
TO-27-CRO-KBY-1-01 | 110kV FEEDER - COOLROE 110-KILBARRY 110-1 | Unknown | Unknown | 10 | Planned | September | September
TO-27-110 kV B1/B2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1-B2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-RAF-110K1-2-01 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | Unknown | Unknown |  | Planned | September | September
TO-27-TBG-110K1-2-02 | COUPLER/SECTIONALISING CB - TRABEG 110-TRABEG 110-110K1-2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-KBY-MR-2-02 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-110 kV A1/A2 @ RAF-01 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110A1-A2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-RAF-110K1-2-02 | COUPLER/SECTIONALISING CB - RAFFEEN 110-RAFFEEN 110-110K1-2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-CRO-IA-1-01 | 110kV FEEDER - COOLROE 110-INNISCARRA 110-1 | Unknown | Unknown | 4 | Planned | September | September
TO-27-110 kV B1 @ RAF-02 | BUSBAR SECTION - RAFFEEN 110-RAFFEEN 110-110B1 | Unknown | Unknown | 40 | Planned | September | November
TO-27-RAF-TBG-2-05 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-2 | Unknown | Unknown | 5 | Planned | September | September
TO-27-110 kV B1 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110B1 | Unknown | Unknown | 2 | Planned | September | September
TO-27-110 kV A1 @ TBG-02 | BUSBAR SECTION - TRABEG 110-TRABEG 110-110A1 | Unknown | Unknown | 3 | Planned | September | September
TO-27-110 kV A2 @ KBY-04 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | Unknown | Unknown | 3 | Planned | September | September
TO-27-DMY-MAC-1-01 | 110kV FEEDER - DUNMANWAY 110-MACROOM 110-1 | Unknown | Unknown | 5 | Planned | October | October
TO-27-110 kV A1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110A1 | Unknown | Unknown | 60 | Planned | October | December
TO-27-110 kV B1 @ KRA-01 | BUSBAR SECTION - KNOCKRAHA 110-KNOCKRAHA 110-110B1 | Unknown | Unknown | 60 | Planned | October | December
TO-27-110 kV A2 @ KBY-02 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | Unknown | Unknown | 1 | Planned | October | October
TO-27-KBY-MR-2-03 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 1 | Planned | October | October
TO-27-BAR-T141-02 | DISTRIBUTION TRANSFORMER - BARRYMORE 110-BARRYMORE 38-T141 | Unknown | Unknown | 7 | Reference (Planned) | November | November
TO-27-BAR,T-BAR-1-01 | 110kV FEEDER - BARRYMORE tee-BARRYMORE 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-BAR,T-CAH-1-02 | 110kV FEEDER - BARRYMORE tee-CAHIR 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-BAR,T-KRA-1-02 | 110kV FEEDER - BARRYMORE tee-KNOCKRAHA 110-1 | Unknown | Unknown | 7 | Planned | November | November
TO-27-COW-WHI-1-01 | 110kV FEEDER - COW CROSS 110-WHITEGATE 110-1 | Unknown | Unknown | 3 | Planned | November | November
TO-27-RAF-TBG-1-03 | 110kV FEEDER - RAFFEEN 110-TRABEG 110-1 | Unknown | Unknown | 1 | Planned | November | November
TO-27-110 kV A2 @ KBY-01 | BUSBAR SECTION - KILBARRY 110-KILBARRY 110-110A2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-KBY-MR-2-04 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown | 1 | Planned | November | November
TO-27-KBY-MR-2-01 | 110kV FEEDER - KILBARRY 110-MARINA 110-2 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV A2 @ MR-02 | BUSBAR SECTION - MARINA 110-MARINA 110-110A2 | Unknown | Unknown |  | Planned | November | November
TO-27-110 kV B2 @ MR-02 | BUSBAR SECTION - MARINA 110-MARINA 110-110B2 | Unknown | Unknown |  | Planned | November | November