## Wks 44 - 45
Report covers outages commencing/returning/spanning the period: 26/10/2026 - 08/11/2026
Outages commencing/returning in Week 44
OUTAGE ID | PLANT |  | Week 44 | [6 empty] | Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-26-110 kV B2 @ ARK-02 | ARKLOW 110 kV B2 | bar: Week 44 Mo 26; Week 44 Sa 31 to Week 45 Mo 9
TO-26-LSA-T131-03 | LISLEA T131
TO-26-AA GIS-T102-02 | ARDNACRUSHA GIS T102
TO-26-CF-CLO-2-03 | CATHALEENS FALL CLOGHER 2
TO-26-LIS-T131-06 | LISDRUM T131
TO-26-CSH-CAP1-02 | CASHLA CAP1
TO-26-220 kV A1 @ CBT-01 | CASTLEBAGOT 220 kV A1
TO-26-220 kV A2 @ CBT-03 | CASTLEBAGOT 220 kV A2
TO-26-CBT-220K1-02 | CASTLEBAGOT 220K1
TO-26-CBT-220K2-03 | CASTLEBAGOT 220K2
TO-26-CBT-220SA1-2CB-01 | CASTLEBAGOT 220SA1-2CB
TO-26-GWE-T101-01 | GORTAWEE T101
TO-26-110 kV A2 @ KLS-01 | KELLIS 110 kV A2
TO-26-110 kV B2 @ KLS-02 | KELLIS 110 kV B2
TO-26-WOO-T4204-07 | WOODLAND T4204
TO-26-110 kV A2 @ CSH-01 | CASHLA 110 kV A2 | bar: Week 44 Sa 31 to Week 45 We 4
TO-26-110 kV B2 @ CSH-01 | CASHLA 110 kV B2 | bar: Week 44 Sa 31 to Week 45 We 4
TO-26-CSH-GAL GIS-4-01 | CASHLA GALWAY GIS 4 | bar: Week 44 Sa 31 to Week 45 We 4
TO-26-110 kV A2 @ SNU-04 | SNUGBOROUGH 110 kV A2 | bar: Week 44 Sa 31 to Week 45 We 4
TO-26-110 kV B2 @ SNU-03 | SNUGBOROUGH 110 kV B2 | bar: Week 44 Sa 31 to Week 45 We 4
TO-26-SNU-110K2-07 | SNUGBOROUGH 110K2 | bar: Week 44 Sa 31 to Week 45 We 4
TO-26-SNU-110SA1-2CB-06 | SNUGBOROUGH 110SA1-2CB | bar: Week 44 Sa 31 to Week 45 We 4
TO-26-SNU-110SB1-2CB-03 | SNUGBOROUGH 110SB1-2CB | bar: Week 44 Sa 31 to Week 45 We 4
TO-26-SNU-T104-01 | SNUGBOROUGH T104 | bar: Week 44 Sa 31 to Week 45 We 4
TO-26-DFR-T122-15 | DUNFIRTH T122 | bar: Week 44 Sa 31 to Week 45 Fr 6
TO-26-DFR,T-DFR-1-14 | DUNFIRTH tee DUNFIRTH | bar: Week 44 Sa 31 to Week 45 Fr 6
TO-26-DFR,T-KIN-1-14 | DUNFIRTH tee KINNEGAD | bar: Week 44 Sa 31 to Week 45 Fr 6
TO-26-DFR,T-RNW-1-17 | DUNFIRTH tee RINAWADE | bar: Week 44 Sa 31 to Week 45 Fr 6
TO-26-MAY-RNW-1-07 | MAYNOOTH RINAWADE | bar: Week 44 Sa 31 to Week 45 Fr 6
TO-26-RNW-110SA1-01 | RINAWADE 110SA1 | bar: Week 44 Sa 31 to Week 45 Fr 6
TO-26-RNW-110SA2-01 | RINAWADE 110SA2 | bar: Week 44 Sa 31 to Week 45 Fr 6
TO-26-RNW-T121-04 | RINAWADE T121 | bar: Week 44 Sa 31 to Week 45 Fr 6
TO-26-RNW-T122-03 | RINAWADE T122 | bar: Week 44 Sa 31 to Week 45 Fr 6
TO-26-CVW-COW-1-01 | CASTLEVIEW COW CROSS | bar: Week 44 Sa 31 to Week 45 Mo 9
TO-26-110 kV A2 @ RAF-03 | RAFFEEN 110 kV A2 | bar: Week 44 Sa 31 to Week 45 Mo 9
TO-26-110 kV B2 @ RAF-05 | RAFFEEN 110 kV B2 | bar: Week 44 Sa 31 to Week 45 Mo 9
TO-26-RAF-CAP2-02 | RAFFEEN CAP2 | bar: Week 44 Sa 31 to Week 45 Mo 9
TO-26-MP GIS-400SA1-2CB-01 | MONEYPOINT GIS 400SA1-2CB
TO-26-MP GIS-400SA1-3CB-01 | MONEYPOINT GIS 400SA1-3CB
TO-26-AA GIS-T104-02 | ARDNACRUSHA GIS T104
TO-26-CF-CLO-2-04 | CATHALEENS FALL CLOGHER 2
TO-26-CBT-INC-2-03 | CASTLEBAGOT INCHICORE 2
TO-26-220 kV A6 @ INC-01 | INCHICORE 220 kV A6
TO-26-220 kV B6 @ INC-01 | INCHICORE 220 kV B6
TO-26-INC-SA6-8CB-04 | INCHICORE 220SA6-8CB
TO-26-INC-SB6-8CB-04 | INCHICORE 220SB6-8CB
TO-26-AUG-KPG-1-02 | AUGHINISH KILPADDOGE | bar: Su 25 to Week 44 Mo 26
TO-26-110 kV A1 @ CKG-03 | CORKAGH 110 kV A1 | bar: Su 25 to Week 44 Mo 26
TO-26-CKG-110SA1-2CB-04 | CORKAGH 110SA1-2CB | bar: Su 25 to Week 44 Mo 26
TO-26-CKG-110SA1-3CB-06 | CORKAGH 110SA1-3CB | bar: Su 25 to Week 44 Mo 26
TO-26-DFR-T122-14 | DUNFIRTH T122 | bar: Su 25 to Week 44 Mo 26
TO-26-DFR,T-DFR-1-13 | DUNFIRTH tee DUNFIRTH | bar: Su 25 to Week 44 Mo 26
TO-26-DFR,T-KIN-1-13 | DUNFIRTH tee KINNEGAD | bar: Su 25 to Week 44 Mo 26
TO-26-DFR,T-RNW-1-16 | DUNFIRTH tee RINAWADE | bar: Su 25 to Week 44 Mo 26
TO-26-110 kV A1 @ LLA-03 | LENALEA 110 kV A1 | bar: Su 25 to Week 44 Mo 26
TO-26-110 kV B1 @ LLA-03 | LENALEA 110 kV B1 | bar: Su 25 to Week 44 Mo 26
TO-26-LLA-110K1-05 | LENALEA 110K1 | bar: Su 25 to Week 44 Mo 26
TO-26-LIS-110SA1-08 | LISDRUM 110SA1 | bar: Su 25 to Week 44 Mo 26
TO-26-LIS-110SA2-08 | LISDRUM 110SA2 | bar: Su 25 to Week 44 Mo 26
TO-26-LIS-CAP1-05 | LISDRUM CAP1 | bar: Su 25 to Week 44 Mo 26
TO-26-LIS-LOU-1-04 | LISDRUM LOUTH | bar: Su 25 to Week 44 Mo 26
Report covers outages commencing/returning/spanning the period: 26/10/2026 - 08/11/2026
Outages commencing/returning in Week 44
OUTAGE ID | PLANT | Week 44 Mo 26: Week 44; Week 45 Mo 2: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-26-LIS-T131-04 | LISDRUM T131 | bar: Su 25 to Week 44 Fr 30
TO-26-LIS-T141-03 | LISDRUM T141 | bar: Su 25 to Week 44 Fr 30
TO-26-110 kV A1 @ MAY-01 | MAYNOOTH 110 kV A1 | bar: Su 25 to Week 44 Fr 30
TO-26-110 kV B1 @ MAY-01 | MAYNOOTH 110 kV B1 | bar: Su 25 to Week 44 Fr 30
TO-26-220 kV A1 @ MAY-05 | MAYNOOTH 220 kV A1 | bar: Su 25 to Week 44 Fr 30
TO-26-220 kV B1 @ MAY-05 | MAYNOOTH 220 kV B1 | bar: Su 25 to Week 44 Fr 30
TO-26-MAY-T2101-02 | MAYNOOTH T2101 | bar: Su 25 to Week 44 Fr 30
TO-26-CLE-CDU-1-03 | CLONEE CORDUFF | bar: Week 44 Sa 31 to Week 44 Su 1
TO-26-DRY-110SA1-04 | DRYBRIDGE 110SA1 | bar: Week 44 Sa 31 to Week 44 Su 1
TO-26-DRY-110SA2-04 | DRYBRIDGE 110SA2 | bar: Week 44 Sa 31 to Week 44 Su 1
TO-26-DRY-OBE-1-03 | DRYBRIDGE OLDBRIDGE | bar: Week 44 Sa 31 to Week 44 Su 1
TO-26-DRY-T141-03 | DRYBRIDGE T141 | bar: Week 44 Sa 31 to Week 44 Su 1
TO-26-DSN-MP GIS-1-10 | DUNSTOWN MONEYPOINT GIS | bar: Su 25 to Week 44 Sa 31
TO-26-GGO-RAF-1-02 | GLANAGOW RAFFEEN | bar: Su 25 to Week 44 Sa 31
Outages commencing/returning in Week 45
OUTAGE ID | PLANT | Week 44 Mo 26: Week 44; Week 45 Mo 2: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-26-AUN-T123-03 | AUNGIERSTOWN T123
TO-26-110 kV A2 @ KLN GIS-02 | KILLONAN GIS 110 kV A2
TO-26-110 kV B2 @ KLN GIS-02 | KILLONAN GIS 110 kV B2
TO-26-KLN GIS-110SA1-2CB-02 | KILLONAN GIS 110SA1-2CB
TO-26-KLN GIS-110SA2-4CB-02 | KILLONAN GIS 110SA2-4CB
TO-26-KLN GIS-110SB1-2CB-02 | KILLONAN GIS 110SB1-2CB
TO-26-KLN GIS-110SB2-4CB-02 | KILLONAN GIS 110SB2-4CB
TO-26-KLN GIS-T2102-04 | KILLONAN GIS T2102
TO-26-DJG-TRL-1-06 | DROMBEG TRALEE | bar: Week 45 We 4
TO-26-OBE-T123-03 | OLDBRIDGE T123 | bar: Week 45 We 4
TO-26-OUG,T-TRL-1-03 | OUGHTRAGH tee TRALEE | bar: Week 45 We 4
TO-26-TRL-110SA1-2CB-02 | TRALEE 110SA1-2CB | bar: Week 45 We 4
TO-26-TRL-CAP2-04 | TRALEE CAP2 | bar: Week 45 We 4
TO-26-TRL-T142-02 | TRALEE T142 | bar: Week 45 We 4
TO-26-GWE-T102-02 | GORTAWEE T102 | bar: Week 45 We 4 to Week 45 Th 5
TO-26-BUF-T131-02 | BUFFY T131 | bar: Week 45 We 4 to Week 45 Fr 6
TO-26-CRA-TTU-1-01 | CRANE TULLABEG | bar: Week 45 We 4 to Week 45 Fr 6
TO-26-DSN-MAY-2-01 | DUNSTOWN MAYNOOTH 2 | bar: Week 45 We 4 to Week 45 Fr 6
TO-26-110 kV A1 @ LOU-05 | LOUTH 110 kV A1 | bar: Week 45 We 4 to Week 45 Fr 6
TO-26-110 kV B1 @ LOU-05 | LOUTH 110 kV B1 | bar: Week 45 We 4 to Week 45 Fr 6
TO-26-LOU-T2101-03 | LOUTH T2101 | bar: Week 45 We 4 to Week 45 Fr 6
TO-26-NW-PB-1-01 | NORTH WALL POOLBEG | bar: Week 45 We 4 to Week 45 Fr 6
TO-26-CBR-DLT-1-01 | CASTLEBAR DALTON | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-CLO-DRM-1-02 | CLOGHER DRUMKEEN | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-110 kV A1 @ MR-01 | MARINA 110 kV A1 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-110 kV B1 @ MR-01 | MARINA 110 kV B1 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-110 kV A4 @ MAY-03 | MAYNOOTH 110 kV A4 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-110 kV B4 @ MAY-03 | MAYNOOTH 110 kV B4 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-220 kV A2 @ MAY-02 | MAYNOOTH 220 kV A2 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-220 kV B2 @ MAY-02 | MAYNOOTH 220 kV B2 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-MAY-T2104-01 | MAYNOOTH T2104 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-400 kV B2 @ MP GIS-01 | MONEYPOINT GIS 400 kV B2 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-400 kV B4 @ MP GIS-01 | MONEYPOINT GIS 400 kV B4 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-MP GIS-400K4-02 | MONEYPOINT GIS 400K4 | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-MP GIS-400SB1-2CB-05 | MONEYPOINT GIS 400SB1-2CB | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-MP GIS-400SB2-4CB-01 | MONEYPOINT GIS 400SB2-4CB | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-CTN-KLN-1-01 | CAUTEEN KILLONAN | bar: Su 25 to Week 44 Su 1
TO-26-CSH-PRO-1-01 | CASHLA PROSPECT | bar: Week 45 We 4 to Week 45 Mo 9
TO-26-KLN-SNG-1-01 | KILLONAN SINGLAND | bar: Su 25 to Week 44 Su 1; Week 45 We 4 to Week 45 Th 5
TO-26-KPG-TB-1-01 | KILPADDOGE TARBERT 1 | bar: Su 25 to Week 44 Su 1; Week 45 We 4 to Week 45 Th 5
TO-26-KPG-T2102-04 | KILPADDOGE T2102 | bar: Week 45 Fr 6
Report covers outages commencing/returning/spanning the period: 26/10/2026 - 08/11/2026
Outages commencing/returning in Week 45 | PLANT | Week 44 Mo 26: Week 44; Week 45 Mo 2: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-26-ATY-PLS-1-10 | ATHY PORTLAOISE
TO-26-ATY-PLS-1-01
TO-26-BLK-T142-03 | BLAKE T142
TO-26-BLK,T-BLK-1-04 | BLAKE tee BLAKE
TO-26-BLK,T-MAY-1-05 | BLAKE tee MAYNOOTH
TO-26-BLK,T-NEW-1-08 | BLAKE tee NEWBRIDGE
Outages spanning Weeks 44-45
OUTAGE ID | PLANT | Week 44 Mo 26: Week 44; Week 45 Mo 2: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-CLW-KLS-2-01 | CARLOW KELLIS 2
TO-26-CD-KBY-1-03 | CARRIGADROHID KILBARRY
TO-26-CGG-T131-02 | CARRIGDANGAN T131
TO-26-CBR-SVC-02 | CASTLEBAR SVC
TO-26-CBR-SVC-01
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DRY-LOU-1-01 | DRYBRIDGE LOUTH
TO-26-DRY-T141-01 | DRYBRIDGE T141
TO-26-DSN-T4201-03 | DUNSTOWN T4201
TO-26-FIN-FIN GIS-2-01 | FINGLAS FINGLAS GIS 2
TO-26-FIN GIS-SVN-1-01 | FINGLAS GIS STEPHENSTOWN
TO-26-FIN-T2104-01 | FINGLAS T2104
TO-26-FLA-LOU-1-08 | FLAGFORD LOUTH
TO-26-GAR-GOR-1-03 | GARBALLAGH GORMAN
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-110 kV A1 @ KBY-05 | KILBARRY 110 kV A1
TO-26-KLN-220K1-2-03 | KILLONAN 220K1-2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-M/CAP1-02 | LETTERKENNY M/CAP1
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-110 kV A1 @ LOU-07 | LOUTH 110 kV A1
TO-26-110 kV B1 @ LOU-06 | LOUTH 110 kV B1
TO-26-LOU-AT3-07 | LOUTH AT3
TO-26-MR-T107-01 | MARINA T107
TO-26-MTN-MUN-2-03 | MONETEEN MUNGRET 2
TO-26-MUN-T102-02 | MUNGRET T102
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-NEW-T141-04 | NEWBRIDGE T141
TO-26-PB-R2001-02 | POOLBEG R2001
TO-26-PB-R2001-03
TO-26-RNW-T122-04 | RINAWADE T122
TO-26-220 kV A1 @ TB-02 | TARBERT 220 kV A1
TO-26-220 kV B1 @ TB-02 | TARBERT 220 kV B1
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-WEX-CAP4-06 | WEXFORD CAP4