## Wks 46 - 47
Report covers outages commencing/returning/spanning the period: 09/11/2026 - 22/11/2026
Outages commencing/returning in Week 46
OUTAGE ID | PLANT |  | Week 46 | [6 empty] | Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-26-AUN-T121-03 | AUNGIERSTOWN T121 | bar: Week 46 Mo 9
TO-26-110 kV A1/A2 @ LOU-03 | LOUTH 110 kV A1/A2 | bar: Week 46 Mo 9 to Week 46 Tu 10
TO-26-KUD-T101-01 | KILMAHUD T101 | bar: Week 46 Mo 9 to Week 46 Fr 13
TO-26-LIM-RAT-1-03 | LIMERICK RATHKEALE | bar: Week 46 Mo 9 to Week 46 Fr 13
TO-26-MLN-T124-04 | MULLAGHARLIN T124 | bar: Week 46 Mo 9 to Week 46 Fr 13
TO-26-220 kV A1 @ WOO-04 | WOODLAND 220 kV A1 | bar: Week 46 Mo 9 to Week 46 Fr 13
TO-26-220 kV B1 @ WOO-04 | WOODLAND 220 kV B1 | bar: Week 46 Mo 9 to Week 46 Fr 13
TO-26-WOO-T4201-03 | WOODLAND T4201 | bar: Week 46 Mo 9 to Week 46 Fr 13
TO-26-110 kV A2 @ CLA-01 | CLASHAVOON 110 kV A2 | bar: Week 46 Mo 9 to Week 47 Tu 17
TO-26-110 kV B2 @ CLA-01 | CLASHAVOON 110 kV B2 | bar: Week 46 Mo 9 to Week 47 Tu 17
TO-26-CLA-T2102-01 | CLASHAVOON T2102 | bar: Week 46 Mo 9 to Week 47 Tu 17
TO-26-110 kV A1 @ CKG-04 | CORKAGH 110 kV A1 | bar: Week 46 Mo 9 to Week 47 Fr 20
TO-26-110 kV B1 @ CKG-03 | CORKAGH 110 kV B1 | bar: Week 46 Mo 9 to Week 47 Fr 20
TO-26-CKG-110SA1-2CB-06 | CORKAGH 110SA1-2CB | bar: Week 46 Mo 9 to Week 47 Fr 20
TO-26-CKG-110SA1-3CB-07 | CORKAGH 110SA1-3CB | bar: Week 46 Mo 9 to Week 47 Fr 20
TO-26-CKG-110SB1-2CB-06 | CORKAGH 110SB1-2CB | bar: Week 46 Mo 9 to Week 47 Fr 20
TO-26-CKG-110SB1-3CB-05 | CORKAGH 110SB1-3CB | bar: Week 46 Mo 9 to Week 47 Fr 20
TO-26-LOU-T2104-06 | LOUTH T2104 | bar: Week 46 Mo 9 to Week 47 Fr 20
TO-26-BRA-NEW-1-03 | BRACKLONE NEWBRIDGE
TO-26-CUS-NEW-1-03 | CUSHALING NEWBRIDGE
TO-26-NEW-110SA1-06 | NEWBRIDGE 110SA1
TO-26-NEW-110SA2-07 | NEWBRIDGE 110SA2
TO-26-COS-FLA-1-05 | CARRICK ON SHANNON FLAGFORD 1 | bar: Week 46 Tu 10
TO-26-220 kV A3 @ KPG-05 | KILPADDOGE 220 kV A3 | bar: Week 46 Tu 10
TO-26-220 kV B3 @ KPG-05 | KILPADDOGE 220 kV B3 | bar: Week 46 Tu 10
TO-26-DJG-KPG-1-01 | DROMBEG KILPADDOGE | bar: Week 46 Tu 10 to Week 46 We 11
TO-26-110 kV B1/B2 @ LOU-03 | LOUTH 110 kV B1/B2 | bar: Week 46 Tu 10 to Week 46 We 11
TO-26-110 kV A1 @ MR-01 | MARINA 110 kV A1 | bar: Week 46 Tu 10 to Week 47 Tu 17
TO-26-110 kV B1 @ MR-01 | MARINA 110 kV B1 | bar: Week 46 Tu 10 to Week 47 Tu 17
TO-26-ATH-CUI-1-02 | ATHLONE CUILLEEN | bar: Week 46 We 11
TO-26-BLM-CUI-1-02 | BELLANAMULLIA CUILLEEN | bar: Week 46 We 11
TO-26-BLM-T101-02 | BELLANAMULLIA T101 | bar: Week 46 We 11
TO-26-220 kV A1 @ DSN-02 | DUNSTOWN 220 kV A1 | bar: Week 46 We 11 to Week 46 Th 12
TO-26-BLU-MUL-1-02 | BLUNDELSTOWN MULLINGAR | bar: Week 46 We 11 to Week 47 Mo 23
TO-26-400 kV B2 @ MP GIS-01 | MONEYPOINT GIS 400 kV B2 | bar: Su 8 to Week 46 We 11
TO-26-400 kV B4 @ MP GIS-01 | MONEYPOINT GIS 400 kV B4 | bar: Su 8 to Week 46 We 11
TO-26-MP GIS-400K4-02 | MONEYPOINT GIS 400K4 | bar: Su 8 to Week 46 We 11
TO-26-MP GIS-400SB1-2CB-05 | MONEYPOINT GIS 400SB1-2CB | bar: Su 8 to Week 46 We 11
TO-26-MP GIS-400SB2-4CB-01 | MONEYPOINT GIS 400SB2-4CB | bar: Su 8 to Week 46 We 11
Outages commencing/returning in Week 47
OUTAGE ID | PLANT | Week 46 Mo 9: Week 46; Week 47 Mo 16: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-26-AUG-110SA1-2CB-02 | AUGHINISH 110SA1-2CB
TO-26-DEN-T132-03 | DEENES T132
TO-26-110 kV B1/B2 @ LOU-02 | LOUTH 110 kV B1/B2
TO-26-TBK-T141-02 | TULLABRACK T141
TO-26-TBK,T-BOL-1-02 | TULLABRACK tee BOOLTIAGH
TO-26-TBK,T-MP GIS-1-02 | TULLABRACK tee MONEYPOINT GIS
TO-26-TBK,T-TBK-1-01 | TULLABRACK tee TULLABRACK
TO-26-LOU-T2104-04 | LOUTH T2104
TO-26-CF-COR-1-02 | CATHALEENS FALL CORRACLASSY | bar: Week 47 Th 19 to Week 47 Fr 20
TO-26-MLN-T123-03 | MULLAGHARLIN T123 | bar: Week 47 Th 19 to Week 47 Fr 20
TO-26-RAF-TBG-2-06 | RAFFEEN TRABEG 2 | bar: Week 47 Th 19 to Week 47 Fr 20
TO-26-BLC-FIN-1-03 | BELCAMP FINGLAS | bar: Week 47 Th 19 to Week 47 Mo 23
TO-26-220 kV A2 @ FIN-10 | FINGLAS 220 kV A2 | bar: Week 47 Th 19 to Week 47 Mo 23
TO-26-220 kV B2 @ FIN-08 | FINGLAS 220 kV B2 | bar: Week 47 Th 19 to Week 47 Mo 23
TO-26-FIN-220K2-12 | FINGLAS 220K2 | bar: Week 47 Th 19 to Week 47 Mo 23
TO-26-FIN-220SA1-2CB-18 | FINGLAS 220SA1-2CB | bar: Week 47 Th 19 to Week 47 Mo 23
Report covers outages commencing/returning/spanning the period: 09/11/2026 - 22/11/2026
Outages commencing/returning in Week 47
OUTAGE ID | PLANT | Week 46 Mo 9: Week 46; Week 47 Mo 16: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-26-FIN-220SB1-2CB-15 | FINGLAS 220SB1-2CB
TO-26-MUL-110SA1-2CB-02 | MULLINGAR 110SA1-2CB
TO-26-MUL-CAP2-04 | MULLINGAR CAP2
TO-26-MUL-T102-02 | MULLINGAR T102
TO-26-MUL-T142-02 | MULLINGAR T142
TO-26-220 kV A1 @ PB-04 | POOLBEG 220 kV A1
TO-26-220 kV A2 @ PB-03 | POOLBEG 220 kV A2
TO-26-220 kV A3 @ PB-02 | POOLBEG 220 kV A3
TO-26-220 kV B1 @ PB-04 | POOLBEG 220 kV B1
TO-26-220 kV B2 @ PB-03 | POOLBEG 220 kV B2
TO-26-220 kV B3 @ PB-02 | POOLBEG 220 kV B3
TO-26-PB-220K2-3-02 | POOLBEG 220K2-3
TO-26-PB-220SA1-2-02 | POOLBEG 220SA1-2
TO-26-PB-220SB1-2-04 | POOLBEG 220SB1-2
TO-26-110 kV A1/A2 @ LOU-02 | LOUTH 110 kV A1/A2
TO-26-400 kV B1 @ MP GIS-03 | MONEYPOINT GIS 400 kV B1
TO-26-400 kV B3 @ MP GIS-02 | MONEYPOINT GIS 400 kV B3
TO-26-MP GIS-400K3-05 | MONEYPOINT GIS 400K3
TO-26-MP GIS-400SB1-2CB-04 | MONEYPOINT GIS 400SB1-2CB
TO-26-MP GIS-400SB1-3CB-01 | MONEYPOINT GIS 400SB1-3CB
TO-26-LIB-T101-01 | LIBERTY STREET T101
TO-26-CTN-KLN-1-01 | CAUTEEN KILLONAN
TO-26-DRY-LOU-1-01 | DRYBRIDGE LOUTH
TO-26-110 kV B2 @ KLS-01 | KELLIS 110 kV B2
TO-26-KLS-KKY-1-07 | KELLIS KILKENNY
TO-26-CLW-KLS-2-01 | CARLOW KELLIS 2
TO-26-110 kV A1 @ KBY-05 | KILBARRY 110 kV A1
TO-26-KLN-SNG-1-01 | KILLONAN SINGLAND
TO-26-MR-T107-01 | MARINA T107
TO-26-110 kV A4 @ MAY-03 | MAYNOOTH 110 kV A4
TO-26-110 kV B4 @ MAY-03 | MAYNOOTH 110 kV B4
TO-26-MAY-110K3-4-06 | MAYNOOTH 110K3-4
TO-26-220 kV A2 @ MAY-02 | MAYNOOTH 220 kV A2
TO-26-220 kV B2 @ MAY-02 | MAYNOOTH 220 kV B2
TO-26-MAY-220K1-2-06 | MAYNOOTH 220K1-2
TO-26-MAY-T2104-01 | MAYNOOTH T2104
TO-26-DRY-T141-01 | DRYBRIDGE T141
Outages spanning Weeks 46-47
OUTAGE ID | PLANT | Week 46 Mo 9: Week 46; Week 47 Mo 16: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-26-AD-ST101-03 | AGHADA ST101
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103
TO-26-110 kV B2 @ ARK-02 | ARKLOW 110 kV B2
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-ATY-PLS-1-01 | ATHY PORTLAOISE
TO-26-BLC-FIN-1-01 | BELCAMP FINGLAS
TO-26-BLC-T2103-01 | BELCAMP T2103
TO-26-CD-KBY-1-03 | CARRIGADROHID KILBARRY
TO-26-CGG-T131-02 | CARRIGDANGAN T131
TO-26-CSH-PRO-1-01 | CASHLA PROSPECT
TO-26-CBR-DLT-1-01 | CASTLEBAR DALTON
TO-26-CBR-SVC-02 | CASTLEBAR SVC
TO-26-CBR-SVC-01
TO-26-CVW-COW-1-01 | CASTLEVIEW COW CROSS
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DSN-T4201-03 | DUNSTOWN T4201
TO-26-FIN-FIN GIS-2-01 | FINGLAS FINGLAS GIS 2
TO-26-FIN GIS-SVN-1-01 | FINGLAS GIS STEPHENSTOWN
TO-26-FIN-T2104-01 | FINGLAS T2104
Report covers outages commencing/returning/spanning the period: 09/11/2026 - 22/11/2026
Outages spanning Weeks 46-47
OUTAGE ID | PLANT | Week 46 Mo 9: Week 46; Week 47 Mo 16: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-26-GAR-GOR-1-03 | GARBALLAGH GORMAN
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-KLN-220K1-2-03 | KILLONAN 220K1-2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-M/CAP1-02 | LETTERKENNY M/CAP1
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-110 kV A1 @ LOU-08 | LOUTH 110 kV A1
TO-26-110 kV B1 @ LOU-07 | LOUTH 110 kV B1
TO-26-LOU-AT3-08 | LOUTH AT3
TO-26-LOU-AT3-07
TO-26-MTN-MUN-2-03 | MONETEEN MUNGRET 2
TO-26-MP GIS-T4003-02 | MONEYPOINT GIS T4003
TO-26-MUN-T102-02 | MUNGRET T102
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-NEW-T141-04 | NEWBRIDGE T141
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-PB-R2001-02
TO-26-RNW-T122-04 | RINAWADE T122
TO-26-220 kV A1 @ TB-02 | TARBERT 220 kV A1
TO-26-220 kV B1 @ TB-02 | TARBERT 220 kV B1
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-WEX-CAP4-06 | WEXFORD CAP4